ASUNAFO SOUTH DISTRICT ASSEMBLY

2021 ANNUAL PROGRESS REPORT

(2018-2021) MTDP

FEBRUARY 2022

PREPARED BY: …………………………………………........

DISTRICT PLANNING COORDINATING UNIT

ASUNAFO SOUTH DISTRICT ASSEMBLY

…………………………………………………………………………

TABLE OF CONTENTS

LISTS OF TABLES	II

LIST OF FIGURES	III

ACRONYMS	IV

CHAPTER ONE	1

1.0 INTRODUCTION	1

1.1 Status of Implementation of the Medium Term Development Plan (2018-2021)	1

1.2 Purpose of the Monitoring and Evaluation	6

1.3 Processes Involved and Difficulties Encountered	7

CHAPTER TWO	9

2.0 MONITORING AND EVALUATION ACTIVITIES REPORT	9

2.2 Programmes/Projects Status	9

2.3 Funding Sources	28

2.4 UPDATE ON INDICATORS AND TARGETS	32

2.5 ECONOMIC DEVELOPMENT	36

2.6 SOCIAL DEVELOPMENT	38

2.7 ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENT	39

2.8 GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY	40

2.9 District Specific Indicators	40

2.10 Update on Critical Development and Poverty Issues	44

Livelihood Empowerment against Poverty (LEAP)	46

Youth Employment Agency (YEA)	47

2.11 Evaluation and Participatory Monitoring & Evaluation	49

CHAPTER THREE	54

3.0 THE WAY FORWARD	54

3.1.1 Key Issues Addressed	54

3.1.2 Key Issues yet to be Addressed	54

3.1.3 Recommendations	55

3.1.4 Conclusion	55

LISTS OF TABLES

TABLE 1 STATUS OF IMPLEMENTATION OF THE MEDIUM TERM DEVELOPMENT PLAN (2018-2021)	1

TABLE 2 DETAILS OF ANNUAL ACTION PLAN IMPLEMENTED UNDER AGENDA FOR JOBS POLICY FRAMEWORK	3

TABLE 3 EDUCATION SUB-SECTOR	10

TABLE 4 HEALTH SUB-SECTOR	13

TABLE 5 WATER AND SANITATION	14

TABLE 6 LOCAL ECONOMIC DEVELOPMENT	15

TABLE 7 MANAGEMENT AND ADMINISTRATION	16

TABLE 8 ROADS INFRASTRUCTURE	17

TABLE 9 PROGRAMMES REGISTER FOR 2021	19

TABLE 10 FUNDING SOURCES	30

TABLE 11 UPDATE ON DISBURSEMENTS FROM FUNDING SOURCES	32

TABLE 12 PERFORMANCE INDICATORS AT THE DISTRICT LEVEL	33

TABLE 13 PRESENTS THE MONITORING INDICATORS, BASELINES AND TARGETS OF THE DISTRICT SPECIFIC INDICATORS	40

TABLE 14 CRITICAL DEVELOPMENT AND POVERTY ISSUES	45

TABLE 15 ENROLMENT UNDER THE NATION BUILDERS CORPS (NABCO)	46

TABLE 16 LIST OF BENEFICIARY SCHOOLS UNDER THE SCHOOL FEEDING PROGRAMME IN THE DISTRICT WITHIN THE FOURTH QUARTER, 2021	47

TABLE 17 SHOWING NUMBER OF SCHOOLS AND NUMBER OF STUDENTS ENROLLED UNDER THE FSHSP IN THE DISTRICT	48

TABLE 19 PARTICIPATORY M&E	52

TABLE 20 LIST OF MONITORING TEAM	55

# LIST OF FIGURES

FIGURE 1 PROPORTION OF ANNUAL ACTION PLAN IMPLEMENTED WITH THE PLAN PERIOD	2

FIGURE 2 ANNUAL ACTION PLAN IMPLEMENTED WITHIN THE PLAN PERIOD (2018-2021)	4

FIGURE 3 REVENUE PERFORMANCE UPDATE	31

FIGURE 4 ENROLMENT UNDER THE NATION BUILDERS CORPS(NABCO)	46

FIGURE 5. PERCENTAGE OF MALE AND FEMALE IN THE FSHSP	49

# ACRONYMS

AAP			Annual Action Plan

AEAs			Agricultural Extension Agents

AIDS			Acquired Immune Deficiency Syndrome

APR			Annual Progress Report

ASDA			Asunafo South District Assembly

DACF			District Assembly Common Fund

DACF-RFG		District Assembly Common Fund-Responsive Factor Grant

DDF			District Development Facility

DPCU			District Planning Coordinating Unit

GETFUND		Ghana Education Trust Fund

GHS			Ghana Health Service

GIZ			German Agency for International Cooperation

GSGDA		                Ghana Shared Growth and Development Agenda

HIV			Human Immune Deficiency Virus

IGF			Internally Generated Funds

JHS			Junior High School

SHS			Senior High School

M & E			Monitoring and Evaluation

MCHNP		                Maternal, Child Health and Nutrition Programme

MTDP			Medium Term Development Plan

NABCO		                 Nation Builders Corps

NADMO		                National Disaster Management Organization

NDPC			National Development Planning Commission

NGO			Non-Governmental Organization

ODF			Open Defecation Free

PFJ			Planting for Food and Jobs

RCC			Regional Coordinating Council

RPCU			Regional Planning and Coordinating Unit

SDGs			Sustainable Development Goals

SHS			Senior High School

SWP			Sanitation and Water Project

YEA			Youth Employment Agency

EXECUTIVE SUMMARY

The Local Governance Act, (Act 936) of 2016 enjoins all District Assemblies to plan, implement and source for funding for their development programmes in their respective jurisdictions.  In line with the above, all Districts are mandated to prepare their plans based on the existing conditions and ensure that their plans are fully implemented to achieve the desired impact.

The LI 2232 further required the districts to prepare and submit quarterly and annually progress report to the NDPC through the regional coordinating council. The ultimate goal of the District Medium-Term Development Plan 2018-2021 was to achieve a just, free and prosperous District with high levels of household income and broad-based socio-economic development.

The methodologies deployed in the conduct of monitoring and evaluation by the district included the gathering of primary data through questionnaires, interviews, focus group discussions, observations and monitoring checklists. Also, a standard reporting template was developed for all departments, agencies, institutions and district sub- structures to ensure uniformity in data presentation. Secondary data were also collated from departmental progress reports and projects site inspection reports from the monitoring team.

The report is presented in three (3) chapters.

Chapter one (1) presents an introduction which entails the summary of achievements and challenges with the implementation of the District Annual Action Plan for 2021, the purpose of the Monitoring and Evaluation (M&E) activity for the year and processes involved as well as the challenges encountered.

Chapter two (2) presents details on the Monitoring and Evaluation activities which entails the assessment of program/project status, updates on funding sources and disbursements, updates on indicators and targets as well as updates on critical development and poverty issues. It also presents findings and recommendations on development evaluations conducted during the year and findings on participatory evaluation conducted.

Lastly, Chapter three (3) is focused on key issues addressed and those yet to be addressed as well as recommendations and the way forward

# CHAPTER ONE

# 1.0 INTRODUCTION

The preparation of Annual Progress Report (APR) is a requirement on the Assembly to account on the state of implementation of programmes and projects. This chapter focuses on the status of implementation of MTDP (2018-2021), the purpose of Monitoring & Evaluation as well as the processes involved and the difficulties encountered in monitoring and evaluation of projects and programmes within the District. This report is a compilation of various Annual Progress Reports from the Departments and Units of the Assembly and the achievement of progress made by the Assembly in the implementation of the 2021 Annual Action Plan.

## 1.1 STATUS OF IMPLEMENTATION OF THE MEDIUM TERM DEVELOPMENT PLAN (2018-2021)

The Annual Action Plan (AAP)-2021 was derived from the Medium Term Development Plan 2018-2021 under the National Development Framework, An Agenda for Jobs: Creating Prosperity and Equal Opportunities for All. The Plan had the goal of “achieving sustainable development through the quick deployment of environmentally sound and basic socio-economic Infrastructure leading to improved living conditions of the people”.

Table 1.1 presents the details on the proportion of the MTDP implemented by the end of the year, 2021. It also indicates percentage of the Annual Action Plans performed in diverse levels of completion in yearly basis. As indicated in table 1, Percentage of interventions is 0 because the district had no abandoned interventions within the plan period. Also the district had no yet to start interventions within the plan period and that’s the reason for the zero (0) figures.

TABLE 1 STATUS OF IMPLEMENTATION OF THE MEDIUM TERM DEVELOPMENT PLAN (2018-2021)

| Indicators | Baseline 2017 | Actual 2018 | Actual 2019 | Actual 2020 | Target 2021 | Actual 2021 |
| --- | --- | --- | --- | --- | --- | --- |
| Proportion of the Annual Action Plan implemented by the end of the year, 2021 | 89.8 | 90.0 | 90.4 | 91.8 | 100 | 91.6 |
| - Percentage completed | 49.8 | 50.0 | 49.3 | 51.6 | 100 | 52.2 |
| - Percentage of ongoing interventions | 40.0 | 40.0 | 41.1 | 40.2 | 0 | 39.2 |
| - Percentage of interventions abandoned | 0 | 0 | 0 | 0 | 0 | 0 |
| - Percentage of interventions yet to start | 10.2 | 10 | 9.6 | 8.2 | 0 | 8.5 |
| - Percentage of interventions executed outside the plan | 0 | 0 | 0 | 0 | 0 | 0 |
| Proportion of the overall Medium Term Development Plan Implemented | - | 23.5 | 44.8 | 72.9 | 100 | 93.7 |

From figure 1, below the proportion of the AAP implemented by end of year had a significant improvement from 2017(89.8) to 2019(90.4) and had a sharp improvement from 2019(90.4) to 2020(91.8) .it insignificantly dropped by 0.4% in 2021(91.6). The sharp improvement in 2020 is as a results of presidential elections where a lot of projects and programmes are being implemented during the period of elections. The results from the drop of percentage implemented in 2021 was as a results of non-release of DACF for the execution of projects in the year 2021 as a result of delay in the appointment of MMDCEs in the country.

FIGURE 1 PROPORTION OF ANNUAL ACTION PLAN IMPLEMENTED WITH THE PLAN PERIOD

Table 2. As indicated below, the Annual Action Plan for 2021 had a total of 178 activities earmarked for implementation. Out of the 178 activities, 163 were implemented at various stages of completion because many of the activities were routine and mostly non-physical projects for specific departments such as the Central Administration, Social Welfare and Community Development, Agricultural development just to mention a few. The analysis of the status of implementation revealed that 93.7 percent of the entire four-year plan (2018-2021) had been implemented as at the end of the year, 2021.

The achievement of the indicators of these activities formed the basis of the assessment of the status of achievements of the implementation of the Medium Term Development Plan.

Table 1.2 presents the total number of planned and executed activities for 2021 categorized according to the development dimensions of the framework, agenda for jobs. The table also shows the various years, what was planned and what has been executed.

TABLE 2 DETAILS OF ANNUAL ACTION PLAN IMPLEMENTED UNDER AGENDA FOR JOBS POLICY FRAMEWORK

| Table 1.2 |  | Summary of Activities in Annual Action Plans, 2018 – 2021 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S/N | Development Dimensions |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  |
|  |  |  | Plan | Exec | Plan | Exec | Plan | Exec | Plan | Exec |
| 1 | Economic Development |  | 26 | 23 | 25 | 22 | 28 | 25 | 39 | 34 |
| 2 | Social Development |  | 61 | 54 | 47 | 43 | 56 | 50 | 66 | 61 |
| 3 | Environment, Infrastructure and Human Settlement |  | 23 | 20 | 17 | 14 | 22 | 21 | 41 | 37 |
| 4 | Governance, Corruption and Public Accountability |  | 20 | 20 | 25 | 24 | 16 | 16 | 32 | 31 |
|  | Total |  | 130 | 117 | 114 | 103 | 122 | 112 | 178 | 163 |
| Source: DPCU, 2021 |  |  |  |  |  |  |  |  |  |  |

FIGURE 2 ANNUAL ACTION PLAN IMPLEMENTED WITHIN THE PLAN PERIOD (2018-2021)

From the graphical presentation, it is observed that social development activities dominated throughout the four-year plan period. This is because the social development issues are so broad covering critical departments such as Education, Health, Social Welfare and Community Development and water.  On the average, all four development dimensions received a fair share of implementation in each year of the four-year plan period.

#### 1.1.1 IMPLICATION OF THE RESULTS ON ATTAINMENT OF DISTRICT GOALS AND OBJECTIVES

The Asunafo South District after implementing its 2018-2021 medium term plan has seen a tremendous improvement under the various policy dimensions.

Under Economic Development policy framework which has a goal of building a prosperous society, the District chalked the following successes;

- The implementation of government’s flagship program, NABCO helped boost revenue generation in the District through the recruitment of 17 personnel into the Revenue Ghana module. Under the period, 205 graduates were enrolled into the various modules unto the Nation Builders Corpse program in the district.

- Increased productivity in the agriculture sector through the application of improved farming techniques under the Modernizing Agriculture in Ghana (MAG) initiative and the use of improved seedlings and fertilizers from the Planting for Food and Jobs program.

- Improved livelihood conditions of the people. Economic development initiatives such as rural electrification saw the improvement of livelihood among people living in remote communities of the District.

The Social Development policy dimension under the goal, providing equal opportunities for all the thematic area that saw the most programs and projects implemented. This broad dimension saw significant improvement in the education sector, health, social welfare and water sectors. Some of the implications include;

- Increased access to quality education. The building of many classroom blocks, dormitories and teachers’ quarters over the period has helped expanded the frontiers of quality education to the most rural communities in the district.

- Increased access to healthcare. The number of Community-Based Health Planning and Services compounds have increased over the period hence creating access to quality healthcare to more people in the district.

- Access to potable water. The period also saw the drilling and mechanization of numerous water projects with the aim of improving access to potable water supply in the district.

- Improved living conditions of the marginalized. The Livelihood Empowerment Against Poverty (LEAP) program, enrolment of PWDs on NHIS, financial support for PWDs among other initiatives have contributed to a more decent and improved livelihood conditions of the marginalized in Asunafo South District.

Under Environment, Infrastructure and Human Settlement, the goal was to ensure a resilient built environment and maintain a stable, united and safe society. This thematic area of development saw considerable improvements in the areas of sanitation, spatial planning and feeder roads development. Under sanitation, there has been a significant jump in the proportion of households that have easy access to toilet facilities.

#### 1.1.2 CHALLENGES ENCOUNTERED IN THE IMPLEMENTATION OF THE ANNUAL ACTION PLAN

The specific constraints, problems and difficulties the District Planning Coordinating Unit (DPCU) encountered during the implementation, monitoring and evaluation of the 2021 Annual Action Plan under the DMTDP 2018-2021 are outlined below.

- A major challenge facing the implementation of the plan is inadequate and untimely release of funds from all sources (GOG, DACF, DACF-RFG, IGF and Other Donor Support).

- Inadequate logistical support and other resources for monitoring and evaluation activities in the District and at the Area Council levels.

- Lack of assigned permanent vehicle for monitoring and evaluation of programmes, projects and activities in the District.

- Lack of sustainable funds to conduct DPCU meetings and activities, Social Accountability Programmes, Evaluation and Participatory Monitoring and Evaluation.

## 1.2 PURPOSE OF THE MONITORING AND EVALUATION

Monitoring is a continuous process of tracking the progress of an activity by stakeholders to verify whether planned activities are being implemented using the right resources and in this regard, assessing the progress made in the implementation process of the Medium-Term Development Plan (2018-2021) and the Annual Action Plan for 2021 for that matter. Monitoring involves the observation and learning of a situation for changes that have occurred over time and requires the gathering of information in a systematic manner. Evaluation on the other hand is a periodic assessment of an on-going or completed project by stakeholders both external and internal in line with set objectives.

The rationale of the Monitoring and Evaluation for the year includes providing stakeholders information on whether or not progress is being made towards achieving stated objectives making changes on project implementation as well as learning through the process. Monitoring also provides feedback on projects and programmes to enhance learning and with the feedback mechanism improve upon the planning process and hence the effectiveness of planned interventions.

- With the inclusion of stakeholders in the process, monitoring increases accountability to donors, project sponsors and all other stakeholders including beneficiaries thus reducing suspicion and improving trust.

- The processes of the monitoring also enable Heads of Departments and the Planning Team to make timely adjustments and corrective measures when the need arises to improve upon project design, work plan and implementation. This increases the gains and minimizes losses.

- Monitoring finally checks on conditions and situations of target beneficiaries to assess changes that have occurred as a result of interventions in the form of projects and programme activities. The process is also used to determine the continued relevance of the said intervention, thus ensuring sustainability and positive impacts in the future.

Evaluation on the other hand is the purposive and systematic assessment of an on-going or completed intervention projects in line with set objectives. It is based on a systematic collection and analysis of data to assess the effectiveness, efficiency, relevance, sustainability and impact on stakeholders. The purpose of evaluation of the implementation of the 2021 Plan is to provide management information regarding policy, programme and project performances, while determining the weaknesses and strengths of the said interventions for improvements in planning in the future; it also serves as a tool for validation of earlier assessments.

Through evaluation, the Assembly was able to determine the extent to which projects in the 2021 AAP have been successful in terms of achieving intended objectives. Among others, evaluation also becomes a learning process, when causes of failures or successes are revealed; it becomes lessons for the future.

The ultimate aim is for the Assembly to provide effective and efficient services to the citizens of the District.

## 1.3 PROCESSES INVOLVED AND DIFFICULTIES ENCOUNTERED

#### 1.3.1	PROCESSES INVOLVED

The monitoring team of the Assembly spearheaded by the District Planning Coordinating Unit (DPCU), undertook quarterly monitoring visits to project sites. At the various project sites, the team was joined by Assembly Members, Chiefs, Opinion Leaders and managers of said projects. The various contractors and consultants are made to meet the team on each visit.

The Works Department carry out their routine inspection of implementing projects. Their observations are put together in the form of individual project reports which feed into the composite progress report. Verification reports are also prepared by a five-member team namely; Planning, Budget, Internal Audit, Works and Assembly members of electoral areas that have projects located. Summary reports are then prepared before payments are effected.

Departments such as Education, Health among others and the Works sub-Committee also undertake monitoring of their projects be it physical or non-physical. There are instances where external bodies also undertake monitoring on projects of interest to them. Examples are the Regional Coordinating Council (RCC) and the Office of the Administrator of DACF among others.

The processes also involve the holding of quarterly review meetings, assessment of set indicators and follow-ups where necessary. These review meetings are held with other non-DPCU members who are stakeholders such as State Owned Organizations, Traditional Authority among others. The lists of all those involved in monitoring and evaluation have been compiled as Annex.

The Assembly relies on the DPCU for undertaking Participatory Monitoring and Evaluation (PM&E) in the District. This team comprises of all relevant stakeholders both the primary and secondary stakeholders and this team visits all project sites every quarter.

#### 1.3.2	DIFFICULTIES ENCOUNTERED

Among the difficulties encountered by the District Assembly in the implementation of the MTDP as well as preparation of Annual and Quarterly monitoring and evaluation reports have been outlined below;

- One major difficulty encountered is that in the wake of Coronavirus, most Departments and Units were not able to execute their specific work plans on time as scheduled or could not execute the activity at all.

- Again, the bureaucracy involved when seeking information from some institutions and agencies within our reach with the review of the 20 core indicators, the Assembly had to initiate steps to obtain existing data and to make new contacts with other institutions.

- Most of the Departments complained about the late releases of funds for planned projects hence their inability to execute their activities on time.

- Some departments are also challenged with inadequate office logistics that hinder their timely submission of their quarterly reports and other deliverables.

- Untimely Change of political heads made transfers of funds from the central government delay

- Lack of proper documentation from some of the departments on their job schedules

- Unavailability of digitalized data

- Inconsistencies in reports from some departments

- Unwilliness of some departments to release vital information from their side

# CHAPTER TWO

# 2.0 MONITORING AND EVALUATION ACTIVITIES REPORT

2.1 INTRODUCTION

This section highlights the 2021 projects and programme registers (programmes and projects or activities carried out through the year), the funding sources and disbursements, update on indicators and targets, update on critical development and poverty issues, evaluations conducted, their findings and recommendations and participatory monitoring and evaluations conducted and their results. It discusses the financial inflows and outflows for the year as compared to that of previous year.

## 2.2 PROGRAMMES/PROJECTS STATUS

A total of 178 projects and programmes were earmarked for 2021. Out of the 178 projects, 163 were implemented with 15 rolled over to be implemented in 2022. With the 163 programmes and projects implemented, 52.2% were completed while 39.2% are on-going. No project has been abandoned under any of the funding sources. Appendix A and B contains the details of the projects and programmes implemented in 2021.

#### 2.2.1 REPORT ON PHYSICAL PROJECTS AS AT FOURTH QUARTER 2021

TABLE 3 EDUCATION SUB-SECTOR

| NO. | PROJECT DISCRIPTION | DEVELOPMENT DIMENSION OF POLICY FRAMEWORK | LOCATION | CONTRACTOR/CONSULTANT | CONTRACT SUM (GH₵) | SOURCE OF FUNDING | DATE OF AWARD | DATE STARTED | EXPECTED DATE OF COMPLETION | ACTUAL PAYMENT TO DATE (GH₵) | OUT STANDING BALANCE | IMPLEMEN- TATION STATUS (%) | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Completion of 1No 3-unit classroom block | Social Development | Motopenso | Great Agyedus Ventures | 88, 186.46 | MPCF | 10th Nov 2016 | 25th Nov, 2016 | March2017 | 66,048.10 | 6,483.64 | 100% | Completed |
| 2 | Construction of 1No 3-unit classroom block with ancillary facilities | Social Development | Kukuom | Maaxim Construction Works | 66,183.21 | DACF | 8th May, 2012 | 22nd May, 2012 | Sep. 2012 | 62,935.0 | 0.00 | 100% | Completed (Retention) |
| 3 | Construction of 3-unit classroom block with ancillary facilities | Social Development | Sankore Islamic | Wambinib Build & Const. Work | 67,449.03 | DACF | 8thDec, 2011 | 28th Dec, 2011 | Apr, 2012 | 64,319.64 | 2,713.89 | 100% | Completed (Retention) |
| 4 | Supply of 2000 Dual Desk | Social Development | District-wide | Lethnass Ltd | 175,440.00 | DACF | Nov, 2009 | Dec, 2009 | Mar, 2010 | 78,930.00 | 96,510.00 | 78% | On-going |
| 5 | Completion of 1No. 3-- unit classroom block | Social Development | Kukuom Anglican KG | Possible Power Ltd. | 85,846.50 | DACF | 12th Jan. 2015 | 30th Jan. 2015 | June 2015 | 37,000.00 | 39,352.05 | 40% | On-going |
| 6 | Construction of 3-unit classroom block | Social Development | Noberkaw | Fairhome Developers Limited | 76,879.00 | DACF | 2nd Feb. 2016 | 22nd Feb. 2016 | May, 2016 | 20,000.00 | 3,426.28 | 80% | Complete |
| 7 | Completion of 3-unit classroom block at Siiso | Social Development | Siiso | Musanba Ltd. | 77,524.15 | DACF | 2nd Feb, 2016 | 22nd Feb, 2016 | May 2016 | 0.00 | 0.00 | 100% | Completed – Unpaid |
| 8 | Supply of 1000No. of Dual Desk (Upper Primary | Social Development | District Wide | Aerisko Ent. | 120,000.00 | DACF | 11th Jan. 2016 | 27th Jan. 2016 | June, 2016 | 20,000.00 | 29,405.00 | 75.5% | On-going |
| 9 | Supply of 700No. of Dual Desk (Upper Primary) & 300No. of Mono Desk | Social Development | District Wide | Aerisko Ent. | 119,000.00 | DACF | 1st April 2016 | 20th April, 2016 | Oct. 2016 | 37,610.00 | 80,828.00 | 20% | Temporarily at a halt due to inadequate funding |
| 10 | Completion of Teacher’s Quarters with 2No. Toilet & bathroom | Social Development | Naketey | Adjemavoss (GH) Ltd. | 26,609.70 | DDF | 4th April 2016 | 18th April 2016 | Aug. 2016 | 10,000.00 | 12,196.20 | 46% | On-going |
| 11 | Construction of 1No 3-unit classroom block with 4 seater KVIP & urinal | Social Development | Sankore SDA | Great Agyedus Ventures | 182,688.08 | DACF | 1st April 2016 | 21st April 2016 | Aug. 2016 | 100,000.00 | 41,301.99 | 70% | On-going |
| 12 | Supply of 600 No. of Dual Desk (Lower Primary), 200No. Teacher’s Table & Chair | Social Development | District Wide | Aerisko Ent. | 124,200.00 | DACF | 8th Jan. 2016 | 29th Jan. 2016 | June, 2016 | 0.00 | 27,295.00 | 47% | On-going |
| 13 | Supply of 800 No. of Dual Desk (Lower Primary), 100No. Teacher’s Table and 100No. Teacher’s Chair | Social Development | District Wide | Aerisko Ent. | 133,000.00 | DACF | 20th April 2016 | 4th May, 2016 | Oct. 2016 | 0.00 | 133,000.00 |  | Yet to Start |
| 14 | Construction of 1No 3-unit classroom block with 4 seater KVIP & urinal | Social Development | Siiso Bowjiase | Musanba Ent. | 181,970.93 | DACF | 1st April 2016 | 21st April 2016 | Aug. 2016 | 60,000.00 | 67,314.59 | 47% | On-going |
| 15 | Extension of Male Hostel with 3No. Teacher’s Quarters | Social Development | Kwapong N TC | Lethnass Limited | 245,323.05 | DACF | 7th Nov. 2017 | 30th Nov, 2017 | Aug. 2018 | 30,000.00 | 130,515.45 | 84% | On-going |
| 16 | Construction of 1No 3-unit classroom block with 4 seater KVIP & urinal | Social Development | Asempanaye | SuleSalimanu Ent. | 182,437.65 | DACF | 1st April 2016 | 22nd April 2016 | Aug. 2016 | 60,000.00 | 99,521.4 | 47.1% | On-going |
| 17 | Const. of 1No. 3-unit classroom Block with 4-seater KVIP and urinal | Social Development | Kukuom Methodist Primary | JoywayWadada & Sons Ltd. | 191,769.29 | DACF | 7th Nov. 2017 | 29th Nov. 2017 | June, 2018 | 144,287.00 | 32,348.44 | 100% | Completed |
| 18 | Renovation of 1No. 6-Unit Classroom Block | Social Development | Kukuom Methodist Primary | JoywayWadada & Sons Ltd | 148,245.50 | DACF | 3rd April 2019 | 19th April 2019 | July 2019 |  | 148,245.50 |  | Work in progress |
| 19 | Construction of 1no. 3 –unit classroom block with 4 -- seater KVIP, a urinal and supply of furniture. | Social Development | Abuom D/A JHS, | Possible Power Limited | 274,740.13 | DACF | 4th Sept. 2018 | 25th Sept, 2018 | June, 2019 | 127,622.25 | 128,666.98 | 53% | On-going |
| 20 | Construction of 1no. 3 –unit classroom block with 4- seater KVIP, a urinal and supply of furniture | Social Development | Siiso D/A JHS | Eagle Power Limited | 273,869.56 | DACF | 4th Sept. 2018 | 25th Sept, 2018 | June, 2019 | 110,454.30 | 184,201.66 | 45% | On-going |
| 21 | Const. of 1No. 6-unit Classroom block Kukuom Agriculture Senior High Sch. | Social Development | Kukuom | Nhyira Building & Civil Works Limited | 506,841.34 | DACF | 5th Nov. 2018 | 29th Nov. 2018 | Nov. 2019 | 100,000.00 | 257,549.94 | 49% | Project temporarily at a halt due to inadequate funding |
| 22 | Completion of 1no. 3 unit teachers quarters at Adwumakase | Social Development | Adwumakase | Nti Hebron Construction | 60,023.21 | MPs GETFUND | 2nd Sept, 2019 | 24th Sept, 2019 | Feb, 2020 | 57,022.05 | 3,001.16 |  | Completed (Retention) |
| 23 | Completion of 1No. 3- Unit Classroom Block with Office and Staff Common Room at Ndayinanse JHS | Social Development | Ndayinanse | S.A. Miracle Const. Ltd. | 72,239.10 | MPCF | 10th Dec, 2019 | 2nd Jan, 2019 | Jul, 2020 |  | 72,239.10 |  | Work in progress |
| 24 | Construction of 3-unit classroom Block with Ancillary Facilities | Social Development | Siiso Bowjiase | Musanba Ltd. | 98,154.50 | MPCF | 11th Aug. 2015 | 27th Aug. 2015 | Dec. 2015 | 89,649.80 | 0.00 | 100% | Completed (Unpaid) |
| 25 | Construction of 1No. 3 unit classroom block with a toilet | Social Development | Adwumam | Aerisko Ent. | 125,034.40 | Stool Lands Admin Fund | 9th Jan. 2015 | 20th Jan. 2015 | June 2015 | 72,500.00 | 58,214.35 | 54% | On-going |
| 26 | Construction of 1No teachers' quarters | Social Development | Kwapong | PRIMACY | 80,852.27 | DDF | 13th Jan. 2014 | 28th Jan. 2014 | May, 2014 | 76,844.2 | 4,008.07 | 74% | On-going |
| 27 | Construction of 1No. 3 unit classroom block | Social Development | Nnanyinaanse- Kwapong NTC | Lethnass | 96,286.30 | DDF | 9th Jan. 2015 | 20th Jan. 2015 | June 2015 | 60,535.26 | 35,751.04 | 62.8% | On-going |
| 28 | Const. of 1No.3-unit Classroom Block with Office, Staff Common Room, 2-Seater KVIP and Supply of Furniture | Social Development | Anwiam D/A JHS | Sarfoliz Engineering & Const. Works | 240,064.47 | DDF | 6th June, 2019 | 24th June, 2019 | Feb, 2020 | 149,826.56 | 90,237.91 | 100% | Completed |
| 29 | Construction of 1No. 3-Unit Classroom Block with office, staff common room, 3-Seater KVIP and supply of Furniture | Social Development | Kukuom | Nana Yaw Banahene Co. Ltd. | 248,734.07 | DDF | 6th April, 2021 | 27th April, 2021 | October, 2021 | 80,737.57 | 167,996.50 | 15% | on-going |
| 30 | Construction of 1No. 3-Unit Classroom Block with office, staff common room, 3-Seater KVIP and supply of Furniture | Social Development | Kukuom SDA | JoywayWadada & Sons Co. Ltd. | 271,245.72 | DDF | 12th May, 2021 | 28th May, 2021 | November, 2021 | 0.00 | 271,245.72 |  | On-going |

TABLE 4 HEALTH SUB-SECTOR

| NO. | PROJECT TITLE | DEVELOPMENT DIMENSION OF POLICY FRAMEWORK | LOCATION | CONTRACTOR | CONTRACT SUM (GH₵) | SOURCE OF FUNDING | DATE AWARDED | DATE STARTED | EXPECTED COMPLETION | ACTUAL PAYMENT TO DATE (GH₵) | OUTSTANDING BALANCE (GH₵) | IMPLEMENTATION STATUS % | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Construction of Health Administration Block | Social Development | Kukuom | Reliable Shelter | 370,000.00 | DACF | 9th Oct, 2019 | 24th Oct. 2019 | Mar, 2020 | 343,664.67 | 12,861.13 | 100% | Completed |
| 2 | Construction of 1 No. CHPS | Social Development | Wejakrom | P.F.R. Ltd | 153,371.70 | DACF | 14th Jan. 2015 | 30th Jan. 2015 | Sept. 2015 | 74,227.32 | 79,144.38 | 48.8% | Expected to be completed by 2022 |
| 3 | Construction of 1No. CHPS compound | Social Development | Asibrem | Galton Co. Ltd | 148,998.98 | DACF | 14th Jan. 2015 | 30th Jan. 2015 | Sept. 2015 | 102,919.05 | 45,351.83 | 70% | Expected to be completed by 2022 |
| 4 | Completion of Male & Female ward | Social Development | Kukuom | JoywayWadada & Sons Ltd. | 189,156.37 | DACF | 1st April 2016 | 20th April, 2016 | Aug. 2016 | 164,056.85 | 25,099.52 |  | Major works completed |
| 5 | Completion of CHPS comp. With 4-seater KVIP, a urinal and drilling and mechanization of 1no. Borehole | Social Development | Pafo Nkwanta | Elatarim Ent. | 249,918.95 | DACF/DDF | 10th Sept. 2018 | 28th Sept. 2018 | June, 2019 | 77,856.34 | 166,829.20 | 33% | Expected to be completed by 2022 |
| 6 | Construction of 1No. 2-Unit Single room self-contain Nurses Quarters at Abuom | Social Development | Abuom | S.A. Miracle Const. Ltd. | 145,324.55 | MPHF | 4th Dec, 2019 | 23rd Dec. 2019 | May, 2020 | 58,384.35 | 89,940.20 | 40% | Expected to be completed by 2022 |
| 7 | Construction of 1No.CHPS Compound | Social Development | Asarekrom | S.A. Miracle Const. Ltd | 104,851.34 | MPHF | 13th April, 2016 | 29th April, 2016 | Aug. 2016 | 27,334.72 | 77,516.62 | 45% | Expected to be completed by 2022 |
| 8 | Construction of 1No. Administration Block at Kukuom Hospital | Social Development | Kukuom | Nana Yaw Banahene Company Limited | 354,360.90 | DACF-RFG | 2nd July, 2019 | 25th July, 2019 | May, 2020 | 330,457.03 | 23,903.88 | 100% | Completed (Retention) |
| 9 | Construction of 1No. Clinic and 1No. 3- Unit Staff Quarters at Kwapong | Social Development | Kwapong | Asombe Ent. | 496,578.40 | DACF-RFG | 2nd July, 2019 | 25th July, 2019 | May, 2020 | 471,794.48 | 24,828.92 | 100% | Completed (Retention) |

TABLE 5 WATER AND SANITATION

| NO. | PROJECT TITLE | DEVELOPMENT DIMENSION OF POLICY FRAMEWORK | LOCATION | CONTRACTOR | CONTRACT SUM (GH₵) | SOURCE OF FUNDING | DATE AWARDED | DATE STARTED | EXPECTED COMPLETION | ACTUAL PAYMENT TO DATE (GH₵) | OUTSTANDING BALANCE (GH₵) | IMPLEMENTATION STATUS % | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Renovation and Dislodging of 12 – Seater KVIP | Environment, Infrastructure and Human Settlement | Sankore | Princeboat Comp. Ltd | 33,929.50 | DACF | 8th Jan. 2016 | 20th Jan. 2016 | April, 2016 | 31,573.62 | 2,355.88 | 100% | Completed (Retention) |
| 2 | Construction of 1No. 12-seater KVIP | Environment, Infrastructure and Human Settlement | Sankore | S.A. Miracle Const. Ltd | 118,369.95 | DDF | 14th Dec. 2013 | 28th Dec. 2013 | Jun. 2014 | 66,086.93 | 52,283.02 | 100% | Completed (Retention) |
| 3 | Rehab of 17No. Borehole | Social Development | District wide | Kolong Works Ent | 30,180.00 | DDF | 4th Nov. 2016 | 25th Nov. 2016 | Jan. 2017 | 3,018.00 | 3,018.00 | 100% | Completed (Retention) |
| 4 | Drilling of 4No. Borehole and installation of Afridev hand pump | Social Development | District wide | Kolong Works Ent. | 70,000.00 | DDF | 4th Nov. 2016 | 25th Nov. 2016 | Jan. 2017 | 66,285.00 | 3,715.00 | 100% | Completed (Retention) |
| 5 | Drilling and Mechanization of 1No. Borehole at Noberkaw, Mechanization of 2No. Boreholes at Sikafrebogya & Dantano and Installation of Hand pump at Akwasi-Mframa | Social Development | Noberkaw, Sikafrebogya, Dantano & Akwasi-Mframa | Diakos Power Comp. Ltd. | 112,541.56 | DDF | 11th July, 2019 | 26th July, 2019 | Dec. 2019 | 106,914.48 | 5,627.08 | 100% | Completed (Retention) |

TABLE 6 LOCAL ECONOMIC DEVELOPMENT

| NO. | PROJECT TITLE | DEVELOPMENT DIMENSION OF POLICY FRAMEWORK | LOCATION | CONTRACTOR | CONTRACT SUM (GH₵) | SOURCE OF FUNDING | AWARD DATE | DATE STARTED | EXPECTED COMPLETION DATE | ACTUAL PAYMENT TO DATE (GH₵) | OUTSTANDING BALANCE (GH₵) | IMPLEMENTATION STATUS % | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Construction of 1No 6-unit Lockable market stores | Economic Development | Kukuom | Kwabena Asnado Ltd | 46,981.31 | DACF | 7th Dec. 2011 | 19th Dec. 2011 | Apr. 2012 | 40,660.20 | 0.00 | 100% | Completed (Retention) |
| 2 | Supply of 4No Refrigerators,4No Generators & 4No. Mot | Economic Development | District-wide | K.A World Mgt &Dev't. | 54,600.00 | DACF | 3rd Jan. 2014 | 22nd Jan. 2014 | Mar. 2014 | 14,367.00 | 34,700.00 | 36% | Temporarily at a halt due to inadequate funding |
| 3 | Construction of Abattoir | Economic Development | Kukuom | Monpet Ent. | 48,635.60 | DACF | 2nd Sept. 2014 | 18th Sept. 2014 | Aug. 2018 | 20,000.00 | 24,206.25 | 90% | Project at final stage of completion |
| 4 | Completion of 1No storey for Sankore Daily Market(20-unit) | Economic Development | Kukuom | Lethnass Ltd | 167,124.5 | DACF/IGF | 12th June, 2014 | 25th June, 2014 | Nov. 2019 | 117,496.70 | 23,439.50 | 86% | Project at final stage of completion |
| 5 | Construction of Durbar ground | Economic Development | Sankore | Mountain Top Ventures | 241,985.00 | DACF | 4th July, 2016 | 27th July, 2016 | March 2017 | 0.00 | 197,705.00 | 18% | Temporarily at a halt due to inadequate funding |
| 6 | Construction of Durbar ground | Economic Development | Kwapong | Christ DevidOpoku Ltd. | 238,849.60 | DACF | 4th July, 2016 | 25th July, 2016 | March 2017 | 0.00 | 238,849.60 |  | Yet to start |
| 7 | Extension of Electricity from Kofibenkrom to Siiso Bodwease (3.2km) | Economic Development | Kukuom | Parklynk Ventures | 85,000.00 | MPCF | 3rd Dec. 2019 | 19th Dec. 2019 | Mar. 2020 | 80,750.00 | 4,250.00 | 100% | Completed (Retention) |
| 8 | Redevelopment of Sankore Lorry Terminal | Economic Development | Siiso Bodwease | Cornerstone Const. Ltd. | 400,233.72 | MPCF | 11th Nov. 2015 | 28th Nov. 2015 | March 2016 | 210,000.00 | 121,084.46 | 69% | Project expected to be completed by end of 2022 |
| 9 | Construction of 1No community Centre | Economic Development | Sankore | Samotrust Co. Ltd | 82,140.29 | DDF | 13th Dec. 2013 | 30th Dec. 2013 | May. 2014 | 72,086.69 | 10,053.60 | 100% | Completed (Retention) |
| 10 | Construction of 1 No. 10 unit lockable stores with concrete slab | Economic Development | Sankore | S.A Miracle Const. Ltd | 162,742.00 | DDF | 9th Jan, 2015 | 28th Jan, 2015 | August 2015 | 109,367.90 | 30,437.71 | 83% | Complete |

TABLE 7 MANAGEMENT AND ADMINISTRATION

| NO. | PROJECT TITLE | DEVELOPMENT DIMENSION OF POLICY FRAMEWORK | LOCATION | CONTRACTOR | CONTRACT SUM (GH₵) | SOURCE OF FUNDING | DATE AWARDED | DATE STARTED | EXPECTED COMPLETION | ACTUAL PAYMENT TO DATE (GH₵) | OUTSTANDING BALANCE (GH₵) | IMPLEMENTATION STATUS % | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Completion of 3-storey Administration Block | Governance, Corruption and Public Accountability | Kukuom | A.S.I Mustapha Co. Ltd | 1,186,436.83 | DACF | 15th Aug. 2014 | 2nd Sept. 2014 | Aug. 2017 | 457,965.52 | 728,471.31 | 38.5% | Project temporarily at a halt due to inadequate funds |
| 2 | Renovation of DCE’S Bungalow | Governance, Corruption and Public Accountability | Kukuom | JoywayWadada & Sons Ltd. | 65,756.52 | DACF | 6th Nov. 2017 | 27th Nov. 2017 | March, 2018 | 26,999.73 | 38,756.79 | 41% | On-going |
| 3 | Renovation of Kukuom district court building | Governance, Corruption and Public Accountability | Kukuom | Asombe Ent. | 59,783.86 | DACF | 9th Sept. 2019 | 27th Sept. 2019 | Dec. 2019 | 52,821.96 | 6,961.90 | 68% | On-going |
| 4 | Construction of fire station at Kukuom | Governance, Corruption and Public Accountability | Kukuom | Napsolinks GH Ltd | 192,775.22 | DDF | 13th Jan. 2014 | 24th Jan. 2014 | July 2014 | 186,710.3 | 6,105.3 | 79% | Project at the final stage of completion |

TABLE 8 ROADS INFRASTRUCTURE

| NO. | PROJECT TITLE | DEVELOPMENT DIMENSION OF POLICY FRAMEWORK | LOCATION | CONTRACTOR | CONTRACT SUM (GH₵) | SOURCE OF FUNDING | DATE AWARDED | DATE STARTED | EXPECTED COMPLETION | ACTUAL PAYMENT TO DATE (GH₵) | OUTSTANDING BALANCE (GH₵) | IMPLEMENTATION STATUS % | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Reshaping of 25km feeder road from 1000 Acre to Tettehkwaw and others | Environment, infrastructure and Human settlement | 1000 Acres to Tettehkwaw | Samtay Ventures | 55,000.00 | DACF | 04/10/21 | 08/10/21 | 29/10/21 | 55,000.00 | 0 | 100% | Road in good shape |
| 2 | Reshaping of 18km feeder road from Amankwakrom to Asibrem and others | Environment, infrastructure and Human settlement | Amankwakrom to Asibrem | Samtay Ventures | 45,000.00 | DACF | 04/10/21 | 08/10/21 | 29/10/21 | 45,000.00 | 0 | 100% | Road in good shape |
| 3 | Upgrading of Sankore -Abuom -Nankete(km8-14.5)- 6.5km | Environment, infrastructure and Human settlement | Sankore -Abuom –Nankete | Dynamic Star Ltd | 7.205,923.46 | COCOBOD | 9/12/2015 | 03/02/2016 | 17/11/2020 | 6681871.7 | 524,051.76 | 92% | Project at the final stages of completion |
| 4 | Upgrading of Ntonsu - Amadu Nkwanta - Tetekwao Ph.1 (km 0.00 - 7.00) | Environment, infrastructure and Human settlement | Ntonsu - Amadu Nkwanta – Tetekwao | Salodap Enterprise | 7,980,493.04 | COCOBOD | 23/03/2020 | 21/05/2020 | 20/05/2021 | 1,669,826.66 | 6,310,666 | 30% | N/A |
| 5 | Upgrading of Ntonsu - Amadu Nkwanta - Tetekwao Ph.2 (km 7.0 - 14.0) | Environment, infrastructure and Human settlement | Ntonsu - Amadu Nkwanta | B. K. Nsia Ltd | 11,986.189.16 | COCOBOD | 23/03/2020 | 13/5/2020 | 12/5/2021 | 5,362,583,26 | 6,623,605.90 | 52.9 | N/A |
| 6 | Upgrading of Dodowa jn - Pafo No.2 Feeder Road | Environment, infrastructure and Human settlement | Dodowa jn – Pafo | Wabrama Limited | 32,828,407.7 | COCOBOD | 18/12/2020 | 17/2/21 | 16/8/22 | 9,581.384.12 | 23,242,002.90 | 31% | N/A |
| 7 | Upgrading of Amankwakrom jn - Kwesibeng Feeder Road (12.0km) | Environment, infrastructures and Human settlement | Amankwakrom jn – Kwesibeng | Prime Key Limited | 27,806,051.68 | COCOBOD | 16/06/2021 | 17/8/21 | 16/2/23 | - | 27,806,051.68 | 3% | N/A |
| 8 | Upgrading of Pesewkrom - Boakyekrom - Moshikrom Feeder Road (12.0km) | Environment, infrastructure and Human settlement | Pesewkrom - Boakyekrom – Moshikrom | Kpanyaraga Limited | 31,208.792.25 | COCOBOD | 16/06/2021 | 17/8/21 | 16/8/23 | - | 31,208,797.25 | 2% | N/A |
| 9 | Upgrading of Mensakrom -Muntimi Jn - Druwakrom feeder road (22.00km) | Environment, infrastructure and Human settlement | Mensakrom -Muntimi Jn – Druwakrom | Precise Homes Limited | 47,519.579.27 | COCOBOD | 18/12/2020 | 18/2/21 | 17/2/23 | - | 47,519,579.27 | 5% | N/A |
| 10 | Upgrading of Adwumakese – Mepomshed | Environment, infrastructure and Human settlement | Adwumakese – Mepomshed | S. K. Nimako Ltd | 7,261,404.56 | ROADFUND | 18/08/2020 | 19/11/20 | 18/11/21 | 791,847.60 | 6,469.556.36 | 10% | N/A |
| 11 | Upgrading of Amankwaakrom Jn – Sikafremogya | Environment, infrastructure and Human settlement | Amankwaakrom Jn – Sikafremogya | Ezee Limited | 5,279,938.92 | ROADFUND | 18/08/2020 | 16/11/20 | 15/11/21 | - | 5,279.938.92 | 2% | N/A |

#### 2.2.2 BRIEF ANALYSIS OF THE PROJECT REGISTER

Economic Development: projects under this Development Dimension are captured under LED (Local Economic Development) activities. The projects include the construction of Abattoir, market facility, redevelopment of lorry station, and the construction of durbar grounds. All the projects under this dimension are roll over projects that have been in the system for quite some time. The problem has to do with inadequate and untimely release of funds. 90% of the projects are financed from the DACF with the rest from MPCF. It is however expected that these projects will be completed and handed over by close of 2022.

SOCIAL DEVELOPMENT: projects categorized under this development dimension are the most among all the physical projects in the district. They are dominated by classroom blocks for the education sector. Most of the projects likewise the Economic Development projects are also roll over projects due to same challenge of inadequate and untimely release of funds. However, some of the projects especially those financed from DDF are far advanced towards completion if not completed due to the timely release and constant monitoring at all levels of DDF funded projects. It is expected that most of these on-going projects under this development dimension will be completed and handed over in 2022 to ensure equal opportunities for all.

ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENT: All the infrastructural projects under this dimension, in this case road projects were initiated by the Feeder Roads Department of the Ahafo region. Seven out of the Nine (9) road projects are financed by COCOBOD and the remaining 2 from Road Fund. These construction projects when completed will improve efficiency and effectiveness of road transport infrastructure in the district so as to achieve the goal of ensuring a resilient built environment.

GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY: all except one are funded from the District Assembly’s Common Fund. The DDF funded project, construction of Fire Station is expected to be completed and handed over by close of 2nd quarter 2022. The projects under this policy dimension are aimed at maintaining a stable, united and safe society for the people of Asunafo South.

TABLE 9 PROGRAMMES REGISTER FOR 2021

| S/N | PROGRAMME DESCRIPTION | DEVELOPMENT DIMENSION OF POLICY FRAMEWORK | AMOUNT INVOLVED SUM GH¢ | SOURCE OF FUNDING | DATE STARTED | EXPECTED DATE OF COMPLE- TION | EXPENDI- TURE TO DATE | OUT STANDING BALANCE | IMPLEMEN- TATION STATUS (%) | TOTAL BENEFICIARIES | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Embark on monthly monitoring and supervision of revenue collectors | Governance, Corruption and Public Accountability | - | - | Every month | End of year | - | - | Implemented | 27 | Revenue leakages reduced |
| 2 | Embark on monthly radio revenue sensitization programme | Governance, Corruption and Public Accountability | - | - | Monthly | End of year | - | - | Implemented |  | Officers from the Assembly visited all information centres across the district to educate and sensitize the populace on the need to pay BOPs and Property rates |
| 3 | Update Assembly’s revenue database | Governance, Corruption and Public Accountability | - | - | Weekly | End of year | - | - | Implemented |  | Updates carried out every week |
| 4 | Organize training on service protocols for newly recruited LGS staff | Governance, Corruption and Public Accountability | 1,000.00 | IGF | 23rd July, 2021 | 23rd July, 2021 | 1,000.00 | - | Implemented | 10 | New staff appreciated the experience |
| 5 | Organize town hall meetings with three sub-District structures | Governance, Corruption and Public Accountability | N/A | N/A | Quarterly | End of year | N/A | N/A | Implemented | 260 | Not implemented in 1st quarter due to Covid 19 restrictions |
| 6 | Convene General Assembly meetings | Governance, Corruption and Public Accountability | 17,334.00 | IGF | 30th Sept. 2021 | 30th Sept. 2021 | 17,334.00 | - | Implemented | 35 | Massive participation by all stakeholders |
| 7 | Convene EXECO meetings | Governance, Corruption and Public Accountability | 5,805.00 | IGF | 23rd Sept. 2021 | 23rd Sept. 2021 | 5,805.00 | - | Implemented | 10 | A very interactive and successful outcome |
| 8 | Organise meetings of 5 statutory sub-committees | Governance, Corruption and Public Accountability | 12,630.00 | IGF | 31st Aug. 2021 | 31st Aug. 2021 | 12,630.00 | - | Implemented | 32 | Well patronized and very effective |
| 9 | Organise quarterly Audit Committee meetings | Governance, Corruption and Public Accountability | 18,000.00 | IGF | Quarterly | End of Year | 18,000.00 | - | Implemented |  | Three meetings were organized in 2021 |
| 10 | Organise quarterly Budget Committee meetings | Governance, Corruption and Public Accountability | 2,000.00 | IGF | Quarterly | End of year | 2,000.00 | - | Implemented | 12 | Successfully carried out |
| 11 | Organize quarterly DPCU meetings | Governance, Corruption and Public Accountability | 6,500.00 | IGF | Quarterly | End of year | 6,500.00 | - | Implemented | 25 | Successfully organized |
| 12 | Organize Entity Tender Committee meetings | Governance, Corruption and Public Accountability | 4,148.00 | IGF | Quarterly | End of year | 4,148.00 | - | Implemented |  | Two Entity Tender Committee meetings were organized |
| 13 | Organize quarterly Spatial Planning Committee meetings | Governance, Corruption and Public Accountability | 2,935.00 | IGF | Quarterly | End of year | 2,935.00 | - | Implemented | 13 | Meeting successfully organized. |
| 14 | Organize quarterly Technical sub-committee meetings | Governance, Corruption and Public Accountability | 2,265.00 | IGF | Quarterly | End of year | 2,265.00 | - | Implemented | 9 | Meeting successfully organized |
| 15 | Organise quarterly management and staff meetings | Governance, Corruption and Public Accountability | N/A | N/A | Quarterly | End of year | N/A | N/A | Partially Implemented | 135 | Third quarter meetings delayed |
| 16 | Embark on quarterly monitoring of physical development programmes and projects | Governance, Corruption and Public Accountability | 5,000.00 | DACF | Quarterly | End of year | 5,000.00 | - | Implemented |  | The DPCU undertook monitoring of Assembly’s programmes and projects |
| 17 | Embark on quarterly monitoring of 6 sub-District structures | Governance, Corruption and Public Accountability | 4,000.00 | IGF | Quarterly | End of year | 4,000.00 | - | Implemented |  | All six area councils monitored |
| 18 | Undertake Community needs assessment for the preparation of 2022-2025 DMTDP | Governance, Corruption and Public Accountability | 7,500.00 | DACF | 16th-17th Sept. 2021 | 17th September, 2021 | 7,500.00 | - | Implemented | 10,425 | Intensify the bottom up approach towards development |
| 19 | Train 50 SMEs on financial literacy and effective business management | Economic development | N/A | N/A | 14th July, 2021 | 14th July, 2021 | N/A | N/A | Implemented | 50 | Training was led by BAC team from Asunafo North |
| 20 | Establishment of BAC District office in Asunafo South | Governance, Corruption and Public Accountability | - | - | March, 2021 | - | - | - | On-going | N/A | Office space and logistics have been secured. |
| 21 | Inspection of demarcated area designated for the siting of 1D1F | Governance, Corruption and Public Accountability | - | - | 12th March, 2021 | 12th March, 2021 | N/A | - | Implemented | N/A | Land is ready and fit for purpose. Passes EPA assessment |
| 22 | Train 50 traders in business planning and management | Economic development | 2,000.00 | GEA | 11th June, 2021 | 11th June, 2021 | 2,000.00 | - | Implemented | 50 | Training was facilitated by BAC officer from Asunafo North |
| 23 | Organise Farmers’ Day | Economic Development | 55,233.00 | IGF/Donor | 3rd Dec. 2021 | 3rd Dec. 2021 | 55,233.00 | - | 100% |  | Successfully organized and well patronized |
| 24 | Farm and home visits | Economic Development | 34,000.00 | MAG | Weekly (4th Quarter) | End of year | 34,000.00 | - | 100% | 8,374 | Visitation has boosted farmers |
| 25 | Training Livestock FBOs on Networking and Record keeping | Economic Development | 9,000.00 | MAG | 10th March, 2021 | 10th March, 2021 | 9,000.00 | - | 100% | 47 | Training equipped livestock FBOs with requisite knowledge on record keeping |
| 26 | Training FBOs on signing of MOUs and Contract | Economic Development | 2000.00 | MAG | 14th April, 2021 | 14th April, 2021 | 2000.00 | - | 100% | 55 | Training has built the capacity of Rice FBOs |
| 27 | Training FBO’s on cost benefit analysis of major commodities | Economic Development | 1,800.00 | MAG | 11th, 17th, 23rd Nov. 2021 | 23rd Nov. 2021 | 1,800.00 | - | 100% | 223 | Target of 200 FBOs exceeded by 23 |
| 28 | Vaccination and prophylactic treatment of livestock and pets | Economic Development | 1,500.00 | MAG | Quarterly | End of year | 1,500.00 | - | 100% | 829 | The team ensured that affected livestock were treated. 8000 beds in total were attended to. |
| 29 | Sensitization on FAW menace and control | Economic Development | 2,425.42 | MAG | March 15-May 31, 2021 | May 31, 2021 | 2,425.42 | - | 100% | 552 | FAW menace managed and economic damage of insect is less. |
| 30 | Training on Plantain paring and Bud Multiplication Technique | Economic Development | 2,000.00 | Self help | March 2-April 28, 2021 | April 28, 2021 | 2,000.00 | - | 100% | 551 | Beneficiaries were equipped with modern Agric. Technology practices that will help increase yield |
| 31 | Conduct staff Technical Review Meeting | Economic Development | 3,960.00 | MAG | Quarterly | End of year | 3,960.00 | - | 100% | 35 | Built capacity of staff |
| 32 | Training on Safe use of Agrochemical and use of PPEs | Economic Development | 3,000.00 | MAG | April 19-May 20, 2021 | May 20, 2021 | 3,000.00 | - | 100% | 207 | Training has equipped farmers to ensure safety precautions at all times |
| 33 | Training on integrated pest management(IPM) | Economic Development | 1,000.00 | Self help | June 22-30, 2021 | June 22-30, 2021 | 1,000.00 | - | 100% | 526 | Farmers have been equipped with pest management techniques to help reduce pest invasions |
| 34 | Demonstration on Rice & maize (GAPs) | Economic Development | 2,934.00 | MAG | April 7-July 22, 2021 | July 22, 2021 | 2,934.00 | - | 100% | 125 | Enhanced cereal yield and production |
| 35 | Training for women on soap making as an additional livelihood | Economic Development | 2,090.00 | MAG | Aug. 13-18, 2021 | Aug. 13-18, 2021 | 2,090.00 | - | 100% | 55 | 49 women empowered |
| 36 | Training women on soya kebab preparation for nutritional Improvement | Economic Development | 2,090.00 | MAG | July 23-Aug 31, 2021 | Aug 31, 2021 | 2,090.00 | - | 100% | 62 | 58 women empowered |
| 37 | Conduct RECL planning session | Economic Development | 3,240.00 | MAG | July 14-Aug 11, 2021 | Aug 11, 2021 | 3,240.00 | - | 100% | 39 |  |
| 38 | Sensitization on Avian Influenza(bird flu) | Economic Development | 2,000.00 | Self help | Aug 11-26, 2021 | Aug 11-26, 2021 | 2,000.00 | - | 100% | 152 | Ensure that necessary measures are put in place to reduce to barest minimum the effect of the outbreak |
| 39 | Poultry and Livestock survey | Economic Development | 1,800.00 | MAG | Quarterly | End of year | 1,800.00 | - | 100% |  | Survey conducted successfully |
| 40 | Market data collection on food commodities and livestock and agrochemicals | Economic Development | 763.20 | MAG | 4th Quarter (weekly) | End of year | 763.20 | - | 100% |  | Data successfully collected |
| 41 | Improved post-harvest management techniques | Economic Development | - | Dept. of Agric (self-help) | 13th, 15th, 20th, Dec. 2021 | 20th, Dec. 2021 |  | - | 100% | 144 | Successfully impacted |
| 42 | Workshop on transition to English Language PLUS (T2E PLUS) for 38 Non-GALOP Schools | Social Development | N/A | N/A | 04-09-2021 | 04-09-2021 | N/A | N/A | Implemented | 124 | Objective was to equip lower grade learners to read and write with understanding |
| 43 | Utilization of GALOP learning grant workshop organized for 41 GALOP schools | Social Development | N/A | N/A | 13/14-07-2021 | 14-07-2021 | N/A | N/A | Implemented | 82 | Objective was to equip lower grade learners to read and write with understanding |
| 44 | Conduct quarterly MAC meetings | Social Development | N/A | N/A | Quarterly | End of year | N/A | N/A | Implemented | 8 | Successful |
| 45 | Embark on quarterly monitoring of PMTCT, ART Centers and HIV school alert programmes | Social Development | N/A | N/A | Quarterly | End of year | N/A | N/A | Implemented |  | ART center at Kukuom Government Hospital was monitored where data on HIV/AIDS were collated across the District |
| 46 | Educational workshop on breast cancer | Social Development | N/A | N/A | 13th Oct. 2021 | 13th Oct. 2021 | N/A | N/A | Implemented | 55 | Program was successfully carried out. |
| 47 | Organize education and sensitization on the COVID 19 Vaccines | Social Development | N/A | N/A | May 2021 | May, 2021 | N/A | N/A | Implemented |  | Reduced the fear associated with taking the COVID 19 jab |
| 48 | Administering of COVID 19 doses | Social Development | - | - | All year round | On-going | - | - | On-going | 20,752 | 10,367 people out of the 20,752 have fully vaccinated |
| 49 | Settlement of family tribunal cases | Social Development | N/A | N/A | N/A | N/A | N/A | N/A | Implemented | 11 | All cases were successfully settled |
| 50 | Registration of persons with disability (PWDs) | Social Development | N/A | N/A | N/A | N/A | N/A | N/A | Implemented | 23 | The department has systems in place to fish out and register those who are yet to be captured. |
| 51 | Enrolment of PWDs on NHIS | Social Development | N/A | N/A | Quarterly | End of year | N/A | N/A | Implemented | 16 | 16 out of the 23 registered PWDs have been successfully enrolled onto NHIS |
| 52 | Organise the celebration of World Child Labour Day | Social Development | N/A | N/A | 12-06-2021 | 12-06-2021 | N/A | N/A | Implemented | 98 | Parents were encouraged to invest in the future of their wards as a major step towards eradicating poverty |
| 53 | Resolve child related cases to promote and protect the right of the child | Social Development | N/A | N/A | N/A | N/A | N/A | N/A | Implemented | 32 | Thirty-Two (32) child rights related cases on child maintenance, family welfare and child custody were reported with 28 of the cases resolved |
| 54 | Provide financial assistance to LEAP beneficiaries | Social Development | N/A | N/A | Bi-Monthly | End of Year/ Cyclical | N/A | N/A | Implemented | 382 | 382 beneficiaries have received support with a total of GH₡132,627.20 |
| 55 | Conduct routine house to house (domiciliary) and market inspections | Environment, Infrastructure and Human Settlement | N/A | N/A | Monthly | End of year | N/A | N/A | Implemented | 45,000 | A major improvement in household and institutional sanitation |
| 56 | Routine inspection of household latrines (toilet facilities) | Environment, Infrastructure and Human Settlement | N/A | N/A | Quarterly | End of Year | N/A | N/A | Implemented | 25,000 | There has been an increase in the number of households with toilet facilities in the district |
| 57 | Inspection of Restaurants, Chop Bars, and Food Vendors | Environment, Infrastructure and Human Settlement | N/A | N/A | Weekly | End of year | N/A | N/A | Implemented | 150 | Team ensured that wholesome food is sold to the public |
| 58 | Routine inspection of stores | Environment, Infrastructure and Human Settlement | N/A | N/A | Weekly | End of year | N/A | N/A | Implemented | 455 | To ensure that products on display are not expired |
| 59 | Routine inspection of schools | Environment, Infrastructure and Human Settlement | N/A | N/A | Monthly | End of year | N/A | N/A | Implemented | 76 Schools | To ensure compliance to hygiene protocols |
| 60 | Education on the need for household toilet facilities | Environment, Infrastructure and Human Settlement | N/A | N/A | Weekly | End of year | N/A | N/A | Implemented | 10,000 | There has been an increase in the number of households with toilet facilities in the district |
| 61 | Embark on screening of food vendors | Environment, Infrastructure and Human Settlement | N/A | N/A | 1st Quarter | End of year | N/A | N/A | Implemented | 1,709 | The test was rigorously undertaken and was compulsory for all vendors |
| 62 | Conduct regular meat inspection | Environment, Infrastructure and Human Settlement | N/A | N/A | Weekly | End of year | N/A | N/A | Implemented | - | Meat slaughtered at Kukuom, Sankore and Kwapong were inspected by Officers from Veterinary and Environmental Health and Sanitation Unit |
| 63 | Conduct quarterly hygiene promotion | Environment, Infrastructure and Human Settlement | N/A | N/A | Quarterly | End of year | N/A | N/A | Implemented | 32,500 | Hygiene promotion was undertaken in twenty three (23) communities on COVID-19 pandemic |
| 64 | Conduct intensive public education and awareness creation on human induced disasters | Environment, Infrastructure and Human Settlement | N/A | N/A | Monthly | End of year | N/A | N/A | Implemented | N/A | Targeted at reducing bush fires, erosions and other human induced disasters |
| 65 | Demolishing of weak disaster-prone structures | Environment, Infrastructure and Human Settlement | N/A | N/A | 26-07-2021 | 26-07-2021 | N/A | N/A | Partially Implemented | N/A | Two poorly conditioned structures were demolished in Sankore and Abuom in the 3rd quarter |
| 66 | Public education on child kidnapping | Social Development | N/A | N/A | 03-09-2021 | 03-09-2021 | N/A | N/A | Partially implemented | 560 | Education delivered at a church revival in Sankore |
| 67 | Organise media discussions at various information centres on disaster related issues | Environment, Infrastructure and Human Settlement | N/A | N/A | Monthly | End of year | N/A | N/A | Implemented | 75,000 | 30 media discussions were undertaken during the quarter at various information centres across the district |
| 68 | Provision of relief items to victims of fire disaster | Environment, Infrastructure and Human Settlement | N/A | N/A | 06-08-2021, 07-08-2021 | 07-08-2021 | N/A | N/A | Implemented | 22 | 22 victims benefited |
| 69 | Planting of ornamental trees and lawn development around new administration block | Environment, Infrastructure and Human Settlement | N/A | N/A | July, 2021 | September, 2021 | N/A | N/A | Implemented | N/A | Control erosion and conserve environment |
| 70 | Planting of avenue trees along major roads | Environment, Infrastructure and Human Settlement | N/A | N/A | 2nd Quarter | End of 3rd Quarter | N/A | N/A | On-going | N/A | Collaboration with forestry commission |
| 71 | Clearing of pedestrian walkways along major roads | Environment, Infrastructure and Human Settlement | N/A | N/A | Quarterly | Routine | N/A | N/A | Implemented | N/A | Ensure enough space on shoulders of roads for commuters and emergency situations |
| 72 | Provision and maintenance of street lights | Environment, Infrastructure and Human Settlement | 14,854.90 | NRSA/ DA | 2nd, 3rd, and 4th Quarters | 4th Quarter | 14,854.90 | - | Implemented | N/A | Street lightening projects intensified within the district. |

#### 2.2.3 BRIEF ANALYSIS ON THE PROGRAMMES ORGANIZED IN 2021

Most of the activities under this matrix do not receive funds for their implementation. Typical of them are the routine field activities of the Environmental Health and Sanitation unit, and the Social Welfare and Community Development Department among a few others. The Department of Agriculture embarked on the most activities in the program matrix. Over 90% of their activities were financed from Modernization Agriculture in Ghana (MAG) funds sourced from a Canadian organization (external donors). The programs undertaken by the Agric. Department were very extensive across the district with beneficiaries cutting across board. This helped strengthen the district economic goal of building a prosperous society under the policy objectives of creating an enabling agribusiness environment and enhancing agricultural production systems.

In strengthening governance, corruption and public accountability with the goal of maintaining a stable, united and safe society, all statutory meetings were successfully organized within the year with funding mostly from the Assembly’s Internally Generated Funds (IGF). General Assembly and DPCU meetings in 2021 were very effective relative to the previous years. For General Assembly, some notable activities such as voting and endorsement of the DCE, discussions and approval of the 2022 AAP and Composite Budget among others were effectively carried out. The DPCU also engaged in a series of meetings notably, preparation of the District Medium Term Development Plan, preparation of annual and quarterly progress reports among others. Other statutory meetings such as sub-committee meetings, budget committee, entity tender committee, spatial planning committee, and technical sub-committee meetings were also effectively carried out. With the successful implementation of these programs, the district has been able to deepen democratic governance, deepen political, financial and administrative decentralization, improved popular participation and deepen transparency and public accountability, all geared towards the goal of maintaining a stable, united and safe society.

A lot of attention and resources were committed into spatial planning activities to leverage on the digitization agenda of the government and ensuring the achievement of the district goal and objectives under the policy dimension, Environment, Infrastructure and Human Settlement. Notable activities in this area are the embossment of digital addresses on all commercial and residential properties/structures, street naming, and the development of planning schemes. These activities have helped promote the policy objective of sustaining socially integrated development of human settlement.

Another area that received a lot of attention is education and sensitization programmes. The Assembly realized the urgent need to rump up sensitization activities in the district across all sectors including the need for emergency preparedness following the fallout from the COVID 19 pandemic. Education and Sensitization occurred in the areas of disaster control, COVID 19 protocols and the need for the vaccines administration, best farming practices, sanitation and hygiene, and participation in decision making. Training and workshops were also organized to provide skills for the youth and also build capacity of workers within the district.

## 2.3 FUNDING SOURCES

A total of GH¢3,232,838.27 was the amount received out of the budgeted amount of GH¢6,996,428.58 representing 47.6% percent by the Asunafo South District Assembly by the end of the 2021 fiscal year. The range of the revenue sources include Internally Generated Fund (IGF), District Assemblies Common Fund (DACF), Member of Parliament Common Fund (MPCF), Disability Common Fund (PWDCF), District Development Facility (DDF) and Other Sources. A summary of the trend of revenue performance of the District is presented in Table 2.3.  As shown on Table 2.3, out of the IGF, GH¢578,820.95 estimated by the end of 2021, an amount of GH¢477,137.77 was realized representing 82.4 percent.

With respect to the revenue mobilization drive, the District performed GH¢24,655.82 less than the 2020 IGF actual receipts. In order to generate enough IGF, adequate measures have been put in place to educate the public on the need to pay rates. In addition, several actions will be taken by the Assembly to improve upon the revenue collection and management during the year, 2022. These include compilation of revenue database register for major towns in the District, establishment of a Revenue Task Force and successful implementation of the 2022 Revenue Improvement Action Plan.

With the implementation of the Assembly’s projects and programmes from the 2021 Annual Action Plan, the District managed to record 91.5 percent level of implementation. This indicates that goals and the policy objectives adopted by the Assembly were substantially achieved in 2021. This improved the building of a prosperous society, creating opportunities for all, safeguarding the natural environment and ensuring a resilient built environment, and maintaining a stable, united and safe society in the District.

TABLE 10 FUNDING SOURCES

| Expenditure Item | Baseline 2017 | Actual 2018 | Actual 2019 | Target 2020 | Actual2020 | Target 2021 | Actual 2021 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| IGF | 269,360.40 | 467,548.52 | 455,034.49 | 422,883.69 | 501,793.59 | 578,820.95 | 477,137.77 |
| DACF | 1,551,882.82 | 1,198,898.69 | 1,887,232.53 | 3,468,511.44 | 1,962,216.04 | 3,950,965.00 | 750,795.55 |
| MP’s CF | 156,971.34 | 339,739.00 | 404,138.50 | 300,000.00 | 388,724.68 | 276,567.55 | 359,251.92 |
| PWDs CF | 5,000.00 | 215,823.41 | 175,228.08 | 200,000.00 | 207,053.33 | 118,528.95 | 80,032.61 |
| DDF | 359,915.12 | 630,872.21 | 1,283,475.58 | 1,283,475.58 | 585,329.01 | 1,916,404.13 | 1,465,192.00 |
| OTHERS | 315,992.42 | 11,504.87 | 12,178.21 | 95,000.00 | 146,588.05 | 155,196.00 | 100,428.42 |
| TOTAL | 2,659,122.10 | 2,864,386.70 | 4,217,287.39 | 5,769,870.71 | 3,791,704.70 | 6,996,482.58 | 3,232,838.27 |

SOURCE: Annual Financial Statement, Finance Department, ASDA

FIGURE 3 REVENUE PERFORMANCE UPDATE

The Assembly was able to collect about 82.4 percent of its budgeted IGF. This depicts a significant decrease from the 2020 fiscal year. The decrease in total revenue mobilized is attributed to the effects and impacts of the coronavirus pandemic which resulted in the loss of livelihoods and closure of businesses and developments within the District.

#### 2.3.1 UPDATE ON DISBURSEMENTS FROM FUNDING SOURCES

This section of the progress report brings on board the revenue and expenditure for the year under review. This will demonstrate the total revenue generated within the year and how funds were released to finance the expenditure of the 2021 Composite Budget and the 2021 Annual Action Plan.

From Table 2.4, in 2021, an amount GH¢5,418,718.48 representing 61.6 percent out of the total estimated expenditure of GH¢8,803,119.21 was spent. However, out of the total actual receipts of GH¢3,232,838.27, the District spent GH¢5,418,718.48 leaving a balance deficit of GH¢2,185,880.21 (67.6 percent). All the expenditure items represent all the programmes, projects and activities in the 2021 Annual Action Plan and 2021 Composite Budget, which were prepared from the DMTDP 2018-2021

TABLE 11 UPDATE ON DISBURSEMENTS FROM FUNDING SOURCES

| Expenditure Item | Baseline 2017 | Actual 2018 | Actual 2019 | Target 2020 | Actual 2020 | Target 2021 | Actual 2021 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Compensation | 1,425,918.73 | 1,636,900.69 | 1,656,426.51 | 1,948,594.80 | 1,905,258.69 | 2,502,241.09 | 2,430,066.28 |
| Goods and Service | 1,171,185.29 | 1,561,688.17 | 2,326,802.66 | 2,387,675.58 | 1,851,073.98 | 3,240,976.18 | 405,494.91 |
| CAPEX | 978,923.27 | 1,406,729.56 | 1,800,915.41 | 3,468,511.44 | 2,113,633.37 | 2,949,550.64 | 2,547,734.11 |
| Others | - | 19,850.00 | 69,058.08 | 24,500.00 | 57,604.95 | 110,351.30 | 35,423.18 |
| TOTAL | 3,576,027.29 | 4,625,168.42 | 5,853,202.66 | 7,829,281.82 | 5,927,570.99 | 8,803,119.21 | 5,418,718.48 |

## 2.4 UPDATE ON INDICATORS AND TARGETS

#### 2.4.1 DISTRICT CORE INDICATORS AND TARGETS

As the main objective of monitoring is to track implementation and outputs and measure the effectiveness of programmes and projects, these critical indicators are to provide snap shot of progress made in achieving the NMTDPF broad thematic objectives at the district level and augment the National Annual Progress Report. The table below gives details of various indicators grouped under the Development Dimension of Agenda for Jobs and their level of achievement in 2021.

TABLE 12 PERFORMANCE INDICATORS AT THE DISTRICT LEVEL

|  | Indicator (Categorised by Development Dimension of Agenda for Jobs) |  | Baseline (2017) |  | Actual 2018 |  | Actual 2019 |  | Target 2020 |  | Actual2020 |  | Target2021 |  | Actual2021 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CORE INDICATORS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Total output in agricultural production |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Maize |  | 602 |  | 400 |  | 532 |  | 675 |  | 573 |  | 639 |  | 595 |  |
|  | - Rice (milled), |  | 576 |  | 648 |  | 768 |  | 940 |  | 878 |  | 820 |  | 900 |  |
|  | - Cassava |  | 261,183 |  | 341,377 |  | 331,793 |  | 350,213 |  | 323,721 |  | 350,712 |  | 331,679 |  |
|  | - Yam |  | 212 |  | 591 |  | 532 |  | 417 |  | 363 |  | 400 |  | 315 |  |
|  | - Cocoyam |  | 70,147 |  | 73,526 |  | 73,621 |  | 68,620 |  | 67,240 |  | 60,515 |  | 40,535 |  |
|  | - Plantain |  | 267,393 |  | 275,420 |  | 219,750 |  | 275,416 |  | 273,240 |  | 260,700 |  | 263,700 |  |
|  | - Cocoa |  | 12,219 |  | 13,370 |  | 9,398 |  | 9,472 |  | 9,478 |  | 7,040 |  | 6,732 |  |
|  | - Oil palm |  | 12,213 |  | 11,215 |  | 12,204 |  | 9,855 |  | 9,623 |  | 10,613 |  | 9,134 |  |
|  | - Cattle |  | 800 |  | 920 |  | 1,013 |  | 1,500 |  | 1,460 |  | 2,200 |  | 1,620 |  |
|  | - Sheep |  | 17,000 |  | 20,325 |  | 20,913 |  | 22,000 |  | 19,800 |  | 23,121 |  | 19,200 |  |
|  | - Goat |  | 6,000 |  | 7,123 |  | 7,914 |  | 8,000 |  | 7,021 |  | 9,000 |  | 7,125 |  |
|  | - Pig |  | 10,000 |  | 11,139 |  | 11,819 |  | 12,250 |  | 13,729 |  | 14,817 |  | 13,028 |  |
|  | - Poultry |  | 19,217 |  | 21,666 |  | 22,851 |  | 23,994 |  | 23,013 |  | 24,819 |  | 23,088 |  |
| 2 | Percentage of arable land under cultivation |  | 64.8% |  | 66.7% |  | 65.3% |  | 68.3% |  | 65.1% |  | 70% |  | 66.6% |  |
| 3 | Number of new industries established |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Agriculture |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |
|  | - Industry |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |
|  | - Service |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |
| 4 | Number of new jobs created |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Agriculture |  | 810 |  | 0 |  | 0 |  | 4,000 |  | 4,733 |  | 2,000 |  | 2,166 |  |
|  | Industry |  | 0 |  | 0 |  | 0 |  | 20 |  | 0 |  | 20 |  | 0 |  |
|  | Service |  | 0 |  | 0 |  | 11 |  | 10 |  | 0 |  | 15 |  | 7 |  |
|  | SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Net enrolment ratio |  | 84.4% |  | 78.7% |  | 73.2% |  | 74.1% |  | 64.9% |  | 65.1% |  | 60.9% |  |
|  | - Kindergarten |  | 83.6% |  | 78.6% |  | 73.4% |  | 73.4 |  | 68.1% |  | 68.1% |  | 67.3% |  |
|  | - Primary |  | 46.4% |  | 40.3% |  | 38.2 |  | 38.2 |  | 37.1% |  | 38.1% |  | 30.0% |  |
|  | - JHS |  | 0.95 |  | 0.95 |  | 0.96 |  | 0.98 |  | 1.01 |  | 1.01 |  | 1.02 |  |
| 6 | Gender Parity Index |  | 0.91 |  | 86.5 |  | 0.90 |  | 0.91 |  | 0.92 |  | 0.93 |  | 0.96 |  |
|  | - Kindergarten |  | 0.83 |  | 88.7 |  | 0.81 |  | 0.83 |  | 0.88 |  | 0.89 |  | 0.94 |  |
|  | - Primary |  | 0.76 |  | 0.89 |  | 0.90 |  | 0.92 |  | 0.89 |  | 0.95 |  | 1.05 |  |
|  | - JHS |  | 98.2% |  | 96.8% |  | 91.8% |  | 92.1% |  | 84.1% |  | 85.1% |  | 87.3% |  |
|  | - SHS |  | 96.2% |  | 86.5% |  | 90.6% |  | 91.1% |  | 88.0% |  | 88.0% |  | 83.6% |  |
| 7 | Completion rate |  | 74.4% |  | 88.7% |  | 82.3% |  | 83.1% |  | 78.4% |  | 78.1% |  | 77.3% |  |
|  | - Kindergarten |  | 33.7% |  | 34.6% |  | 45.9% |  | 48.1% |  | 38.2% |  | 40.%1 |  | 41.1% |  |
|  | - Primary |  | 84.4% |  | 78.7% |  | 73.2% |  | 74.1% |  | 64.9% |  | 65.1% |  | 60.9% |  |
|  | - JHS |  | 83.6% |  | 78.6% |  | 73.4% |  | 73.4 |  | 68.1% |  | 68.1% |  | 67.3% |  |
|  | - SHS |  | 46.4% |  | 40.3% |  | 38.2 |  | 38.2 |  | 37.1% |  | 38.1% |  | 30.0% |  |
| 8 | Number of operational Health facilities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - CHPS Compound |  | 12 |  | 12 |  | 12 |  | 13 |  | 13 |  | 14 |  | 14 |  |
|  | - Clinic |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |
|  | - Health Centre |  | 1 |  | 1 |  | 1 |  | 3 |  | 3 |  | 3 |  | 3 |  |
|  | - Hospital |  | 0 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |
| 9 | Proportion of population with valid NHIS card |  | 31% |  | 26% |  | 32.3% |  | 37.3% |  | 29.8% |  | 47.8% |  | 48.5% |  |
|  | - Total (by sex) |  | M=15.1% F=15.9% |  | M=11.7% F=14.3% |  | M=13.3% F=16.3% |  | M=16% F=21.3% |  | M=14% F=15.8% |  | M=21.5% F=26.3% |  | M=22.8% F=25.7% |  |
|  | - Indigents |  | 0.37% |  | 1.06% |  | 2.57% |  | 8.4% |  | 4.56% |  | 7.42% |  | 6.46% |  |
|  | - Informal |  | 6.33% |  | 6.45% |  | 8.25% |  | 8.30% |  | 8.37% |  | 9.5% |  | 9.94% |  |
|  | - Aged |  | 1.13% |  | 0.97% |  | 1.12% |  | 1.15% |  | 1.07% |  | 1.1% |  | 1.05% |  |
|  | - Under 18 years |  | 8.18% |  | 8.05% |  | 8.29% |  | 8% |  | 7.28% |  | 8% |  | 8.10% |  |
|  | - Pregnant women |  | 2.38% |  | 2.09% |  | 1.74 |  | 1.7% |  | 1.44% |  | 1.5% |  | 1.10% |  |
| 10 | Number of Births and Deaths Registered |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Births (sex) |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | N/A |  | M=1,087 F=1,081 |  |
|  | - Deaths (sex, age group) | Age grp | M | F | M | F | M | F | M | F | M | F | M | F | M | F |
|  |  | 0-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 |
|  |  | 11-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 |
|  |  | 18-39 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3 | 1 |
|  |  | 40-59 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 |
|  |  | 60+ | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3 | 0 |
| 11 | Percentage of population with sustainable access to drinking water |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - District |  | 80% |  | 84% |  | 85.75% |  | 100% |  | 87.5% |  | 100% |  | 88.5% |  |
|  | - Urban |  | 95% |  | 97% |  | 97% |  | 100% |  | 98% |  | 100% |  | 98% |  |
|  | - Rural |  | 65% |  | 71% |  | 74.5% |  | 100% |  | 77% |  | 100% |  | 79% |  |
| 12 | Proportion of population with access to improved sanitation services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - District |  | 40% |  | 25% |  | 55% |  | 75% |  | 60% |  | 80% |  | 50% |  |
|  | - Urban |  | - |  | - |  | - |  | - |  | - |  | - |  | - |  |
|  | - Rural |  | - |  | - |  | - |  | - |  | - |  | - |  | - |  |
| 13 | Maternal mortality ratio (institutional) |  | 1 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |
| 14 | Malaria case fatality (institutional) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Sex |  | M=2 F=0 |  | M=0 F=0 |  | M=2 F=0 |  | M=0 F=0 |  | M=1 F=0 |  | M=0 F=0 |  | M=1 F=0 |  |
|  | - Age group |  | CH=0 AD=2 |  | CH=0 AD=0 |  | CH=2 AD=0 |  | CH=0 AD=0 |  | CH=1 AD=0 |  | CH=0 AD=0 |  | CH=1 AD=0 |  |
| 15 | Number of recorded cases of child trafficking and abuse |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Child trafficking (sex) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |
|  | - Child abuse (sex) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |
| 16 | Percentage of road network in good condition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Total |  | 35% |  | 38% |  | 32% |  | 80% |  | 18% |  | 85% |  | 25% |  |
|  | - Urban |  | 10% |  | 15% |  | 18% |  | 30% |  | - |  | 30% |  | - |  |
|  | - Feeder |  | 25% |  | 23% |  | 14% |  | 50% |  | 18% |  | 55% |  | 25% |  |
| 17 | Percentage of communities covered by electricity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - District |  | 63% |  | 65% |  | 69% |  | 100% |  | 75% |  | 100% |  | 81% |  |
|  | - Rural |  | 26% |  | 30% |  | 38% |  | 100% |  | 50% |  | 100% |  | 62% |  |
|  | - Urban |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  |
| 18 | Reported cases of crime |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Men |  | 319 |  | 169 |  | 207 |  | - |  | 149 |  | - |  | 103 |  |
|  | - Women |  | 136 |  | 103 |  | 103 |  | - |  | 88 |  | - |  | 94 |  |
|  | - Children |  | 7 |  | 3 |  | 4 |  | - |  | 1 |  | - |  | 4 |  |
| 19 | Percentage of Annual Action Plan implemented |  | 89.8 |  | 90 |  | 90.4 |  | 100 |  | 91.8 |  | 100 |  | 91.5 |  |
| 20 | Number of communities affected by disaster |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Bushfire |  | 2 |  | 0 |  | 1 |  | 0 |  | 1 |  | 0 |  | 0 |  |
|  | - Flood |  | 2 |  | 0 |  | 2 |  | 0 |  | 1 |  | 0 |  | 0 |  |

## NOTE:  The indicators with N/A denotes information NOT AVAILABLE.

Maize, Rice, Cocoa were recorded in Metric Tons

Cassava, Cocoyam, yam are recorded in Tubers

## 2.5 ECONOMIC DEVELOPMENT

The Economic development policy dimension at the District level has seen some level of improvement over the years. The trend of the indicators reveals a seemingly steady progress in the sector. Below is a detailed analysis of the Economic development indicators.

Under Agriculture, there was a slight improvement in the total yield for the two cereals, Maize and Rice recording 592 and 900 metric tons respectively in 2021 as against 573 metric tons for Maize and 878 for Rice in 2020. Rice production in the District could be more lucrative if farmers had access to certain critical logistics and machineries. The arable land in Asunafo South is one that is very fertile and suitable for rice production. The level of production as recorded above is not the optimal level due to a number of challenges including low technology levels and changes in rainfall patterns. The Department of Agriculture in Asunafo South is doing its possible best to support rice farmers and also pushing in collaboration with the Assembly to get a rice processing factory (1D1F Initiative) to boost rice production. Cassava also experienced an increase in 2021 with the difference as 7,958 tubers. Produce such as yam, cocoyam, plantain and oil palm all experienced a negative growth from 2020 to 2021. Plantain which is the 4th major crop grown in the District, recorded 263,700 in 2021 as against 273,240 in 2020 revealing a downward growth. Similar trend applies to the other produce other than maize and cassava.

The slight decrease in the production of domestic crops is partly attributed to farmers shifting some attention to the production of vegetables which is currently gaining some momentum. Particular mention are Cabbages and Tomatoes. In 2021, 10,553 tons of cabbage and 738.4 boxes of Tomatoes were produced. In 2017, Cabbage recorded 592.6 tons with Tomato recording 372.1 boxes. There was a huge jump of over 1000% (1,680%) in cabbage production from the base year (2017) to the end of the plan period (2021). This scenario explains why traditional crops like cocoyam and plantain experienced reductions.

On livestock production, rearing of goat in particular isn’t so lucrative due to cultural factors. Most of the traditional areas in the district abhor the rearing of goats accounting to the very low records. Nonetheless, other livestock such as poultry and pig have been considerably sustainable in terms of the numbers.

Cocoa production is a major farming business in the district. From the indicator, it is realized that cocoa yield has been declining after achieving bumper yields in 2017 and 2018. In 2017, total output was 12,219 Metric tons. This appreciated to 13,370 in 2018 and saw a huge fall in 2019 at 9,398 metric tons. According to the quality control unit of COCOBOD in the District, the trend has it that anytime the district experiences bumper harvest, it is naturally preceded with a relatively low harvest in the subsequent year. This explains the fall between 2018 and 2019. In 2020, output increased slightly to 9,478 and saw a sharp decline to 6,732 metric tons in 2021. The decline however was anticipated, hence reflective in the 2021 target of 7,040 and this is due to reported cases of diseases affecting the farms and its associated intent to cut down all cocoa trees affected. The Sankore area which produces the most bags for the district were greatly affected by the cutting of infected cocoa trees exercise which in turns translated into the lower output recorded for the year. Other factors include change in rainfall patterns. The department in charge of cocoa affairs in the district (COCOBOD) intends to embark on massive education for all cocoa farmers in the District in order to restore the seasons of bumper harvest in subsequent production years.

Total arable land under cultivation as at end of 2021 stood at 66.6% which is 1.5% higher than that of 2020 at 65.1%. This ideally should have generated a positive correlation with yield (all things being equal) judging from the figures under the economic indicators. However, as mentioned earlier, the diversion of production into vegetables has been one of the major reasons for such outlook. Again, some of the arable lands have been used to grow perennial cash crops like cocoa which will take some time to yield. It is however expected that going forward, the District will record much higher output figures in the near future judging from the response of farmers to extension advices from AEAs.

Job Creation

Job creation is one important component if not the most among all the indicators in the medium term plan. This is reflective in the main theme for the 2018-2021 NMTDP, ‘Agenda for Jobs’. Under the new jobs created indicator, it is realized that the district created more jobs in the Agriculture sector than the other two sectors. This tells how vibrant agriculture is in the Asunafo South District.

All the jobs created under the Agric. Sector come from the cocoa industry. In the base year 2017, total number of jobs under Agriculture was 810 recruited under cocoa pollination and cocoa pruning. However, in the 2018 and 2019 seasons, no new jobs were created under the sector. In 2020, the Agriculture sector experienced a significant increase in new jobs with a figure of 4,733. These jobs were also created from the cocoa sector with 4,444 recruited into cocoa rehabilitation and 289 into cocoa pollination exceeding the 2020 new job creation target of 4,000 under agriculture. The reporting year 2021 saw 2,166 new jobs created under the Agriculture sector once again all from the cocoa sub sector. Here, all the 2,166 new jobs were recruited into cocoa rehabilitation unto the existing 4,733 in 2020.

The services sector in 2021 also created 7 new jobs in the district. 5 out of the 7 were absorbed into the National Disaster Management Organization as zonal disaster management coordinators and the remaining 2 recruited as driver and secretary respectively for the District Chief Executive.

All the economic indicators detailed above come together to ensure that the district goal which is to build a prosperous society and the main theme for the plan which is agenda for jobs are achieved. Although it cannot be said that the goal has been fully achieved, a number of policy objectives under the goal have been achieved. These objectives include modernizing and enhancing agricultural production, creating an enabling agribusiness environment, and promoting agriculture as a viable business among the youth.

## 2.6 SOCIAL DEVELOPMENT

The Social Development goal as adopted from the national goal is to create equal opportunities for all. The district in its effort to achieving this goal deployed a host of social development interventions (the highest in terms of activities among the four policy dimensions) across the length and breadth of the District to ensure uniform distribution and equity.

In terms of educational interventions, a lot of efforts were devoted into bridging the gender parity index and the indicators show a positive result. The District targeted to achieve a gender parity index of 1.01 for the year 2021 and ended up with an index of 1.02. Completion rate also shot up above the target from 84.1% in 2020 to 87.3% in 2021. This indicates a further improvement in reducing the rate of dropouts and enhancing equitable access to, and participation in quality education at all levels fulfilling a policy objective under this dimension. This success story in the education sector was achieved through the collaborative efforts of the District Education Directorate and the District Assembly in the areas of increasing physical projects and intensifying outreach and capacity building.

In the health sector, the District beefed up its strength in the area of access by adding one more CHPS compounds in 2021. There is still no clinic in the District. For Health centres, the District added two more in 2020 to arrive at 3 in total with none added in 2021. Access to quality health care in general is fairly good yet more room for improvement. The outlook on Maternal Mortality and Malaria case fatality remain positive as the former recorded 0 for four consecutive years (2018, 2019, 2020, 2021) which also implies that throughout the four-year plan period, there was no maternal mortality recorded. These successes are as a result of intensive outreach programs and education. Antenatal and postnatal services are more patronized and this has helped check maternal and infant mortalities. Hence, the objective of ensuring accessible and quality universal health coverage for all has been enhanced to create equal opportunities for all.

Another critical indicator that has seen improvement under the Social Development dimension is the proportion of population with valid NHIS cards. From the table, 2017 which is the base year recorded a total proportion of 31% of the population, with 2021 recording 48.5% of the total population. This indicates a significant improvement over the plan period attributed to intensive education and sensitization, increased access to health facilities, and periodic mobile registrations in rural communities in the district.

On Number of recorded cases of child trafficking and abuse under indicator 15, the district did not record any cases throughout the plan period. This may sound unusual as it is expected that in a span of four (4) years, there should be at least some recorded cases of child abuse. However, the Asunafo South District throughout the four-year plan period recorded zero (0) cases of child trafficking and abuse as seen in the table above. This is due to effective education and counselling programmes for mothers through community health outreach programmes, antenatal and postnatal counselling workshops, and special programmes for women periodically organized by a gender-based Non-Governmental Organization, Abantu for Development. These and many other sensitization outreaches by the department of Social Welfare and Community Development, are the major factors that have contributed to the zero (0) record of child trafficking and abuse cases over the whole plan period strengthening the policy objective of preventing and protecting children from all violence, abuse, neglect and exploitation.

The social development dimension indicators analyzed above point to a positive direction of ensuring equal opportunities for all.

## 2.7 ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENT

Under this development dimension, the district chalked some level of successes in the area of disaster prevention. From the records, the district did not record any disasters from bushfire and floods. Measures put in place to achieve this feat include intensive sensitization and awareness creation. The District’s disaster prevention officers also engaged media houses and information centres and also appeared in community durbars to educate the populace on disaster prevention.

On Infrastructure, the District’s Feeder Roads Department targeted to upgrade 85% of its roads in 2021 but ended up upgrading only 25%. The huge difference is mainly attributed to funding. The 25% done constituted seven (7) feeder roads projects financed by COCOBOD. Although far from the target, the few done, have contributed to the socioeconomic development of the District and the policy objective of improving efficiency and effectiveness of road transport infrastructure and services towards the goal of ensuring a resilient built environment.

## 2.8 GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY

Under this thematic area, the District in terms of security performed better within the plan period. From the data above, reported crime cases for the base year 2017 was 462 in total. This figure reduced drastically to 275 in 2018, 314 in 2019, 238 in 2020 and 201 in 2021. There is a whopping 130 percentage decrease in crime cases in the district between 2017 and 2021. Some of the factors that accounted for this success story are; increased police visibility, rampant patrols, increased police post and the establishment of the Sankore District command among others. This has tremendously contributed to the enhancement of security service delivery as the district’s security objective towards the goal of maintaining a stable, united and safe society.

## 2.9 DISTRICT SPECIFIC INDICATORS

Indicators are needed for measuring progress while targets are specific, planned level of results expected to be achieved within a timeframe. The selection of indicators for the M&E plan was based on the outcome of the stakeholders’ meeting held with the 11 Decentralized Departments and other agencies. The District Specific Indicators were selected and linked in relation to the adopted policy objectives of the District. The core indicators (20) were agreed at the national level (NDPC) whereas the specific indicators were agreed at the District level (DPCU). These indicators have been disaggregated, where possible, into age, gender, location and among others.

TABLE 13 PRESENTS THE MONITORING INDICATORS, BASELINES AND TARGETS OF THE DISTRICT SPECIFIC INDICATORS

| DISTRICT SPECIFIC INDICATORS |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Indicator (Categorised by Development Dimension of Agenda for Jobs) | Baseline (2017) | Actual 2018 | Actual 2019 | Target 2020 | Actual 2020 | Target 2021 | Actual 2021 |
| 1 | Total output in selected vegetable production |  |  |  |  |  |  |  |
|  | - Cabbage | 592.6 | 811.8 | 896.1 | 960.3 | 973.4 | 1,160 | 1,553 |
|  | - Tomato | 372.1 | 423.6 | 528 | 650.7 | 625.8 | 800 | 739.9 |
| 2 | Proportion of case workers trained in child protection and family welfare | - | - | - | - | - | 1 | - |
| 3 | Number of child violence cases benefitting from social welfare/social services | 20 | 17 | 20 | 21 | 18 | 9 | 9 |
| 4 | Number of children reached by social work/social services | 5000 | 3287 | 4449 | 1200 | 500 | 3287 | 3000 |
| 5 | Number of people reached with child protection and SGBV information | - | - | - | - | - | 390 | 270 |
| 6 | Number of LEAP household members on NHIS | 842 | 842 | 842 | 842 | 842 | 842 | 842 |
| 7 | Number of households with adolescent girls benefiting from LEAP Programme | 573 | 553 | 553 | 558 |  | 553 | 559 |
| 8 | Number of outreach visits to communities with LEAP households | 6 | 6 | 6 | 6 | 5 | 6 | 5 |
| 9 | Number of referrals received from GHS | - | - | 3 | 9 | 4 | 15 | 6 |
| 10 | Proportion of referrals receiving adequate follow-up | - | - | 100% | 100% | 100% | 100% | 100% |
| 11 | Number of DSWCD’s that have shared their MMDA’s LEAP Household data with both NHIS and GHS | 382 | 382 | 382 | 382 | 382 | 382 | 382 |
| 12 | Number of regional intersectoral monitoring visits | - | 4 | 4 | - | 4 | 4 | 2 |
| 13 | Number of meetings to discuss integrated services | - | - | - | - | - | 3 | 1 |
| 14 | Number of girls reached by prevention and care services | - | - | 1250 | - | 400 | 2450 | 1450 |
| 15 | Number of CP/SGBV cases referred to other services and followed up | - | - | - | - | - | 3 | 2 |
| 16 | Number of NGOs, including RHCs, trained | - | - | - | - | - | 3 | - |
| 17 | Number of children in RHCs profiled and reunified | - | - | - | - | - | 3 | 1 |
| 18 | Proportion of sub-standard RHCs closed | - | - | - | - | - | - | - |
| 19 | Number of children placed in foster care | - | - | - | - | - | - | - |
| 20 | Proportion of population with access to basic drinking water sources | 80% | 84% | 85.75% | 100% | 87.5% | 100% | 88.5% |
| 21 | Proportion of population with access to improved sanitation services | 40% | 25% | 55% | 75% | 60% | 80% | 50% |
| 22 | Proportion of people in ODF communities | 30% | 40% | 55% | 60% | 75% | 80% | 50% |

The District in determining specific indicators that suits it, focused much attention on social issues, precisely from the Department of Social Welfare and Community Development. Meanwhile, there are a few economic development and environmental specific indicators captured.

Under Economic Development, the district has realized a huge potential in the production of vegetables in recent years. Two of those vegetables have been selected among the district specific indicators. The production of cabbage yielded 592.6 in the base year, 811.8, 896.1 and 960.3 in 2018, 2019 and 2020 respectively. In 2021 however, there was a significant jump to 1,553 metric tons. A similar trend can be said about output on Tomatoes. This confirms the earlier assertion that there is a huge potential in the production of vegetables in the district.

THE FOLLOWING EXPLAINS EACH INDICATOR UNDER SOCIAL SERVICES.

- Number of trainings conducted on ISSOPse:  One training was conducted on intersectoral standard operating procedures for Child Protection and Family Welfare (ISSOPse) in Accra at Sun Lodge Hotel, Tesano on 25th to 27th October 2021. The training by the Ministry of Gender Children and Social Protection in collaboration with the department of social welfare.  Sixty districts were in attendance in which Asunafo South District was part the programme was supported by USAID aimed at building the capacity of the social welfare officers directly working with children in their various district, the participant was a female.

- Proportion of case workers trained in child protection and family welfare:  officers were trained in Child Protection & Family Welfare in 2021 in Accra Sun Lodge Hotel, Tesano the participant was a female.

- In 2017, 20 child violence cases were targeted and recorded out of which 17 of them were the actuals selected, that is 7males and 10 females to benefit from social welfare and social services. In 2019 again 20 of the children benefited from social services whereas 12 were females. In the year 2020, 21 children were targeted out of which 18 were actuals reached with social services, that is 10 males and 8 females. In the year 2021, 9 was the target and all the 9 have been actualized.  That is Five females and four males. The target reduced in 2021 because of financial constraint.

- Number of children reached by social work/social services: In 2017 the department had 5000 children as baseline to reach with social services and 3287 was the actual figure of children reached for social work and social services in 2018 out of which 2000 were females and 1287 were males. In 2019, 4449 children were reached for social work/service and the break down is 2000 males and 2449 were females. The year 2020 target was 1200 out of which 500(female 220, male 230) was reached as the actual due to the covid-19 pandemic we could not reach more of our target. The department target in 2021 was 2387 but the actual children reached were 3000 (2800 female, 1200 males) hence the actual was more than the target because there were carry forward of some cases from 2020. Children reached were from leap households, children with disability, children in education sector and other orphans and vulnerable children (OVCs) groups.

- Number of people reached with child protection and SGBV information: In 2021 we targeted 390 children but achieved 270 (180 males, 90 females) as the actual people reached with child protection and sexual and gender base violence (SGBV) information.

- Number of LEAP household members on NHIS:  the total number of leap household’s members on NHIS stands at 842 from 2017 down to 2021

- Number of households with adolescent girls benefiting from LEAP Programme:  in the year 2017 the baseline number of adolescent girls in leap beneficiary’s households was 573 and actual was 533 for 2018 and 2019 respectively. In the year 2020 the baseline figure was 558 but there were no actuals realized. Reason being that, due to the pandemic the department could not gather data. In the year 2021 the department used the 2019 figure as its target and had an actual of 559 adolescent girls benefiting from the programme.

- Number of outreach visits to communities with LEAP households in the year 2017, 2018, and 2019 were the same. But in 2020 the department targeted 6 but 5 were actualized.  In each year 2021 the same figure was achieved. The reason being that funds were not available for the outreach programme.

- In the year 2017 and 2018 there were no referral s made from the Ghana health service. But in the year 2019, 3 males were refereed for support in the area of disability. In 2020 the department target was 9 but only had 4 referrals (2males and 2 females) with child protection issues. Finally, in 2021l, 15 were targeted and 6 (2 males 4 females) were actualized.

- Proportion of referrals receiving adequate follow-up:  in the year 2019 3% of the Proportion of referrals were receiving adequate follow-up. 4% in 2020 and 6% in 2021.

- Number of DSWCD’s that have shared their MMDA’s LEAP Household data with both NHIS and GHS: the department shared 382 leap household data with only NHIS and the figure is 382 from 2017-2021. The reasons were that, a total of 382 leap household data was the only approved figure given by the leap secretariat at the national to the department.

- Number of regional inter sectoral monitoring visits: the department in 2018 and 19 received four regional inter sectoral monitoring visits respectively. Whereas the department in 2020 received 4 regional inter sectoral monitoring visit and 2 in 2021.

- Number of meetings to discuss integrated services: the department targeted 3 integrated services meetings but achieved one (1) due to financial constraint

- Number of girls reached by prevention and care services: 1250 girls were reached by prevention and care services in 2019. In 2020 the department did not set any target due to the pandemic but reached out to 400 girls. In 2021 the target was 2450 and the department achieved 1450

- Number of CP/SGBV cases referred to other services and followed up: in the year 2021 the department targeted 3 Child protection, sexual and gender base violence cases but only had 2 which has been referred to other services.

- In the year 2021 only three of NGOs, including rehabilitation homes and centres RHCs, were targeted to be trained.

- Number of children in RHCs profiled and reunified: the department targeted three cases but only had one (male) case of a child in rehabilitation home and centres profiled and reunified.

- Proportion of sub-standard RHCs closed: unfortunately, Asunafo South District does not have any sub-standard rehabilitation homes or centres known to the department RHCs for closure

- There were no children placed under foster care in the district from 2017 to 2021.

## 2.10 UPDATE ON CRITICAL DEVELOPMENT AND POVERTY ISSUES

This section provides an update of the critical development and poverty issues being implemented

in the District. These include Ghana School Feeding Programme, Capitation Grant, National Health Insurance Scheme, LEAP Programme, National Youth Employment Program, Nation Builder Corps, One District-One Factory Programme, and Planting for Food and Jobs, Free SHS Programme, and National Entrepreneurship and Innovation Plan (NEIP) among others. In order to provide lasting solutions to the challenges identified, policy recommendations have been provided under each section.

The Assembly has successfully created a conducive investment environment for the implementation of critical development and poverty issues targeted at improving the standard of living especially among the most deprived people in the District. This includes supporting government interventions like Free SHS, Planting for Food and Jobs programme, Livelihood Empowerment Against Poverty, the National Youth Employment Program and the Nation Builders’ Corpse among others. In marching the achievement to the District’s goals and objectives, the District has, beyond the numerous challenges, improved in; building a prosperous society, creating opportunities for all, safeguarding the natural environment and ensuring a resilient built environment, and maintaining a stable, united and safe society.

From the table, it can be realized that some of the flagship programmes do not have data allocated to them. This is because they do not take place in our district. All those programmes have been however denoted ‘N/A’ meaning ‘not applicable/available’ for clarity. PFJ was one of the most beneficial interventions in the district. It directly benefited 7,103 people, 1,603 more than the target. However, the Department of Agriculture in the district believe strongly that with the interventions and hard work invested in the programme, the numbers could have been more. Reason being that, agriculture inputs although subsidized, was still high for many who wanted to enroll. Also, no monetary allocation was made to the department to undertake more activities in order to get many more farmers enrolled. That notwithstanding, the PFJ program was a huge success with the hope that it will be even better if some more commitments are invested in.

The National Health Insurance Scheme is also another flagship initiative that has seen massive development in the Asunafo South District. The scheme was able to exceed its target by renewing and enrolling 864 beneficiaries on top of the targeted 57,708 to arrive at 58,572 by the end of 2021. The district’s NHIA team intensified sensitization and outreach throughout the year.

TABLE 14 CRITICAL DEVELOPMENT AND POVERTY ISSUES

| CRITICAL DEVELOPMENT AND POVERTY ISSUES | ALLOCATION GH¢ | ACTUAL RECEIPT GH¢ | NO OF BENEFICIARIES |  |
| --- | --- | --- | --- | --- |
|  |  |  | Targets | Actuals |
| Ghana School Feeding Programme | 881,532.12 | 881,532.12 | 4,800 | 4,886 |
| Capitation Grants | 77,744.76 | 60,400.80 |  | 25,167 |
| National Health Insurance Scheme | 134,053.00 | 79,089.37 | 57,708 | 58,572 |
| National Youth Employment Program | 12,000.00 | 21,600.00 | - | 120 |
| Livelihood Empowerment Against Poverty (LEAP) programme | 66,842.60 | 66,842.60 |  | 382 |
| One District-One Factory Programme | N/A | N/A | N/A | N/A |
| Planting for Food and Jobs Programme | 18,562,150.00 | 18,562,150.00 | 5,500 | 7,103 |
| Free SHS Programme | 1,003,112.73 | 868,707.00 | 3,321 | 3,321 |
| National Entrepreneurship and Innovation Plan (NEIP) | N/A | N/A | N/A | N/A |

NATION BUILDERS CORPs(NABCO)

From table 2, the Nation Builders Corps has a total of One Hundred and Twenty (120) trainees as at end of 2021 in the Asunafo South District. This is made up of Ninety-Four (94) males and Twenty-Six (26) females.

On placement, the trainees continued to work in the various departments and agencies such as the GES, LGS, GHS, GRA and NHIS among others under the modules of NABCO as indicated above

TABLE 15 ENROLMENT UNDER THE NATION BUILDERS CORPS (NABCO)

| MODEL | TOTAL NO. OF BENEFICIARIES |  | TOTAL |
| --- | --- | --- | --- |
|  | Male | Female |  |
| Revenue Ghana | 12 | 5 | 17 |
| Educate Ghana | 44 | 18 | 62 |
| Heal Ghana | 4 | 0 | 4 |
| Civic Ghana | 17 | 1 | 18 |
| Feed Ghana | 8 | 1 | 9 |
| Digitize Ghana | 5 | 1 | 6 |
| Enterprise Ghana | 4 | 0 | 4 |
| Total | 94 | 26 | 120 |

FIGURE 5 below Indicates that education had the highest enrollment (52%) of the NABCO personnel followed by civic Ghana (15%), then revenue Ghana (14%), feed Ghana (8%), digitize Ghana (5%), and lastly is heal Ghana (3%) and enterprise Ghana (3%)

FIGURE 4 ENROLMENT UNDER THE NATION BUILDERS CORPS(NABCO)

## LIVELIHOOD EMPOWERMENT AGAINST POVERTY (LEAP)

Under the LEAP programme initiated, a Social Protection measure to cushion orphans, people with severe disability and the aged with subsistence grant. The total number of beneficiaries as at 2021 is 382 across the District. An amount of GH¢132,627.20 has been paid to the 382 beneficiaries. This amount was payed over four (4) cycles (from January to August).

## YOUTH EMPLOYMENT AGENCY (YEA)

The Agency received applications under the following modules; Community Police Assistant, youth in Sports and Arabic instructors.

A total of fifty-three (53) youth had been engaged in three (3) modules as at 2021. Out of this, thirty-seven (37) were males and sixteen (16) were females.

SCHOOL FEEDING PROGRAMME IMPLEMENTATION

The District has currently 13 primary/KG schools benefiting from the program covering 4,886 pupils out of which 2,541 are males and 2,345 are females. Tremendous improvement in terms of enrolment has been registered since its inception.

TABLE 16 LIST OF BENEFICIARY SCHOOLS UNDER THE SCHOOL FEEDING PROGRAMME IN THE DISTRICT WITHIN THE FOURTH QUARTER, 2021

| S/N | NAME OF SCHOOL | NUMBER OF BENEFICIARIES |  | TOTAL |
| --- | --- | --- | --- | --- |
|  |  | Male | Female |  |
|  | Yankye D/A Primary | 191 | 163 | 354 |
|  | Domeabra D/A Primary | 212 | 259 | 471 |
|  | Kukuom R/C Primary | 203 | 186 | 389 |
|  | Atotrom D/A Primary | 148 | 146 | 294 |
|  | Asibrem D/A Primary | 257 | 202 | 459 |
|  | Sikafrebogya D/A Primary | 90 | 101 | 191 |
|  | Siana D/A Primary | 193 | 158 | 351 |
|  | Pafo D/A Primary | 47 | 42 | 89 |
|  | Anum D/A Primary | 173 | 141 | 314 |
|  | Pesewkrom D/A Primary | 190 | 152 | 342 |
|  | Tettekwao D/A Primary | 177 | 157 | 334 |
|  | Ntonso D/A Primary | 98 | 83 | 181 |
|  | Wejakrom D/A Primary | 198 | 180 | 378 |
|  |  | 2,541 | 2,345 | 4,886 |

Source: ASDA, School Feeding Desk Office, December, 2021

FREE SENIOR HIGH SCHOOL POLICY

The Free Senior High School Policy is one of the flagship policies to be introduced in Ghana. It is aimed at providing access to free quality senior high education to all children in Ghana.

The District is benefitting from the intervention and during the period under review, a total of 3,321 students have been enrolled into the two (2) Senior High Schools in the District.

The table below provides the breakdown in respect of the two (2) SHS’s and the number of students enrolled.

TABLE 17 SHOWING NUMBER OF SCHOOLS AND NUMBER OF STUDENTS ENROLLED UNDER THE FSHSP IN THE DISTRICT

| S/N | NAME OF SCHOOL | ENROLMENT |  | TOTAL |
| --- | --- | --- | --- | --- |
|  |  | Male | Female |  |
| 1 | Kukuom Agric. SHS | 1115 | 976 | 2091 |
| 2 | Sankore SHS | 604 | 626 | 1230 |
|  | Total | 1,719 | 1,602 | 3,321 |
|  | PERCENTAGE | 52% | 48% | 100% |

Source: ASDA, DED, December, 2021

From figure 3. The FSHSP has higher percentage of males (52%) than females of 48%. This indicates that the total number of males enrolled in senior high schools are more that the total number of females enrolled in senior high schools in the district.

FIGURE 5. PERCENTAGE OF MALE AND FEMALE IN THE FSHSP

## 2.11 EVALUATION AND PARTICIPATORY MONITORING & EVALUATION

#### 2.11.1 EVALUATIONS CONDUCTED

Evaluation is the systematic and objective assessment of an on-going or completed project, programme or policy, its design, implementation and results. It determines the relevance and fulfilment of objectives, efficiency, effectiveness, impact and sustainability. It should provide information that is credible and useful, enabling incorporation of lessons learned into the decision-making process of both recipients and donors (IFRC, 2007). The Assembly therefore undertook an exercise during 2021 to evaluate some specific projects. The methods employed in the evaluation and the findings are tabulated below.

#### 2.5.2 PARTICIPATORY MONITORING & EVALUATION

Participatory Monitoring and Evaluation (PM&E) refers to the practice where all key stakeholders are directly involved in the M&E design and implementation process. For the 2021 under review, the District conducted PM&E using Interview questionnaires and Transect walk. The key stakeholders who participated in the PM&E through the stakeholders’ analysis included Traditional Authorities, Assembly Members, Unit Committee Members, Opinion Leaders, Contractors, Heads of Decentralised Department and Agencies, Political Parties (NPP and NDC), Civil Society Organisations, Religious Bodies, Financial Institutions, Artisans, Communities and Media. The detail of the conduct of the PM&E is presented in the table below;

TABLE 19 PARTICIPATORY M&E

| S/N | NAME OF PM&E TOOL | POLICY/PROGRAMME /PROJECT INVOLVED | CONSULTANT/RES OURCE PERSON INVOLVED | METHODOLOGY USED | FINDINGS/ISSUES | RECOMMENDATIONS |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Key informant Interviews | Construction of 20-unit market stores at Sankore Daily market | Trade and Industry Regional Rep, BAC District Officer | - One on one questionnaire administration on market folks. - Observations | - Unhygienic market environment - Poor market revenue mobilization - Poor storage facilities for goods and services - Pressure on existing facilities | - Construct a modernized lockable market facility |
| 2 | Interview Questionnaire | Improved hygiene and sanitation practices among households | Environmental Health and Sanitation Officer | - House to house visitations - One on one questionnaire administration | - Lack of waste bins in households - Inappropriate waste disposal among some households - Lack of proper drainage systems for liquid waste disposal especially in old settlements. - Lack of toilet facilities especially in clustered communities | - Intensify education and sensitization on good hygiene and sanitation practices. - Liaise with Zoomlion to provide standard bins to households - Educate house owners to include toilet facilities in their building plans and existing structures |
| 3 | Transect Walk | Inspection of demarcated area designated for the siting of 1D1F project. | Trade & Industry Regional Rep | - Walking tour in and around the proposed site | - Site close to the raw material base - Land use falls within approved spatial plan scheme - Land suitable for siting a factory - Area demarcated easily accessible - Need to compensate original occupants of proposed site | - Initiate processes to facilitate the building of the factory - Negotiate with the private investor to expedite actions - Compensate original occupants of proposed site to avoid future conflict |
| 4 | Outcome Mapping | Const. of 1No.3-unit Classroom Block with Office, Staff Common Room, 2-Seater KVIP and Supply of Furniture at Anwiam. | District Director of Education | - One on one community interactions - Observation | - School enrolment improved - Quality teaching and learning enhanced - Improved school infrastructure | - Ensure regular maintenance of facility - Establish ICT lab to compliment quality delivery in the area of Science and Technology. |

# CHAPTER THREE

# 3.0 THE WAY FORWARD

This chapter summarizes and concludes the 2021 Annual Progress Report by exhibiting the key issues addressed and those yet to be addressed as well as the recommendations for successful implementation of subsequent Annual Action Plans.

## 3.1.1 KEY ISSUES ADDRESSED

- Quarterly meetings of the DPCU and budget committee

- Timely submission of quarterly reports by Departments and Agencies

- Improved link between plan and budget

## 3.1.2 KEY ISSUES YET TO BE ADDRESSED

Some key issues yet to be addressed were;

- Ineffective collaboration between Assembly and Non-Governmental Organisations and other development partners

- Difficulty in accessing data from some departments and agencies.

- Poor records keeping among departments and units.

- Inadequate logistics for effective monitoring and evaluation

- Poor Basic Education Certificate Examination (BECE) performance

- Poor road conditions

- Broken down boreholes

- Low Internally Generated Fund (IGF)

- Inadequate potable water supply

- High unemployment among the youth

- Dilapidated classroom blocks

- Inadequate CHPS Compounds

- Open defecation

## 3.1.3 RECOMMENDATIONS

- Investment in the construction and rehabilitation of classroom blocks

- Investment in the construction and rehabilitation of health facilities

- Organisation of public education campaigns on the need to pay taxes eg. Property rate.

- Exploitation of other internally lucrative sources of funds aside the conventional sources.

- Improve the infrastructural and institutional capacity of sub-district structures to enhance their operations.

- Investment in the procurement of office facilities and equipment and capacity building to improve productivity levels of staff.

## 3.1.4 CONCLUSION

The ultimate goal of the District Medium Term Development Plan 2018-2021 is to achieve an improvement in socio-economic development through the continuous development of social and economic infrastructure and the development of human capital whilst enhancing good governance. The realisation of this goal requires the effective and efficient utilisation of available potentials and opportunities to the District whilst mitigating the impact of its constraints and challenges. In this light, it is imperative that, popular participation is encouraged to ensure ownership of the development process by the populace whilst promoting transparency and accountability.

ANNEX A

TABLE 20 LIST OF MONITORING TEAM

| S/N | NAME | DESIGNATION |
| --- | --- | --- |
|  | HON. FRANK ADUSE POKU | DISTRICT CHIEF EXECUTIVE |
|  | ASAMOAH DAMOAH | DISTRICT COORDINATING DIRECTOR |
|  | SABINA OBENG | DISTRICT PLANNING OFFICER |
|  | AGNES AMIHERE | DISTRICT EDUCATION DIRECTOR |
|  | THERESA KRAH | DISTRICT DIRECTOR OF HEALTH |
|  | MARK TACHIE | DISTRICT ENGINEER |
|  | ALIDU IBRAHIM | DISTRICT BUDGET ANALYST |
|  | SETH O. BOAMAH | DISTRICT FINANCE OFFICER |
|  | MOHAMMED YAKUBU | HUMAN RESOURCE MANAGER |
|  | MANASEH ALI | DISTRICT ENVIRONMENTAL HEALTH OFFICER |
|  | AKWASI AMOAKO | INTERNAL AUDITOR |
|  | SABI SENTI MICHAEL | DISTRICT AGRIC. DIRECTOR |
|  | ESTHER ANTWI | DISTRICT SOCIAL WELFARE & COMMUNITY DEVELOPMENT OFFICER |
|  | EMMANUEL MENSAH | DISTRICT PHYSICAL PLANNING OFFICER |
| STAKEHOLDERS (EXTERNAL) |  |  |
|  | HON. BOAKYE DANKWA | ASSEMBLY MEMBER, KUKUOM ABROMAM |
|  | HON. BENJAMIN YINKAH | ASSEMBLY MEMBER, KUKUOM ABROMAM |
|  | HON. MAXWELL D. HAYFORD | ASSEMBLY MEMBER, NOBERKAW |
|  | HON. JOSHUA ASANTE | ASSEMBLY MEMBER, ANWIAM |
|  | HON. ISHMAEL MOHAMMED | ASSEMBLY MEMBER, SANKORE NORTH |
|  | HON. ALHASSAN JOSEPH | ASSEMBLY MEMBER, ASAREKROM |
|  | HON. KONTO NICHOLAS AHI | ASSEMBLY MEMBER, ABUOM |
|  | HON. JUSTICE MANU | ASSEMBLY MEMBER, ASAWINSO ADWUMAM |
|  | HON. GIDEON ATAKORA AMANIAMPONG | ASSEMBLY MEMBER, KWAPONG NEW TOWN |
|  | JACKSON ACQUAH | OPINION LEADER, ASAREKROM |
|  | SAMUEL OFORI | OPINION LEADER, ADWUMAM |
|  | GEORGE OWUSU FORDJOUR | OPINION LEADER, KUKUOM |
|  | ALBERT TAWIAH | OPINION LEADER, SIISO |
|  | JOYCE AWUAH | OPINION LEADER, ASEMPANAYE |
|  | NANA | TRADITIONAL COUNCIL KUKUOM |
|  | BERTIE ASAMOAH | PRINCIPAL KWAPONG NTC |
|  | MRS DORITHY ANTWI | HEAD MISTRESS KUKUOM |
|  | NANA KOOFIE | TRADITIONAL COUNCIL SANKORE |
|  | NANA BONSU | MANAGING DTR WADADA AND SONS LTD |
|  | NANA YAW BANAHENE | CONTRACTOR |
|  | MR VICTOR | HEAD MASTER KUKUOM |
|  | SAMUEL ASARE | MANAGINGNDIRECTOR GREAT AGYEDUS VENTURES |
|  | NANA ABABIO FOKUO 1 | KWAPONG TRADITIONAL COUNCIL |
|  | NANA GYAMBIBI | ASREKROM TRADITIONAL COUNCIL |
|  | KWAKU ASAMOAH | HEAD MASTER ANWIAM |
|  | NYOURTOYIE RAPHEL | TEACHER ASEMPANEYE |
|  | NANA WIREKOWAA | SUB COMMIITTEE NAKETEY |
|  | DORMINIC TETTEH | HEAD MASTER NOBERKOW |

## NOTE:  The indicators with N/A denotes information NOT AVAILABLE.

NOTE: The expenditure item denoted OTHERS comprises other donor funds, specifically MAG and CIDA