ASUNAFO SOUTH DISTRICT ASSEMBLY 2022 ANNUAL ACTION PLAN
	Programme
	Sub-Programme
	Broad Activities
	Location
	Time Frame
	Cost
	Programme Status
	Implementing Inst./Department

	
	
	
	
	Q1
	Q2
	Q3
	Q4
	GOG
	IGF
	Others
	New
	On-going
	Lead
	Collaborating

	Promote Economic Development
	Local trade and industrial development
	Promote Business Development Services
	Kukuom
	
	
	
	
	
	
	67,120.00
	
	
	BAC
	DA, GDO

	
	
	Agricultural commodity processing development
	Noberkaw
	
	
	
	
	
	
	12,730.00
	
	
	BAC
	DA

	
	
	Institutional Capacity Building

	Kukuom
	
	
	
	
	
	
	11, 560.00
	
	
	BAC
	GEA, Reps

	
	Sub Total
	
	
	
	
	
	
	
	
	91,410.00
	
	
	
	

	
	Agricultural development
	  Purchase of Stationery for office use  

	Kukuom  

	
	
	
	
	
	
	1,000.00
	
	
	Dep't of Agric  
	Central Admin

	
	
	Purchase 20 wellington boot for twenty staff members  
	Kukuom
	
	
	
	
	
	
	1,000.00
	
	
	Dep't of Agric  
	Central Admin

	
	
	Collect weekly market data on commodity prices and movement from 2 market outlet by December 2024.  

	Kukuom Sankore, and Kwapong
	
	
	
	
	
	
	           2,160.00 

	
	
	Dep't of Agric  
	ASDA 


	
	
	Conduct survey on all waterbodies and facilitate the construction of mini dams to aid irrigation of crops 

	Kukuom, kwapong, sankore, Abuom zone 

	
	
	
	
	
	
	   120,000.00 

	
	
	  Dep't of Agric  
  Dep't of Agric  

	ASDA 


	
	
	  Conduct one Poultry and Livestock survey  
	  All Operational Areas  

	
	
	
	
	
	
	2,000.00
	
	
	  Dep't of Agric  

	ASDA

	
	
	  Conduct four (4) quarterly management meetings.  

	Kukuom
	
	
	
	
	
	
	1,080.00
	
	
	  Dep't of Agric  

	ASDA

	
	
	  Conduct four (4) quarterly Technical review meetings.  

	Kukuom
	
	
	
	
	
	
	3,000.00
	
	
	  Dep't of Agric  

	ASDA

	
	
	  Participate in one RELC Regional Planning session.  

	Goaso
	
	
	
	
	
	
	1,000.00
	
	
	  Dep't of Agric  

	ASDA

	
	
	  Organize one stakeholders meeting to establish District Agriculture Business Partnership programme  

	Kukuom
	
	
	
	
	
	
	1,000.00
	
	
	  Dep't of Agric  

	RADU,ASDA 


	
	
	  Attend three (3) technical review meetings at Regional level.  

	Goaso
	
	
	
	
	
	
	2,200.00
	
	
	  Dep't of Agric  

	  RADU  
ASDA

	
	
	  Organize one District farmers Day celebration    

	
	
	
	
	
	70,000.00
	
	
	
	
	  Dep't of Agric  

	ASDA TA,Assembly Members

	
	
	  Attend nine (9) staff training workshops at Regional level.  

	Goaso
	
	
	
	
	
	
	4,200.00
	
	
	  Dep't of Agric  

	  RADU, ASDA


	
	
	  Conduct monitoring and evaluation on all projects by DDA, DCD and other unit heads of the Assembly for all government flagship programmes.  

	all operational zones 

	
	
	
	
	
	
	4,000.00
	
	
	  Dep't of Agric  

	  DPCU, ASDA  


	
	
	  Conduct monitoring by DDA, DAOs, on AEAs' activities in the operational areas.  

	all operational zones 

	
	
	
	
	
	
	15,000.00
	
	
	Dep't of Agric  

	ASDA

	
	
	  Conduct four (4) quarterly inspections to agro-input shops  

	all operational zones 

	
	
	
	
	
	
	400.00
	
	
	Dep't of Agric  

	ASDA

	
	
	  Conduct field and home visits by AEAs.  

	All operational Areas of the district 

	
	
	
	
	
	
	15,000.00
	
	
	Dep't of Agric  

	ASDA

	
	
	  Organize three (3) zonal RELC meetings.  

	all 4 zones of the district 

	
	
	
	
	
	
	1,000.00
	
	
	Dep't of Agric  

	ASDA

	
	
	  Organize one District RELC meeting.  

	Kukuom
	
	
	
	
	
	
	5,000.00
	
	
	Dep't of Agric  

	  RADU, ASDA 


	
	
	Sensitize farmers and stakeholders on the menace and control of FAW

	All Operational Areas of the district 

	
	
	
	
	
	
	3,000.00
	
	
	Dep't of Agric  

	ASDA

	
	
	  Organize five training for farmers in communities on safe handling of agro chemicals  

	Kukuom, Noberkaw, Asufufuo, camp No1, Adomako, Yankye, Anwiam.  

	
	
	
	
	
	
	1,500.00
	
	
	Dep't of Agric  

	ASDA

	
	
	Organize one training for 20 women on mushroom production. 
	Kukuom
	
	
	
	
	
	
	3,000.00
	
	
	Dep't of Agric  

	ASDA, BAC, NBSSI

	
	
	Train one women FBO on " farming as a business" 
	kukuom 

	
	
	
	
	
	
	2,000.00
	
	
	Dep't of Agric  

	ASDA, BAC, NBSSI

	
	
	Train twenty (20) women in farming in Soap making 
	Dantano
	
	
	
	
	
	
	1,800.00
	
	
	Dep't of Agric  

	ASDA, BAC, NBSSI, SWCD

	
	
	  Organize three (3) trainings for 75 Livestock Farmers on Supplementary Feeding  

	Adomakokrom, Dantano, Siana 

	
	
	
	
	
	
	900.00
	
	
	Dep't of Agric  

	ASDA, BAC, NBSSI, SWCD

	
	
	  Organize three (3) trainings for 75 Livestock farmers on improved housing  
	Sankore, Abuom, Dantano 

	
	
	
	
	
	
	900.00
	
	
	Dep't of Agric  

	ASDA, BAC, NBSSI, SWCD

	
	
	  Sensitization and Vaccination of Livestock  
	All 4 zones of the district 

	
	
	
	
	
	
	10,000.00
	
	
	Dep't of Agric  

	ASDA

	
	
	  Train 120 farmers in two communities on postharvest management practices  

	Tanoso, Noberkaw 

	
	
	
	
	
	
	2,000.00
	
	
	Dep't of Agric  

	ASDA

	
	
	  Train thirty- five (35) agro dealers on PFJ modalities  
	Kukuom
	
	
	
	
	
	
	1,500.00
	
	
	Dep't of Agric  

	ASDA

	
	
	  Attend twenty-seven (27) Radio education and sensitization talk shows on Agriculture related issues.  
	all 4 zones of the district 

	
	
	
	
	
	
	2,000.00
	
	
	Dep't of Agric  

	Information centers 


	
	
	  Train two (2) FBOs on integrated soil fertility management (ISFM)  
	Kukuom
	
	
	
	
	
	
	1,500.00
	
	
	Dep't of Agric  

	  ASDA, RELC, SRI  


	
	
	  Establish two demonstrations on maize and rice on ISFM  

	Kukuom, Kokooso 

	
	
	
	
	
	
	2,300.00
	
	
	Dep't of Agric  

	  ASDA, RELC, SRI  


	
	
	  Establish two demonstrations on plantain sucker multiplication  
	Pesewkrom,  
Abuom
	
	
	
	
	
	
	2,000.00
	
	
	Dep't of Agric  

	  ASDA, RELC, SRI  


	
	
	  Establish one varietal demonstration on tomato  

	Tanoso 

	
	
	
	
	
	
	2,500.00
	
	
	Dep't of Agric  

	  ASDA, RELC, SRI  


	
	
	  Distribute 500 cockerels to farmers under RFJ  

	all 4 zones of the district  

	
	
	
	
	
	
	4,000.00
	
	
	Dep't of Agric  

	ASDA

	
	
	  Nurse and distribute 40,000 seedlings (oil palm, coconut,) to 800 farmers  
	All 4 zones of the district 

	
	
	
	
	
	
	140,000.00
	
	
	Dep't of Agric  

	ASDA

	
	
	  Facilitate the distribution of subsidized input to 40,000 farmers under PFJ   

	District Wide
	
	
	
	
	
	
	800,000.00
	
	
	Dep't of Agric  

	

	
	
	Procure 5,000 Coconut seedlings for 100 farmers under the Planting for Export and Rural Development (PERD) programme
	Districtwide
	
	
	
	
	50,000.00
	
	
	
	
	Dep’t of Agric.
	ASDA

	
	
	Train 30 women on farming as business
	Kukuom
	
	
	
	
	2,000.00
	
	
	
	
	GDO
	Dep’t of Agric.

	
	
	Youth in Agric Development (Palm Plantation)
	Yankye, Noberkaw
	
	
	
	
	150,000.00
	
	
	
	
	Dep't of Agric  

	DA,NBSSI, BAC 

	
	
	Agricultural investment
	District wide
	
	
	
	
	250,000.00
	
	
	
	
	Dep't of Agric  

	ASDA

	
	Sub Total
	
	
	
	
	
	
	195,600.00
	
	1,160,840.00
	
	
	
	

	Enhancement of the Management and Administration of the Assembly
	General Administration
	Strengthening of sub district structures
	Kukuom, Kwapong, Sankore, Asarekrom, Abuom and Kokooso
	
	
	
	
	120,000.00
	
	
	
	
	CA
	Other Department

	
	
	Convene 3no. General Assembly meetings 
	Kukuom
	
	
	
	
	
	
	25,000.00
	
	
	Cent Admin
	Other Depts

	
	
	Convene 3no. EXECO meetings 
	Kukuom
	
	
	
	
	
	
	5,000.00
	
	
	Cent Admin
	 

	
	
	Organise 3no. meetings of 5 statutory sub-committee 
	Kukuom
	
	
	
	
	
	
	25,000.00
	
	
	Cent Admin
	 Other depts

	
	
	Organise quarterly Audit committee meetings
	Kukuom
	
	
	
	
	
	
	
	
	
	Cent Admin
	Internal Audit Unit

	
	
	Organise national Independence Day celebration 
	Kukuom
	
	
	
	
	25,000.00
	
	
	
	
	Educ Dept
	Cent Admin

	
	
	Organise quarterly Budget C’ttee meetings 
	Kukuom
	
	
	
	
	
	
	10,000.00
	
	
	Budget Unit
	 

	
	
	Organize quarterly Entity Tender Committee meetings 
	Kukuom
	
	
	
	
	
	
	5,000.00
	
	
	Proc Unit
	Plg Unit

	
	
	Organize monthly Spatial Planning Committee meetings 
	Kukuom
	
	
	
	
	
	
	5,000.00
	
	
	PPD
	Plg Unit

	
	
	Organize monthly Technical sub-committee meetings 
	Kukuom
	
	
	
	
	
	
	5,000.00
	
	
	PPD
	Plg Unit

	
	
	Organise quarterly management and staff meetings 
	Kukuom
	
	
	
	
	
	
	20,000.00
	
	
	Cent Admin
	 

	
	
	Organise quarterly radio sensitisation programmes on the evils of corruption and the ethos of anti-corruption
	Kukuom
	
	
	
	
	4,000.00
	
	
	
	
	Cent Admin
	CHRAJ/NCCE

	
	
	Organise 1no. stakeholder’s engagement meeting with Council of churches and Islamic clerks on inclusion of anti-corruption sermons and teachings
	Kukuom
	
	
	
	
	4,000.00
	
	
	
	
	Cent Admin
	CHRAJ/NCCE

	
	
	Organize bi-Annual District LEAP Implementing Committee (DLIC) Meeting 
	Kukuom
	
	
	
	
	
	
	5,000.00
	
	
	SW&CD
	 

	
	
	Organize quarterly PRCC meeting 
	Kukuom
	
	
	
	
	
	
	8,000.00
	
	
	Cent Admin
	PM

	
	
	Hold quarterly DISEC meetings 
	Kukuom
	
	
	
	
	
	10,000.00
	
	
	
	Cent Admin
	 Security Agencies

	
	
	Servicing of 6no. vehicles
	
	
	
	
	
	
	20,000.00
	20,000.00
	
	
	WKS Dept
	 

	
	
	Procure office equipment for the Assembly
	Kukuom
	
	
	
	
	40,000.00
	40,000.00
	
	
	
	Proc Unit
	PLG Unit

	
	
	Procure office stationery
	Kukuom
	
	
	
	
	50,000.00
	
	
	
	
	Cent Admin
	 Procuement Unit

	
	
	Procure office equipment for 6no. Area Councils 
	Kukuom, Kwapong, Sankore, Asarekrom, Abuom, Kokooso
	
	
	
	
	30,000.00
	
	
	
	
	Proc. Unit
	Plg Unit

	
	
	Rehabilitate Staff bungalows
	Kukuom
	
	
	
	
	185,000.00
	
	
	
	
	Wks Dept
	Plg Unit/Proc Unit

	
	
	Support District Security Agencies (Police, Fire Service, Military, Immigration, BNI)
	Kukuom/Sankore
	
	
	
	
	25,000.00
	
	
	
	
	Cent Admin
	 

	
	
	Support to Good Governance institutions and agencies
	Kukuom
	
	
	
	
	30,000.00
	
	
	
	
	CA
	Other Department

	
	Sub Total
	
	
	
	
	
	
	587,867.00
	100,000.00
	153,000.00
	
	
	
	

	
	Finance and Revenue Mobilization
	Prepare and implement Revenue Improvement Action Plan


	Kukuom
	
	
	
	
	5,000.00
	
	
	
	
	Finance Dept.
	CA

	
	
	
Embark on monthly monitoring and supervision of revenue collectors
	District wide
	
	
	
	
	8,000.00
	
	
	
	
	Finance Dept.
	Planing Unit. HRD

	
	
	Embark on monthly radio revenue sensitization programme 
	Kukuom
	
	
	
	
	5,000.00
	
	
	
	
	Budget Unit
	Plg Unit,

	
	
	Embark on quarterly rotation of revenue collectors 
	District wide 
	
	
	
	
	
	1,000.00
	
	
	
	Finance Dept
	 HRD, Plg Unit

	
	
	Value properties in the District
	District wide
	
	
	
	
	5,000.00
	
	
	
	
	Central Admin
	Plg Unit/ Finance Dept

	
	
	Update Assembly’s revenue database
	Kukuom
	
	
	
	
	2,000.00
	
	
	
	
	Budget Unit
	  Plg Unit

	
	
	
Printing and serving of demand notice to property owners and business operators
	District Wide
	
	
	
	
	5,000.00
	
	
	
	
	Finance Dept
	

	
	Sub Total
	
	
	
	
	
	
	54,000.00
	1,000.00
	
	
	
	
	

	
	Planning, Budgeting and Coordination
	Preparation of composite Annual Action Plan and budget
	Kukuom
	
	
	
	
	10,000.00
	
	
	
	
	Planning Unit
	Other Department

	
	
	Organize 2No Town Hall Meetings.
	Kukuom, Kwapong and Sankore
	
	
	
	
	20,000.00
	
	
	
	
	Planning Unit
	Media, TA, Community members

	
	
	Organize DPCU and budget committee meetings
	Kukuom
	
	
	
	
	16,000.00
	
	
	
	
	Planning Unit
	Other Department

	
	
	Monitoring, Evaluation and Reporting on Projects
	Kukuom
	
	
	
	
	25,000.00
	
	
	
	
	Planning Unit
	Other Department

	
	
	Support for MP’s activities and programmes
	Districtwide
	
	
	
	
	
	
	30,000.00
	
	
	MP
	Other Departments

	
	Sub Total
	
	
	
	
	
	
	71,000.00
	
	30,000.00
	
	
	
	

	
	Human Resource Management
	Organize 1no capacity building workshop on Records Management

	Kukuom
	
	
	
	
	
	
	1,687.5
	
	
	HRM
	ASDA,

	
	
	Organize 1no capacity building workshop for Assembly Members on Local Governance Act, Act 936, 2016
	Kukuom
	
	
	
	
	
	
	5,000.00
	
	
	HRD
	Plg Unit

	
	
	Organize 1no.  refresher workshop on Performance Management System for LGS staff
	Kukuom
	
	
	
	
	
	
	2,500.00
	
	
	Cent Admin
	

	
	
	Organize 1no. training on service protocols for LGS staff
	Kukuom
	
	
	
	
	
	
	2,500.00
	
	
	HRD
	PLG Unit

	
	
	Organize 1no. Training workshop on Strategic HR Polices for non-HR Staff
	Kukuom
	
	
	
	
	
	
	2,000.00
	
	
	HRD
	CHRAJ

	
	
	Organize training on leave entitlement and preparation towards retirement for public servants
	Kukuom
	
	
	
	
	
	
	2,500.00
	
	
	HRD
	 

	
	
	Organise 1no. refresher workshop for newly staff employed and National Service Personnel
	Kukuom
	
	
	
	
	
	
	2,000.00
	
	
	HRD
	 

	
	
	Salary and Payroll Management
	Kukuom
	
	
	
	
	
	
	1,500.00
	
	
	HRD
	Finance Dept. ASDA

	
	Sub Total
	
	
	
	
	
	
	
	
	19,687.50
	
	
	
	

	Infrastructure delivery and Humana Settlement Management
	Health Care Infrastructure
	Completion of CHPS Compounds
	 Asibrem, Wejakrom, Pafo Nkwata, Asarekrom

	
	
	
	
	522,364.09
	
	
	
	
	DWD
	DA, DHD

	
	
	Renovation and Rehabilitation of Health facilities
	District Wide
	
	
	
	
	100,000.00
	
	
	
	
	DWD
	DHD,plg unit

	
	Sub Total
	
	
	
	
	
	
	1,327,364.09
	10,000.00
	
	
	
	
	

	
	Educational Infrastructure
	Completion of 1No. 3 Unit Classroom Blocks
	Noberkaw
	
	
	
	
	41,685.60
	
	
	
	
	DED
	DWD, TA, Assembly Member

	
	
	Completion of 1No. 3 Unit Classroom Block with 4-seater KVIP, Urinal and Supply of Furniture
	Abuom D/A JHS
	
	
	
	
	173,700.49
	
	
	
	
	DED
	DWD, TA, Assembly Member

	
	
	Completion of 1No. 3 Unit Classroom Block
	Nnanyinaanse-Kwapong NTC
	
	
	
	
	57,741.26
	
	
	
	
	DED
	DWD, TA, Assembly Member

	
	
	Completion of 1No. 3-Unit Classroom Block with office, staff common room, 3-Seater KVIP and Supply of Furniture
	Kukuom SDA school
	
	
	
	
	65,550.21
	
	
	
	
	DED
	DWD, TA, Assembly Member

	
	
	Construction of 1No. 3-Unit Classroom Block with Office, Staff room, Supply of Furniture & 3-Seater KVIP
	Kukuom Model School
	
	
	
	
	248,734.07
	
	
	
	
	DED
	DWD, TA, Assembly Member

	
	
	Construction of Computer Laboratory
	Kwapong
	
	
	
	
	100,000.00
	
	
	
	
	DED
	Works

	
	
	Construction of 1No. 3-Unit Classroom Block with Office, Staff room, Supply of Furniture & 3-Seater KVIP
	Noberkow Methodist JHS
	
	
	
	
	280,000.00
	
	
	
	
	DED
	DWD, TA, Assembly Member

	
	
	Supply of 276No. dual desk to selected schools
	Kokooso, Nkawie, Asawinso, Adwumam, Asante Nkae, Agyeikrom, Kwapong, Asibrem, Agyarekrom, Nnayinanse, Motopenso

	
	
	
	
	110,485.00
	
	
	
	
	District Assembly
	DED

	
	
	Renovation of Education infrastructure
	KamirekromDantano, Kokooso, Agyeikrom, Naketey J.H.S, Ntonso

	
	
	
	
	320,000.00
	
	
	
	
	GES
	DWD, TA, Assembly Member

	
	
	Construction toilet facilities in schools
	Afodowa School, Duruwaakrom School, Domeabra School, Mfrekrom School
	
	
	
	
	220,000.00
	
	
	
	
	GES
	DWD, TA, Assembly Member

	
	Sub Total
	
	
	
	
	
	
	4,349,235.57
	
	
	
	
	
	

	
	Energy, Telecommunication, Transportation  and Road Infrastructure
	Reshaping/Spot Improvement/Rehabilitation of 60 km feeder roads
	Districtwide
	
	
	
	
	135,000.00
	
	
	
	
	DWD
	ASDA,

	
	
	Facilitate the development of Telecommunication Network Infrastructure
	Kokooso, Beposo, Anum, Afodowa, Mfrekrom, 
	
	
	
	
	50,000.00
	
	
	
	
	Tel. Comm. Network Operators,DW
	ASDA

	
	
	Completion of Sankore Lorry Terminal
	Sankore
	
	
	
	
	50,000.00
	
	100,000.00
	
	
	DA
	DWD

	
	
	Redevelopment of Kukuom Lorry park
	Kukuom
	
	
	
	
	
	50,000.00
	150,000.00
	
	
	DA
	DWD

	
	
	Support for road safety 
	District wide
	
	
	
	
	
	
	5,000.00
	
	
	DA, 
	Ambulance Service, Road Safety Department, GPS,GFS,MTTD, GPRTU

	
	
	Extension of electricity  
	Kukuom, Kwapong, Asibrem, Sankore, Abuom

	
	
	
	
	620,000.00
	
	
	
	
	DWD
	ASDA Assembly Members, NEDCO

	
	
	Procurement of Canoe/Boat and life Jackets to aid crossing on the Tano River
	Asawinso
	
	
	
	
	
	
	6,200.00
	
	
	DWD
	Assembly Member, TA

	
	
	Maintenance of street lights
	Districtwide
	
	
	
	
	120,000.00
	
	
	
	
	DWD
	ASDA,

	
	Sub Total
	
	
	
	
	
	
	975,000.00
	50,000.00
	261,200.00
	
	
	
	

	
	Human Settlement Management
	Prepare District Spatial Development framework
	District Wide
	
	
	
	
	24,000.00
	
	
	
	
	DA
	PPD, RCC, Trad. Authorities, Depts, 
LUSPA

	
	
	Continuation of Street Naming and Property Addressing System
	
	
	
	
	
	10,000.00
	
	
	
	
	DA
	MLGRD, T&CPD,  VRA, GNFS,
Traditional Authorities, Private developers

	
	
	Preparation of structure plans for the district
	
	
	
	
	
	50,000.00
	
	
	
	
	DA
	PPD, RCC, Trad. Authorities, Depts, 
LUSPA

	
	
	Preparation of Local plans for the district
	
	
	
	
	
	200,000.00
	
	
	
	
	

DA
	PPD, RCC, Trad. Authorities, Depts,
LUSPA

	
	
	Practice Site and Services before lands are demarcated and allocated for development 
	
	
	
	
	
	
20,000.00
	
	
	
	
	

PPD
	DA, RCC, Trad. Authorities, Depts,
LUSPA

	
	
	Strengthen the physical planning and Parks and Gardens Unit with the requisite logistics to perform
	
	
	
	
	
	
21,000.00
	
	
	
	
	

DA
	PPD, RCC, Trad. Authorities, Depts,
LUSPA

	
	
	Train staff and Spatial Planning Committee members on new models and Legislation enacted on Physical Development
	
	
	
	
	
	
100,000.00
	
	
	
	
	


DA
	PPD, RCC, MLGRD, LGS, Depts, 
LUSPA

	
	
	Create public awareness on greening of human settlements
	
	
	
	
	
	25,000.00
	
	
	
	
	
 DA
	PPD, Trad. Authorities, Depts, Developers

	
	Sub Total
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	
	Completion of 1 No. 20 -Unit Storey for Sankore Daily Market
	Sankore
	
	
	
	
	42,000.00
	
	
	
	
	DWD
	TA, Assembly members

	
	Sub Total
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Water infrastructure
	Drilling and construction of boreholes, LMS and pipe systems
	Districtwide
	
	
	
	
	520,000.00
	
	
	
	
	DWD
	TA, Assembly members

	
	
	Construction of 1No. Police Station and Supply of Water
	Abuom
	
	
	
	
	184,314.40
	
	
	
	
	DA
	GPS

	
	Sub Total
	
	
	
	
	
	
	754,314.40
	
	
	
	
	
	

	
	Office and Staff Accommodation
	Construction of Junior Staff Quarters
	Kukuom
	
	
	
	
	420,000.00
	
	
	
	
	DWD
	TA, Assembly members

	
	
	Completion of 1No. Staff Bungalows
	Kukuom
	
	
	
	
	525,000.00
	
	
	
	
	DWD
	DA

	
	
	Development of the forecourt of the District Assembly’s Office Block
	Kukuom
	
	
	
	
	220,000.00
	
	
	
	
	DWD
	TA, Assembly members

	
	
	Construction of Sankore District Police Headquarters
	Sankore
	
	
	
	
	350,000.00
	
	
	
	
	DA
	GPS

	
	
	Completion of the ground floor of 3-storey Administration Block
	Kukuom
	
	
	
	
	420,000.00
	
	
	
	
	DWD
	TA, Assembly members

	
	Sub Total
	
	
	
	
	
	
	1,935,000.00
	
	
	
	
	
	

	Improve Social Services Delivery
	Quality Education Delivery
	Provision of Teaching and learning materials
	Districtwide
	
	
	
	
	25,000.00
	
	
	
	
	GES
	DA, NADef

	
	
	  Purchase of utilities (Electricity, Water, Communication, Internet)  
	Kukuom
	
	
	
	
	25,000.00
	
	
	
	
	  DDE  
	  ASDA, TSMA  

	
	
	Support to teaching and learning delivery
	Districtwide
	
	
	
	
	10,000.00
	
	
	
	
	GES
	ASDA, NADef,

	
	
	Supervision and inspection of education delivery
	Districtwide
	
	
	
	
	10,000.00
	
	
	
	
	GES
	

	
	
	Payroll Audit/inspection of promotions
	Kukuom
	
	
	
	
	5,000.00
	
	
	
	
	GES
	

	
	
	Capacity Building
	Kukuom
	
	
	
	
	20,000.00
	
	
	
	
	GES
	ASDA

	
	
	Organise my First Day at school for KG & Prim. 1
	District Wide
	
	
	
	
	3,000.00
	
	
	
	
	Cent Admin
	Educ Dept

	
	
	Conduct School census
	Districtwide
	
	
	
	
	1,000.00
	
	
	
	
	GES
	

	
	
	Sensitization of parents and teachers on the learning needs of PWDs
	District wide
	
	
	
	
	1,000.00
	
	
	
	
	GES
	DSWCD

	
	
	Strengthening school management system
	Districtwide
	
	
	
	
	10,000.00
	
	
	
	
	GES
	MoE, PTA

	
	Sub Total
	
	
	
	
	
	
	110,000.00
	
	
	
	
	
	

	
	Quality Healthcare delivery
	Provide Clinical services
	Districtwide
	
	
	
	
	15,000.00
	
	
	
	
	DHD
	DA

	
	
	  Purchase of utilities (Electricity, Water, Communication, Internet)  
	Kukuom
	
	
	
	
	30,000.00
	
	
	
	
	  DDH  
	  ASDA,  

	
	
	Promote  health education and outreach immunization and family planning services
	Districtwide
	
	
	
	
	20,000.00
	
	
	
	
	DHD
	DA

	
	
	Capacity building for staff
	Kukuom
	
	
	
	
	10,000.00
	
	
	
	
	DHD
	GHS

	
	
	Intensify disease surveillance at all levels
	Districtwide
	
	
	
	
	10,000.00
	
	
	
	
	DHD
	GHS

	
	
	Monitoring and supervision of health delivery points
	Districtwide
	
	
	
	
	20,000.00
	
	
	
	
	GHS
	DA

	
	
	Provide sponsorship packages  for  staff
	
	
	
	
	
	
	
	100,000.00
	
	
	GHS
	DA

	
	
	Establishment of nutrition rehabilitation centre to manage malnourished cases
	Kukuom
	
	
	
	
	50,000.00
	
	
	
	
	GHS
	DA

	
	Sub Total
	
	
	
	
	
	
	155,000.00
	
	100,000.00
	
	
	
	

	
	Support to Vulnerable and Excluded



































































	Child Rights Promotion and Protection
	Districtwide
	
	
	
	
	15,000.00
	
	
	
	
	DSWCD
	ASDA

	
	
	Provide financial assistance to 10 vulnerable children 
	
	
	
	
	
	10,000.00
	
	
	
	
	DSWCD
	ASDA

	
	
	Organise the celebration of World Child Labour Day
	
	
	
	
	
	5,000.00
	
	
	
	
	DSWCD
	ASDA

	
	
	Provide financial assistance to 300 PWDs 
	
	
	
	
	
	
	
	
	
	
	DSWCD
	ASDA

	
	
	Procure 20 wheel chairs for PWDs
	
	
	
	
	
	50,000.00
	
	
	
	
	DSWCD
	ASDA

	
	
	Resolve 100 child related cases to promote and protect the rights of the child
	
	
	
	
	
	10,000.00
	
	
	
	
	DSWCD
	ASDA

	
	
	Organise 10no. community sensitization on child marriage, teenage pregnancy (child protection) in 10 communities
	Kukuom,Noberkaw, Kwapong, Sankore, Asarekrom, Abuom, Kokooso, Siiso, Nyankye, Mfrekrom
	
	
	
	
	10,000.00
	
	
	
	
	GDO
	SWCD, GES, GHS

	
	
	Organize 1no. capacity building for 60 CCPC members 
	Kukuom
	
	
	
	
	6,000.00
	
	
	
	
	DSWCD
	ASDA

	
	
	Organize quarterly child protection review meetings
	kukuom
	
	
	
	
	6,000.00
	
	
	
	
	DSWCD
	ASDA

	
	
	Organize 1no. capacity building for MLIC members on case management, strengthening of referrals and linkage between social systems
	Kukuom
	
	
	
	
	5,000.00
	
	
	
	
	DSWCD
	ASDA

	
	
	Procure and distribute 600 PPEs for PWDs
	District wide
	
	
	
	
	20,000.00
	
	
	
	
	DSWCD
	ASDA

	
	
	Family Tribunal /Juvenile Court Sittings
	Kukuom
	
	
	
	
	10,000.00
	
	
	
	
	SWCD
	ASDA

	
	
	Registration, Supervision/Inspection of Early Childhood Development Centers.
	Kukuom
	
	
	
	
	5,000.00
	
	
	
	
	SWCD
	GES, E.H

	
	
	Implementation of LEAP
	The 382 LEAP implementing benefitiaries
	
	
	
	
	2,000.00
	
	
	
	
	SWCD
	Police, GES, TA Opinion Leaders,

	
	
	Sensitization of the general public on gender issues
	District wide
	
	
	
	
	5,000.00
	
	
	
	
	GDO 
	SWCD, 

	
	
	Education and Sensitization on teenage pregnancy 
	Kukuom, Kwapog, Noberkaw, Sankore
	
	
	
	
	5,000.00
	
	
	
	
	GDO 
	SWCD, GES, GHS

	
	
	Education and support for menstrual hygiene management
	New Asawinso JHS, Sankore SHS, Kukuom Agric SHS, Kukuom Girls Model School, Kukuom SDA Kukuom Islamic JHS, Noberkaw JHS
	
	
	
	
	10,000.00
	
	
	
	
	GDO
	SWCD, GES, GHS

	
	
	Organize Training for the youth in pastry making
	Noberkaw 
Kukuom, Anwiam, Ntonso, Beposo No.2
	
	
	
	
	20,000.00
	
	
	
	
	GDO
	BAC, Local Banks

	
	
	Education of youth  on the effect of drug abuse .
	Sankore SHS, Kukuom Agric SHS, Kukuom, Kwapong
	
	
	
	
	4,000.00
	
	
	
	
	GDO
	SWCD, GES, GHS

	
	
	Casework with Families
	Districtwide
	
	
	
	
	5,000.00
	
	
	
	
	SWCD
	DOVVSU, CHRAJ, TA, Opinion Leaders, Judicial Service

	
	Sub Total
	
	
	
	
	
	
	203,000.00
	
	
	
	
	
	

	
	Water and Sanitation Delivery
	Training of water vendors
	Districtwide
	
	
	
	
	10,000.00
	
	
	
	
	Planning Unit
	DWD, WVG

	
	
	Implementation of SHEP
	Districtwide
	
	
	
	
	10,000.00
	
	
	
	
	GES
	ASDA, GHS

	
	
	Completion of Slauter House
	Kukuom
	
	
	
	
	20,000.00
	
	
	
	
	DWD
	DEHU,

	
	
	Screening of food vendors, butcher meat sellers, drinking bar operators and School Feeding Operators
	Districtwide
	
	
	
	
	10,000.00
	
	
	
	
	DEHU
	ASDA

	
	Sub Total
	
	
	
	
	
	
	50,000.00
	
	
	
	
	
	

	
	Sports and Youth Development
	Construction of Multi-purpose Town Park
	Kukuom
	
	
	
	
	
	
	100,000.00
	
	
	DA
	NYA, T.A

	
	
	Apprenticeship/vocational training for the youth (Soap Making, Bee Keeping, Fish Farming)
	Sankore
Anum, Noberkaw, Yankye, Kwapong, Kokooso Agyeikrom Kofibenkrom, Ntonso, Beposo No. 1

	
	
	
	
	20,000.00
	
	
	
	
	DGO
	DAD, YEA,BAC,SWCD

	
	
	Promote skill and career guidance training for the youth
	Districtwide
	
	
	
	
	10,000.00
	
	
	
	
	NYA
	DA

	
	
	Provide vocational training and support for 200 youths
	Districtwide
	
	
	
	
	
	100,000.00
	
	
	
	RM
	DA

	
	Sub Total
	
	
	
	
	
	
	30,000.00
	100,000.00
	100,000.00
	
	
	
	

	Improve Culture and Tourism
	Heritage Development
	Research, Documentation and Development of Heritage Sites Festivals and Sacred Grooves for Tourism.

	Kukuom, Tanoso – Dantano, Sankore,
Asufufuo
	
	
	
	
	10,000.00
	
	10,000.00
	
	
	CNC
	Physical planning & MMDES,
Traditional
 Authorities

	
	
	Creation of craft shops near these attraction sites.
	Kukuom,  Sankore
	
	
	
	
	10,000.00
	
	
	
	
	CNC
	DA

	
	
	Departmental cultural orientation on various Customary/ Traditional Rites and courtesies.
	Kukuom
	
	
	
	
	5,000.00
	
	
	
	
	CNC
	DA

	
	
	Radio Cultural info and education on Traditional/
Cultural Values and Ethics
	Districtwide
	
	
	
	
	5,000.00
	
	
	
	
	CNC
	

	
	
	Selection and beautification of spots with murals, sculptures, paintings
	Kwapong, Kukuom, Abuom, Sankore
	
	
	
	
	15,000.00
	
	
	
	
	CNC
	Physical planning, Parks & Gardens

	
	Sub Total
	
	
	
	
	
	
	45,000.00
	
	
	
	
	
	

	Improve Environmental and Sanitation Management
	Disaster Prevention and Environmental Management
	Sensitizations on natural disasters
	Kukuom, Noberkaw, Kwapong, Sankore and Abuom
	
	
	
	
	5,000.00
	
	
	
	
	NADMO
	DA, Assembly Members, EPA, Fire Service, TA

	
	
	Desilting of Drains
	Sankore
Kukuom
	
	
	
	
	120,000.00
	
	
	
	
	DEH
	ASDA,

	
	
	Orientation of food vendor and school feeding contractors on good nutritional practices
	District wide
	
	
	
	
	5,000.00
	
	
	
	
	
DA
	
DEHU, school feeding desk officer

	
	
	Regular monitoring and inspection of markets, households and slaughter houses
	District Wide
	
	
	
	
	20,000.00
	
	
	
	
	DEHU
	

	
	
	Organize regular Education and sensitization on good hygiene practices
	District Wide
	
	
	
	
	10,000.00
	
	
	
	
	DEHU
	PLg unit, DHD

	
	
	Regular Fumigation and clearing of public spaces
	District Wide
	
	
	
	
	20,000.00
	
	
	
	
	DEHO
	

	
	
	Maintenance and rehabilitation of Markets
	District Wide
	
	
	
	
	20,000.00
	
	
	
	
	DA
	Works 

	
	
	Procurement of logistics for cleaning and General services
	
Kukuom
	
	
	
	
	
	
	
	
	
	
DA
	
DEHU

	
	
	Evacuation, maintenance and levelling of refuse heaps/sites
	District Wide
	
	
	
	
	15,000.00
	
	
	
	
	DEH
	ASDA, Zoomlion Gh.

	
	
	Daily collection and disposal of refuse (SIP)
	Districtwide
	
	
	
	
	10,000.00
	
	
	
	
	DEH
	ASDA, Zoomlion Gh.

	
	
	Procurement of skip containers
	Kukuom
	
	
	
	
	20,000.00
	5,000.00
	
	
	
	DEH
	ASDA

	
	
	Arrest of stray animals
	Kukuom, Kwapong, Sankore
	
	
	
	
	
	5,000.00
	
	
	
	DEH
	Zoomlion Ghana

	
	Sub Total
	
	
	
	
	
	
	245,000.00
	10,000.00
	
	
	
	
	

	
	Natural Resource Conservation and Climate Change
	Support and implement tree planting activities
	Districtwide
	
	
	
	
	30,000.00
	
	
	
	
	FC
	ASDA, NADMO

	
	
	Implementation of the Ghana Productive Safety Project (GPSNP)
	Naketey
	
	
	
	
	
	
	
	
	
	DA
	MLGRD, World Bank, Consultants

	
	
	Supply improved and early maturing seedlings
	Districtwide
	
	
	
	
	20,000.00
	
	10,000.00
	
	
	FC
	DDA, ASDA

	Emergency Planning and Preparedness
	COVID-19 Interventions
	Procure PPEs
	Districtwide
	
	
	
	
	
	25,000.00
	
	
	
	DA
	DHD

	
	
	Education and sensitization of COVID-19 safety protocols
	Districtwide
	
	
	
	
	10,000.00
	
	
	
	
	DHD
	DA

	
	
	Monitoring and Supervision of public gatherings
	Districtwide
	
	
	
	
	5,000.00
	
	
	
	
	DA
	DHD

	
	Sub Total
	
	
	
	
	
	
	65,000.00
	25,000.00
	10,000.00
	
	
	
	

	
TOTAL
	12,159,381.06
	296,000.00
	1,926,137.50
	
	
	
	14,261,518.56
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