ASUNAFO SOUTH DISTRICT ASSEMBLY 2022 ANNUAL ACTION PLAN

| Programme | Sub-Programme | Broad Activities | Location | Time Frame |  |  |  | Cost |  |  | Programme Status |  | Implementing Inst./Department |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 | GOG | IGF | Others | New | On-going | Lead | Collaborating |
| Promote Economic Development | Local trade and industrial development | Promote Business Development Services | Kukuom |  |  |  |  |  |  | 67,120.00 |  |  | BAC | DA, GDO |
|  |  | Agricultural commodity processing development | Noberkaw |  |  |  |  |  |  | 12,730.00 |  |  | BAC | DA |
|  |  | Institutional Capacity Building | Kukuom |  |  |  |  |  |  | 11, 560.00 |  |  | BAC | GEA, Reps |
|  | Sub Total |  |  |  |  |  |  |  |  | 91,410.00 |  |  |  |  |
|  | Agricultural development | Purchase of Stationery for office use | Kukuom |  |  |  |  |  |  | 1,000.00 |  |  | Dep't of Agric | Central Admin |
|  |  | Purchase 20 wellington boot for twenty staff members | Kukuom |  |  |  |  |  |  | 1,000.00 |  |  | Dep't of Agric | Central Admin |
|  |  | Collect weekly market data on commodity prices and movement from 2 market outlet by December 2024. | Kukuom Sankore, and Kwapong |  |  |  |  |  |  | 2,160.00 |  |  | Dep't of Agric | ASDA |
|  |  | Conduct survey on all waterbodies and facilitate the construction of mini dams to aid irrigation of crops | Kukuom, kwapong, sankore, Abuom zone |  |  |  |  |  |  | 120,000.00 |  |  | Dep't of Agric Dep't of Agric | ASDA |
|  |  | Conduct one Poultry and Livestock survey | All Operational Areas |  |  |  |  |  |  | 2,000.00 |  |  | Dep't of Agric | ASDA |
|  |  | Conduct four (4) quarterly management meetings. | Kukuom |  |  |  |  |  |  | 1,080.00 |  |  | Dep't of Agric | ASDA |
|  |  | Conduct four (4) quarterly Technical review meetings. | Kukuom |  |  |  |  |  |  | 3,000.00 |  |  | Dep't of Agric | ASDA |
|  |  | Participate in one RELC Regional Planning session. | Goaso |  |  |  |  |  |  | 1,000.00 |  |  | Dep't of Agric | ASDA |
|  |  | Organize one stakeholders meeting to establish District Agriculture Business Partnership programme | Kukuom |  |  |  |  |  |  | 1,000.00 |  |  | Dep't of Agric | RADU,ASDA |
|  |  | Attend three (3) technical review meetings at Regional level. | Goaso |  |  |  |  |  |  | 2,200.00 |  |  | Dep't of Agric | RADU ASDA |
|  |  | Organize one District farmers Day celebration |  |  |  |  |  | 70,000.00 |  |  |  |  | Dep't of Agric | ASDA TA,Assembly Members |
|  |  | Attend nine (9) staff training workshops at Regional level. | Goaso |  |  |  |  |  |  | 4,200.00 |  |  | Dep't of Agric | RADU, ASDA |
|  |  | Conduct monitoring and evaluation on all projects by DDA, DCD and other unit heads of the Assembly for all government flagship programmes. | all operational zones |  |  |  |  |  |  | 4,000.00 |  |  | Dep't of Agric | DPCU, ASDA |
|  |  | Conduct monitoring by DDA, DAOs, on AEAs' activities in the operational areas. | all operational zones |  |  |  |  |  |  | 15,000.00 |  |  | Dep't of Agric | ASDA |
|  |  | Conduct four (4) quarterly inspections to agro-input shops | all operational zones |  |  |  |  |  |  | 400.00 |  |  | Dep't of Agric | ASDA |
|  |  | Conduct field and home visits by AEAs. | All operational Areas of the district |  |  |  |  |  |  | 15,000.00 |  |  | Dep't of Agric | ASDA |
|  |  | Organize three (3) zonal RELC meetings. | all 4 zones of the district |  |  |  |  |  |  | 1,000.00 |  |  | Dep't of Agric | ASDA |
|  |  | Organize one District RELC meeting. | Kukuom |  |  |  |  |  |  | 5,000.00 |  |  | Dep't of Agric | RADU, ASDA |
|  |  | Sensitize farmers and stakeholders on the menace and control of FAW | All Operational Areas of the district |  |  |  |  |  |  | 3,000.00 |  |  | Dep't of Agric | ASDA |
|  |  | Organize five training for farmers in communities on safe handling of agro chemicals | Kukuom, Noberkaw, Asufufuo, camp No1, Adomako, Yankye, Anwiam. |  |  |  |  |  |  | 1,500.00 |  |  | Dep't of Agric | ASDA |
|  |  | Organize one training for 20 women on mushroom production. | Kukuom |  |  |  |  |  |  | 3,000.00 |  |  | Dep't of Agric | ASDA, BAC, NBSSI |
|  |  | Train one women FBO on " farming as a business" | kukuom |  |  |  |  |  |  | 2,000.00 |  |  | Dep't of Agric | ASDA, BAC, NBSSI |
|  |  | Train twenty (20) women in farming in Soap making | Dantano |  |  |  |  |  |  | 1,800.00 |  |  | Dep't of Agric | ASDA, BAC, NBSSI, SWCD |
|  |  | Organize three (3) trainings for 75 Livestock Farmers on Supplementary Feeding | Adomakokrom, Dantano, Siana |  |  |  |  |  |  | 900.00 |  |  | Dep't of Agric | ASDA, BAC, NBSSI, SWCD |
|  |  | Organize three (3) trainings for 75 Livestock farmers on improved housing | Sankore, Abuom, Dantano |  |  |  |  |  |  | 900.00 |  |  | Dep't of Agric | ASDA, BAC, NBSSI, SWCD |
|  |  | Sensitization and Vaccination of Livestock | All 4 zones of the district |  |  |  |  |  |  | 10,000.00 |  |  | Dep't of Agric | ASDA |
|  |  | Train 120 farmers in two communities on postharvest management practices | Tanoso, Noberkaw |  |  |  |  |  |  | 2,000.00 |  |  | Dep't of Agric | ASDA |
|  |  | Train thirty- five (35) agro dealers on PFJ modalities | Kukuom |  |  |  |  |  |  | 1,500.00 |  |  | Dep't of Agric | ASDA |
|  |  | Attend twenty-seven (27) Radio education and sensitization talk shows on Agriculture related issues. | all 4 zones of the district |  |  |  |  |  |  | 2,000.00 |  |  | Dep't of Agric | Information centers |
|  |  | Train two (2) FBOs on integrated soil fertility management (ISFM) | Kukuom |  |  |  |  |  |  | 1,500.00 |  |  | Dep't of Agric | ASDA, RELC, SRI |
|  |  | Establish two demonstrations on maize and rice on ISFM | Kukuom, Kokooso |  |  |  |  |  |  | 2,300.00 |  |  | Dep't of Agric | ASDA, RELC, SRI |
|  |  | Establish two demonstrations on plantain sucker multiplication | Pesewkrom, Abuom |  |  |  |  |  |  | 2,000.00 |  |  | Dep't of Agric | ASDA, RELC, SRI |
|  |  | Establish one varietal demonstration on tomato | Tanoso |  |  |  |  |  |  | 2,500.00 |  |  | Dep't of Agric | ASDA, RELC, SRI |
|  |  | Distribute 500 cockerels to farmers under RFJ | all 4 zones of the district |  |  |  |  |  |  | 4,000.00 |  |  | Dep't of Agric | ASDA |
|  |  | Nurse and distribute 40,000 seedlings (oil palm, coconut,) to 800 farmers | All 4 zones of the district |  |  |  |  |  |  | 140,000.00 |  |  | Dep't of Agric | ASDA |
|  |  | Facilitate the distribution of subsidized input to 40,000 farmers under PFJ | District Wide |  |  |  |  |  |  | 800,000.00 |  |  | Dep't of Agric |  |
|  |  | Procure 5,000 Coconut seedlings for 100 farmers under the Planting for Export and Rural Development (PERD) programme | Districtwide |  |  |  |  | 50,000.00 |  |  |  |  | Dep’t of Agric. | ASDA |
|  |  | Train 30 women on farming as business | Kukuom |  |  |  |  | 2,000.00 |  |  |  |  | GDO | Dep’t of Agric. |
|  |  | Youth in Agric Development (Palm Plantation) | Yankye, Noberkaw |  |  |  |  | 150,000.00 |  |  |  |  | Dep't of Agric | DA,NBSSI, BAC |
|  |  | Agricultural investment | District wide |  |  |  |  | 250,000.00 |  |  |  |  | Dep't of Agric | ASDA |
|  | Sub Total |  |  |  |  |  |  | 195,600.00 |  | 1,160,840.00 |  |  |  |  |
| Enhancement of the Management and Administration of the Assembly | General Administration | Strengthening of sub district structures | Kukuom, Kwapong, Sankore, Asarekrom, Abuom and Kokooso |  |  |  |  | 120,000.00 |  |  |  |  | CA | Other Department |
|  |  | Convene 3no. General Assembly meetings | Kukuom |  |  |  |  |  |  | 25,000.00 |  |  | Cent Admin | Other Depts |
|  |  | Convene 3no. EXECO meetings | Kukuom |  |  |  |  |  |  | 5,000.00 |  |  | Cent Admin |  |
|  |  | Organise 3no. meetings of 5 statutory sub-committee | Kukuom |  |  |  |  |  |  | 25,000.00 |  |  | Cent Admin | Other depts |
|  |  | Organise quarterly Audit committee meetings | Kukuom |  |  |  |  |  |  |  |  |  | Cent Admin | Internal Audit Unit |
|  |  | Organise national Independence Day celebration | Kukuom |  |  |  |  | 25,000.00 |  |  |  |  | Educ Dept | Cent Admin |
|  |  | Organise quarterly Budget C’ttee meetings | Kukuom |  |  |  |  |  |  | 10,000.00 |  |  | Budget Unit |  |
|  |  | Organize quarterly Entity Tender Committee meetings | Kukuom |  |  |  |  |  |  | 5,000.00 |  |  | Proc Unit | Plg Unit |
|  |  | Organize monthly Spatial Planning Committee meetings | Kukuom |  |  |  |  |  |  | 5,000.00 |  |  | PPD | Plg Unit |
|  |  | Organize monthly Technical sub-committee meetings | Kukuom |  |  |  |  |  |  | 5,000.00 |  |  | PPD | Plg Unit |
|  |  | Organise quarterly management and staff meetings | Kukuom |  |  |  |  |  |  | 20,000.00 |  |  | Cent Admin |  |
|  |  | Organise quarterly radio sensitisation programmes on the evils of corruption and the ethos of anti-corruption | Kukuom |  |  |  |  | 4,000.00 |  |  |  |  | Cent Admin | CHRAJ/NCCE |
|  |  | Organise 1no. stakeholder’s engagement meeting with Council of churches and Islamic clerks on inclusion of anti-corruption sermons and teachings | Kukuom |  |  |  |  | 4,000.00 |  |  |  |  | Cent Admin | CHRAJ/NCCE |
|  |  | Organize bi-Annual District LEAP Implementing Committee (DLIC) Meeting | Kukuom |  |  |  |  |  |  | 5,000.00 |  |  | SW&CD |  |
|  |  | Organize quarterly PRCC meeting | Kukuom |  |  |  |  |  |  | 8,000.00 |  |  | Cent Admin | PM |
|  |  | Hold quarterly DISEC meetings | Kukuom |  |  |  |  |  | 10,000.00 |  |  |  | Cent Admin | Security Agencies |
|  |  | Servicing of 6no. vehicles |  |  |  |  |  |  | 20,000.00 | 20,000.00 |  |  | WKS Dept |  |
|  |  | Procure office equipment for the Assembly | Kukuom |  |  |  |  | 40,000.00 | 40,000.00 |  |  |  | Proc Unit | PLG Unit |
|  |  | Procure office stationery | Kukuom |  |  |  |  | 50,000.00 |  |  |  |  | Cent Admin | Procuement Unit |
|  |  | Procure office equipment for 6no. Area Councils | Kukuom, Kwapong, Sankore, Asarekrom, Abuom, Kokooso |  |  |  |  | 30,000.00 |  |  |  |  | Proc. Unit | Plg Unit |
|  |  | Rehabilitate Staff bungalows | Kukuom |  |  |  |  | 185,000.00 |  |  |  |  | Wks Dept | Plg Unit/Proc Unit |
|  |  | Support District Security Agencies (Police, Fire Service, Military, Immigration, BNI) | Kukuom/Sankore |  |  |  |  | 25,000.00 |  |  |  |  | Cent Admin |  |
|  |  | Support to Good Governance institutions and agencies | Kukuom |  |  |  |  | 30,000.00 |  |  |  |  | CA | Other Department |
|  | Sub Total |  |  |  |  |  |  | 587,867.00 | 100,000.00 | 153,000.00 |  |  |  |  |
|  | Finance and Revenue Mobilization | Prepare and implement Revenue Improvement Action Plan | Kukuom |  |  |  |  | 5,000.00 |  |  |  |  | Finance Dept. | CA |
|  |  | Embark on monthly monitoring and supervision of revenue collectors | District wide |  |  |  |  | 8,000.00 |  |  |  |  | Finance Dept. | Planing Unit. HRD |
|  |  | Embark on monthly radio revenue sensitization programme | Kukuom |  |  |  |  | 5,000.00 |  |  |  |  | Budget Unit | Plg Unit, |
|  |  | Embark on quarterly rotation of revenue collectors | District wide |  |  |  |  |  | 1,000.00 |  |  |  | Finance Dept | HRD, Plg Unit |
|  |  | Value properties in the District | District wide |  |  |  |  | 5,000.00 |  |  |  |  | Central Admin | Plg Unit/ Finance Dept |
|  |  | Update Assembly’s revenue database | Kukuom |  |  |  |  | 2,000.00 |  |  |  |  | Budget Unit | Plg Unit |
|  |  | Printing and serving of demand notice to property owners and business operators | District Wide |  |  |  |  | 5,000.00 |  |  |  |  | Finance Dept |  |
|  | Sub Total |  |  |  |  |  |  | 54,000.00 | 1,000.00 |  |  |  |  |  |
|  | Planning, Budgeting and Coordination | Preparation of composite Annual Action Plan and budget | Kukuom |  |  |  |  | 10,000.00 |  |  |  |  | Planning Unit | Other Department |
|  |  | Organize 2No Town Hall Meetings. | Kukuom, Kwapong and Sankore |  |  |  |  | 20,000.00 |  |  |  |  | Planning Unit | Media, TA, Community members |
|  |  | Organize DPCU and budget committee meetings | Kukuom |  |  |  |  | 16,000.00 |  |  |  |  | Planning Unit | Other Department |
|  |  | Monitoring, Evaluation and Reporting on Projects | Kukuom |  |  |  |  | 25,000.00 |  |  |  |  | Planning Unit | Other Department |
|  |  | Support for MP’s activities and programmes | Districtwide |  |  |  |  |  |  | 30,000.00 |  |  | MP | Other Departments |
|  | Sub Total |  |  |  |  |  |  | 71,000.00 |  | 30,000.00 |  |  |  |  |
|  | Human Resource Management | Organize 1no capacity building workshop on Records Management | Kukuom |  |  |  |  |  |  | 1,687.5 |  |  | HRM | ASDA, |
|  |  | Organize 1no capacity building workshop for Assembly Members on Local Governance Act, Act 936, 2016 | Kukuom |  |  |  |  |  |  | 5,000.00 |  |  | HRD | Plg Unit |
|  |  | Organize 1no. refresher workshop on Performance Management System for LGS staff | Kukuom |  |  |  |  |  |  | 2,500.00 |  |  | Cent Admin |  |
|  |  | Organize 1no. training on service protocols for LGS staff | Kukuom |  |  |  |  |  |  | 2,500.00 |  |  | HRD | PLG Unit |
|  |  | Organize 1no. Training workshop on Strategic HR Polices for non-HR Staff | Kukuom |  |  |  |  |  |  | 2,000.00 |  |  | HRD | CHRAJ |
|  |  | Organize training on leave entitlement and preparation towards retirement for public servants | Kukuom |  |  |  |  |  |  | 2,500.00 |  |  | HRD |  |
|  |  | Organise 1no. refresher workshop for newly staff employed and National Service Personnel | Kukuom |  |  |  |  |  |  | 2,000.00 |  |  | HRD |  |
|  |  | Salary and Payroll Management | Kukuom |  |  |  |  |  |  | 1,500.00 |  |  | HRD | Finance Dept. ASDA |
|  | Sub Total |  |  |  |  |  |  |  |  | 19,687.50 |  |  |  |  |
| Infrastructure delivery and Humana Settlement Management | Health Care Infrastructure | Completion of CHPS Compounds | Asibrem, Wejakrom, Pafo Nkwata, Asarekrom |  |  |  |  | 522,364.09 |  |  |  |  | DWD | DA, DHD |
|  |  | Renovation and Rehabilitation of Health facilities | District Wide |  |  |  |  | 100,000.00 |  |  |  |  | DWD | DHD,plg unit |
|  | Sub Total |  |  |  |  |  |  | 1,327,364.09 | 10,000.00 |  |  |  |  |  |
|  | Educational Infrastructure | Completion of 1No. 3 Unit Classroom Blocks | Noberkaw |  |  |  |  | 41,685.60 |  |  |  |  | DED | DWD, TA, Assembly Member |
|  |  | Completion of 1No. 3 Unit Classroom Block with 4-seater KVIP, Urinal and Supply of Furniture | Abuom D/A JHS |  |  |  |  | 173,700.49 |  |  |  |  | DED | DWD, TA, Assembly Member |
|  |  | Completion of 1No. 3 Unit Classroom Block | Nnanyinaanse-Kwapong NTC |  |  |  |  | 57,741.26 |  |  |  |  | DED | DWD, TA, Assembly Member |
|  |  | Completion of 1No. 3-Unit Classroom Block with office, staff common room, 3-Seater KVIP and Supply of Furniture | Kukuom SDA school |  |  |  |  | 65,550.21 |  |  |  |  | DED | DWD, TA, Assembly Member |
|  |  | Construction of 1No. 3-Unit Classroom Block with Office, Staff room, Supply of Furniture & 3-Seater KVIP | Kukuom Model School |  |  |  |  | 248,734.07 |  |  |  |  | DED | DWD, TA, Assembly Member |
|  |  | Construction of Computer Laboratory | Kwapong |  |  |  |  | 100,000.00 |  |  |  |  | DED | Works |
|  |  | Construction of 1No. 3-Unit Classroom Block with Office, Staff room, Supply of Furniture & 3-Seater KVIP | Noberkow Methodist JHS |  |  |  |  | 280,000.00 |  |  |  |  | DED | DWD, TA, Assembly Member |
|  |  | Supply of 276No. dual desk to selected schools | Kokooso, Nkawie, Asawinso, Adwumam, Asante Nkae, Agyeikrom, Kwapong, Asibrem, Agyarekrom, Nnayinanse, Motopenso |  |  |  |  | 110,485.00 |  |  |  |  | District Assembly | DED |
|  |  | Renovation of Education infrastructure | KamirekromDantano, Kokooso, Agyeikrom, Naketey J.H.S, Ntonso |  |  |  |  | 320,000.00 |  |  |  |  | GES | DWD, TA, Assembly Member |
|  |  | Construction toilet facilities in schools | Afodowa School, Duruwaakrom School, Domeabra School, Mfrekrom School |  |  |  |  | 220,000.00 |  |  |  |  | GES | DWD, TA, Assembly Member |
|  | Sub Total |  |  |  |  |  |  | 4,349,235.57 |  |  |  |  |  |  |
|  | Energy, Telecommunication, Transportation and Road Infrastructure | Reshaping/Spot Improvement/Rehabilitation of 60 km feeder roads | Districtwide |  |  |  |  | 135,000.00 |  |  |  |  | DWD | ASDA, |
|  |  | Facilitate the development of Telecommunication Network Infrastructure | Kokooso, Beposo, Anum, Afodowa, Mfrekrom, |  |  |  |  | 50,000.00 |  |  |  |  | Tel. Comm. Network Operators,DW | ASDA |
|  |  | Completion of Sankore Lorry Terminal | Sankore |  |  |  |  | 50,000.00 |  | 100,000.00 |  |  | DA | DWD |
|  |  | Redevelopment of Kukuom Lorry park | Kukuom |  |  |  |  |  | 50,000.00 | 150,000.00 |  |  | DA | DWD |
|  |  | Support for road safety | District wide |  |  |  |  |  |  | 5,000.00 |  |  | DA, | Ambulance Service, Road Safety Department, GPS,GFS,MTTD, GPRTU |
|  |  | Extension of electricity | Kukuom, Kwapong, Asibrem, Sankore, Abuom |  |  |  |  | 620,000.00 |  |  |  |  | DWD | ASDA Assembly Members, NEDCO |
|  |  | Procurement of Canoe/Boat and life Jackets to aid crossing on the Tano River | Asawinso |  |  |  |  |  |  | 6,200.00 |  |  | DWD | Assembly Member, TA |
|  |  | Maintenance of street lights | Districtwide |  |  |  |  | 120,000.00 |  |  |  |  | DWD | ASDA, |
|  | Sub Total |  |  |  |  |  |  | 975,000.00 | 50,000.00 | 261,200.00 |  |  |  |  |
|  | Human Settlement Management | Prepare District Spatial Development framework | District Wide |  |  |  |  | 24,000.00 |  |  |  |  | DA | PPD, RCC, Trad. Authorities, Depts, LUSPA |
|  |  | Continuation of Street Naming and Property Addressing System |  |  |  |  |  | 10,000.00 |  |  |  |  | DA | MLGRD, T&CPD, VRA, GNFS, Traditional Authorities, Private developers |
|  |  | Preparation of structure plans for the district |  |  |  |  |  | 50,000.00 |  |  |  |  | DA | PPD, RCC, Trad. Authorities, Depts, LUSPA |
|  |  | Preparation of Local plans for the district |  |  |  |  |  | 200,000.00 |  |  |  |  | DA | PPD, RCC, Trad. Authorities, Depts, LUSPA |
|  |  | Practice Site and Services before lands are demarcated and allocated for development |  |  |  |  |  | 20,000.00 |  |  |  |  | PPD | DA, RCC, Trad. Authorities, Depts, LUSPA |
|  |  | Strengthen the physical planning and Parks and Gardens Unit with the requisite logistics to perform |  |  |  |  |  | 21,000.00 |  |  |  |  | DA | PPD, RCC, Trad. Authorities, Depts, LUSPA |
|  |  | Train staff and Spatial Planning Committee members on new models and Legislation enacted on Physical Development |  |  |  |  |  | 100,000.00 |  |  |  |  | DA | PPD, RCC, MLGRD, LGS, Depts, LUSPA |
|  |  | Create public awareness on greening of human settlements |  |  |  |  |  | 25,000.00 |  |  |  |  | DA | PPD, Trad. Authorities, Depts, Developers |
|  | Sub Total |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Completion of 1 No. 20 -Unit Storey for Sankore Daily Market | Sankore |  |  |  |  | 42,000.00 |  |  |  |  | DWD | TA, Assembly members |
|  | Sub Total |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Water infrastructure | Drilling and construction of boreholes, LMS and pipe systems | Districtwide |  |  |  |  | 520,000.00 |  |  |  |  | DWD | TA, Assembly members |
|  |  | Construction of 1No. Police Station and Supply of Water | Abuom |  |  |  |  | 184,314.40 |  |  |  |  | DA | GPS |
|  | Sub Total |  |  |  |  |  |  | 754,314.40 |  |  |  |  |  |  |
|  | Office and Staff Accommodation | Construction of Junior Staff Quarters | Kukuom |  |  |  |  | 420,000.00 |  |  |  |  | DWD | TA, Assembly members |
|  |  | Completion of 1No. Staff Bungalows | Kukuom |  |  |  |  | 525,000.00 |  |  |  |  | DWD | DA |
|  |  | Development of the forecourt of the District Assembly’s Office Block | Kukuom |  |  |  |  | 220,000.00 |  |  |  |  | DWD | TA, Assembly members |
|  |  | Construction of Sankore District Police Headquarters | Sankore |  |  |  |  | 350,000.00 |  |  |  |  | DA | GPS |
|  |  | Completion of the ground floor of 3-storey Administration Block | Kukuom |  |  |  |  | 420,000.00 |  |  |  |  | DWD | TA, Assembly members |
|  | Sub Total |  |  |  |  |  |  | 1,935,000.00 |  |  |  |  |  |  |
| Improve Social Services Delivery | Quality Education Delivery | Provision of Teaching and learning materials | Districtwide |  |  |  |  | 25,000.00 |  |  |  |  | GES | DA, NADef |
|  |  | Purchase of utilities (Electricity, Water, Communication, Internet) | Kukuom |  |  |  |  | 25,000.00 |  |  |  |  | DDE | ASDA, TSMA |
|  |  | Support to teaching and learning delivery | Districtwide |  |  |  |  | 10,000.00 |  |  |  |  | GES | ASDA, NADef, |
|  |  | Supervision and inspection of education delivery | Districtwide |  |  |  |  | 10,000.00 |  |  |  |  | GES |  |
|  |  | Payroll Audit/inspection of promotions | Kukuom |  |  |  |  | 5,000.00 |  |  |  |  | GES |  |
|  |  | Capacity Building | Kukuom |  |  |  |  | 20,000.00 |  |  |  |  | GES | ASDA |
|  |  | Organise my First Day at school for KG & Prim. 1 | District Wide |  |  |  |  | 3,000.00 |  |  |  |  | Cent Admin | Educ Dept |
|  |  | Conduct School census | Districtwide |  |  |  |  | 1,000.00 |  |  |  |  | GES |  |
|  |  | Sensitization of parents and teachers on the learning needs of PWDs | District wide |  |  |  |  | 1,000.00 |  |  |  |  | GES | DSWCD |
|  |  | Strengthening school management system | Districtwide |  |  |  |  | 10,000.00 |  |  |  |  | GES | MoE, PTA |
|  | Sub Total |  |  |  |  |  |  | 110,000.00 |  |  |  |  |  |  |
|  | Quality Healthcare delivery | Provide Clinical services | Districtwide |  |  |  |  | 15,000.00 |  |  |  |  | DHD | DA |
|  |  | Purchase of utilities (Electricity, Water, Communication, Internet) | Kukuom |  |  |  |  | 30,000.00 |  |  |  |  | DDH | ASDA, |
|  |  | Promote health education and outreach immunization and family planning services | Districtwide |  |  |  |  | 20,000.00 |  |  |  |  | DHD | DA |
|  |  | Capacity building for staff | Kukuom |  |  |  |  | 10,000.00 |  |  |  |  | DHD | GHS |
|  |  | Intensify disease surveillance at all levels | Districtwide |  |  |  |  | 10,000.00 |  |  |  |  | DHD | GHS |
|  |  | Monitoring and supervision of health delivery points | Districtwide |  |  |  |  | 20,000.00 |  |  |  |  | GHS | DA |
|  |  | Provide sponsorship packages for staff |  |  |  |  |  |  |  | 100,000.00 |  |  | GHS | DA |
|  |  | Establishment of nutrition rehabilitation centre to manage malnourished cases | Kukuom |  |  |  |  | 50,000.00 |  |  |  |  | GHS | DA |
|  | Sub Total |  |  |  |  |  |  | 155,000.00 |  | 100,000.00 |  |  |  |  |
|  | Support to Vulnerable and Excluded | Child Rights Promotion and Protection | Districtwide |  |  |  |  | 15,000.00 |  |  |  |  | DSWCD | ASDA |
|  |  | Provide financial assistance to 10 vulnerable children |  |  |  |  |  | 10,000.00 |  |  |  |  | DSWCD | ASDA |
|  |  | Organise the celebration of World Child Labour Day |  |  |  |  |  | 5,000.00 |  |  |  |  | DSWCD | ASDA |
|  |  | Provide financial assistance to 300 PWDs |  |  |  |  |  |  |  |  |  |  | DSWCD | ASDA |
|  |  | Procure 20 wheel chairs for PWDs |  |  |  |  |  | 50,000.00 |  |  |  |  | DSWCD | ASDA |
|  |  | Resolve 100 child related cases to promote and protect the rights of the child |  |  |  |  |  | 10,000.00 |  |  |  |  | DSWCD | ASDA |
|  |  | Organise 10no. community sensitization on child marriage, teenage pregnancy (child protection) in 10 communities | Kukuom,Noberkaw, Kwapong, Sankore, Asarekrom, Abuom, Kokooso, Siiso, Nyankye, Mfrekrom |  |  |  |  | 10,000.00 |  |  |  |  | GDO | SWCD, GES, GHS |
|  |  | Organize 1no. capacity building for 60 CCPC members | Kukuom |  |  |  |  | 6,000.00 |  |  |  |  | DSWCD | ASDA |
|  |  | Organize quarterly child protection review meetings | kukuom |  |  |  |  | 6,000.00 |  |  |  |  | DSWCD | ASDA |
|  |  | Organize 1no. capacity building for MLIC members on case management, strengthening of referrals and linkage between social systems | Kukuom |  |  |  |  | 5,000.00 |  |  |  |  | DSWCD | ASDA |
|  |  | Procure and distribute 600 PPEs for PWDs | District wide |  |  |  |  | 20,000.00 |  |  |  |  | DSWCD | ASDA |
|  |  | Family Tribunal /Juvenile Court Sittings | Kukuom |  |  |  |  | 10,000.00 |  |  |  |  | SWCD | ASDA |
|  |  | Registration, Supervision/Inspection of Early Childhood Development Centers. | Kukuom |  |  |  |  | 5,000.00 |  |  |  |  | SWCD | GES, E.H |
|  |  | Implementation of LEAP | The 382 LEAP implementing benefitiaries |  |  |  |  | 2,000.00 |  |  |  |  | SWCD | Police, GES, TA Opinion Leaders, |
|  |  | Sensitization of the general public on gender issues | District wide |  |  |  |  | 5,000.00 |  |  |  |  | GDO | SWCD, |
|  |  | Education and Sensitization on teenage pregnancy | Kukuom, Kwapog, Noberkaw, Sankore |  |  |  |  | 5,000.00 |  |  |  |  | GDO | SWCD, GES, GHS |
|  |  | Education and support for menstrual hygiene management | New Asawinso JHS, Sankore SHS, Kukuom Agric SHS, Kukuom Girls Model School, Kukuom SDA Kukuom Islamic JHS, Noberkaw JHS |  |  |  |  | 10,000.00 |  |  |  |  | GDO | SWCD, GES, GHS |
|  |  | Organize Training for the youth in pastry making | Noberkaw Kukuom, Anwiam, Ntonso, Beposo No.2 |  |  |  |  | 20,000.00 |  |  |  |  | GDO | BAC, Local Banks |
|  |  | Education of youth on the effect of drug abuse . | Sankore SHS, Kukuom Agric SHS, Kukuom, Kwapong |  |  |  |  | 4,000.00 |  |  |  |  | GDO | SWCD, GES, GHS |
|  |  | Casework with Families | Districtwide |  |  |  |  | 5,000.00 |  |  |  |  | SWCD | DOVVSU, CHRAJ, TA, Opinion Leaders, Judicial Service |
|  | Sub Total |  |  |  |  |  |  | 203,000.00 |  |  |  |  |  |  |
|  | Water and Sanitation Delivery | Training of water vendors | Districtwide |  |  |  |  | 10,000.00 |  |  |  |  | Planning Unit | DWD, WVG |
|  |  | Implementation of SHEP | Districtwide |  |  |  |  | 10,000.00 |  |  |  |  | GES | ASDA, GHS |
|  |  | Completion of Slauter House | Kukuom |  |  |  |  | 20,000.00 |  |  |  |  | DWD | DEHU, |
|  |  | Screening of food vendors, butcher meat sellers, drinking bar operators and School Feeding Operators | Districtwide |  |  |  |  | 10,000.00 |  |  |  |  | DEHU | ASDA |
|  | Sub Total |  |  |  |  |  |  | 50,000.00 |  |  |  |  |  |  |
|  | Sports and Youth Development | Construction of Multi-purpose Town Park | Kukuom |  |  |  |  |  |  | 100,000.00 |  |  | DA | NYA, T.A |
|  |  | Apprenticeship/vocational training for the youth (Soap Making, Bee Keeping, Fish Farming) | Sankore Anum, Noberkaw, Yankye, Kwapong, Kokooso Agyeikrom Kofibenkrom, Ntonso, Beposo No. 1 |  |  |  |  | 20,000.00 |  |  |  |  | DGO | DAD, YEA,BAC,SWCD |
|  |  | Promote skill and career guidance training for the youth | Districtwide |  |  |  |  | 10,000.00 |  |  |  |  | NYA | DA |
|  |  | Provide vocational training and support for 200 youths | Districtwide |  |  |  |  |  | 100,000.00 |  |  |  | RM | DA |
|  | Sub Total |  |  |  |  |  |  | 30,000.00 | 100,000.00 | 100,000.00 |  |  |  |  |
| Improve Culture and Tourism | Heritage Development | Research, Documentation and Development of Heritage Sites Festivals and Sacred Grooves for Tourism. | Kukuom, Tanoso – Dantano, Sankore, Asufufuo |  |  |  |  | 10,000.00 |  | 10,000.00 |  |  | CNC | Physical planning & MMDES, Traditional Authorities |
|  |  | Creation of craft shops near these attraction sites. | Kukuom, Sankore |  |  |  |  | 10,000.00 |  |  |  |  | CNC | DA |
|  |  | Departmental cultural orientation on various Customary/ Traditional Rites and courtesies. | Kukuom |  |  |  |  | 5,000.00 |  |  |  |  | CNC | DA |
|  |  | Radio Cultural info and education on Traditional/ Cultural Values and Ethics | Districtwide |  |  |  |  | 5,000.00 |  |  |  |  | CNC |  |
|  |  | Selection and beautification of spots with murals, sculptures, paintings | Kwapong, Kukuom, Abuom, Sankore |  |  |  |  | 15,000.00 |  |  |  |  | CNC | Physical planning, Parks & Gardens |
|  | Sub Total |  |  |  |  |  |  | 45,000.00 |  |  |  |  |  |  |
| Improve Environmental and Sanitation Management | Disaster Prevention and Environmental Management | Sensitizations on natural disasters | Kukuom, Noberkaw, Kwapong, Sankore and Abuom |  |  |  |  | 5,000.00 |  |  |  |  | NADMO | DA, Assembly Members, EPA, Fire Service, TA |
|  |  | Desilting of Drains | Sankore Kukuom |  |  |  |  | 120,000.00 |  |  |  |  | DEH | ASDA, |
|  |  | Orientation of food vendor and school feeding contractors on good nutritional practices | District wide |  |  |  |  | 5,000.00 |  |  |  |  | DA | DEHU, school feeding desk officer |
|  |  | Regular monitoring and inspection of markets, households and slaughter houses | District Wide |  |  |  |  | 20,000.00 |  |  |  |  | DEHU |  |
|  |  | Organize regular Education and sensitization on good hygiene practices | District Wide |  |  |  |  | 10,000.00 |  |  |  |  | DEHU | PLg unit, DHD |
|  |  | Regular Fumigation and clearing of public spaces | District Wide |  |  |  |  | 20,000.00 |  |  |  |  | DEHO |  |
|  |  | Maintenance and rehabilitation of Markets | District Wide |  |  |  |  | 20,000.00 |  |  |  |  | DA | Works |
|  |  | Procurement of logistics for cleaning and General services | Kukuom |  |  |  |  |  |  |  |  |  | DA | DEHU |
|  |  | Evacuation, maintenance and levelling of refuse heaps/sites | District Wide |  |  |  |  | 15,000.00 |  |  |  |  | DEH | ASDA, Zoomlion Gh. |
|  |  | Daily collection and disposal of refuse (SIP) | Districtwide |  |  |  |  | 10,000.00 |  |  |  |  | DEH | ASDA, Zoomlion Gh. |
|  |  | Procurement of skip containers | Kukuom |  |  |  |  | 20,000.00 | 5,000.00 |  |  |  | DEH | ASDA |
|  |  | Arrest of stray animals | Kukuom, Kwapong, Sankore |  |  |  |  |  | 5,000.00 |  |  |  | DEH | Zoomlion Ghana |
|  | Sub Total |  |  |  |  |  |  | 245,000.00 | 10,000.00 |  |  |  |  |  |
|  | Natural Resource Conservation and Climate Change | Support and implement tree planting activities | Districtwide |  |  |  |  | 30,000.00 |  |  |  |  | FC | ASDA, NADMO |
|  |  | Implementation of the Ghana Productive Safety Project (GPSNP) | Naketey |  |  |  |  |  |  |  |  |  | DA | MLGRD, World Bank, Consultants |
|  |  | Supply improved and early maturing seedlings | Districtwide |  |  |  |  | 20,000.00 |  | 10,000.00 |  |  | FC | DDA, ASDA |
| Emergency Planning and Preparedness | COVID-19 Interventions | Procure PPEs | Districtwide |  |  |  |  |  | 25,000.00 |  |  |  | DA | DHD |
|  |  | Education and sensitization of COVID-19 safety protocols | Districtwide |  |  |  |  | 10,000.00 |  |  |  |  | DHD | DA |
|  |  | Monitoring and Supervision of public gatherings | Districtwide |  |  |  |  | 5,000.00 |  |  |  |  | DA | DHD |
|  | Sub Total |  |  |  |  |  |  | 65,000.00 | 25,000.00 | 10,000.00 |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  | 12,159,381.06 | 296,000.00 | 1,926,137.50 |  |  |  | 14,261,518.56 |