REPUBLIC OF GHANA

COMPOSITE BUDGET

FOR 2021-2024

PROGRAMME BASED BUDGET ESTIMATES

FOR 2021

ASUNAFO SOUTH DISTRICT ASSEMBLY

Table of Contents

PART A: STRATEGIC OVERVIEW	3

1.	ESTABLISHMENT OF THE DISTRICT	3

2.	POPULATION STRUCTURE	3

3.	DISTRICT ECONOMY	3

4.	VISION OF THE DISTRICT ASSEMBLY	7

5.	MISSION STATEMENT OF THE DISTRICT ASSEMBLY	7

6.	KEY ACHIEVEMENTS IN 2020	8

7.	REVENUE AND EXPENDITURE PERFORMANCE	9

8.	ASUNAFO SOUTH’S ADOPTED POLICY OBJECTIVES FOR 2021 LINK TO SUSTAINABLE DEVELOPMENT GOALS (SDGS)	11

9.	GOAL	11

10.	CORE FUNCTIONS	11

11.	POLICY OUTCOME INDICATORS AND TARGETS	13

12.	REVENUE MOBILIZATION STRATEGIES FOR KEY REVENUE SOURCES IN 2021	14

PART B: BUDGET PROGRAMME SUMMARY	15

PROGRAMME 1: MANAGEMENT AND ADMINISTRATION	15

PROGRAMME 2: INFRASTRUCTURE DELIVERY AND MANAGEMENT	26

PROGRAMME 3: SOCIAL SERVICES DELIVERY	32

PROGRAMME 4: ECONOMIC DEVELOPMENT	46

PROGRAMME 5: ENVIRONMENTAL AND SANITATION MANAGEMENT	53

PART C: FINANCIAL INFORMATION	56

# PART A: STRATEGIC OVERVIEW

INTRODUCTION

- ESTABLISHMENT OF THE DISTRICT

The Asunafo South District is one of the 6 (6) District/Municipal Assemblies in the Ahafo Region of the Republic of Ghana. The Legislative Instrument 1773 in line with government’s objective of deepening decentralization established the district in November 2004. The district capital is sited at Kukuom.

- POPULATION STRUCTURE

According to the 2010 Population Census of Ghana, the population of the district is 95,580. Given an annual growth rate of 2.6% per annum, the figure currently is estimated at 117,449 using geometric growth method.

The district’s current population growth rate of 2.6% is higher than that of Regional rate of 2.5% but lower than the national rate of 2.7%. Kukuom, the district capital has the largest population of 8,742. Only Kukuom and Sankore have population above 5000 where more facilities and service are located. All other settlements have their population below 5000. This shows that the district is rural in nature with scattered settlements. The males form about 50.3% of the estimated total population of the district. This is in line with the regional figures, but deviates from the national figures where females constitute about 51% of the population. The total land size of the district is 3737 km2 with 268.53 km2 covered by forest reserves. This area forms about 3.1% of the total regional land area of Ahafo.

- DISTRICT ECONOMY

The economy of Asunafo South District is made up of agriculture, industry, commerce and the service sectors. Agriculture is the predominant economic activity. However, this is done largely at the subsistence level except cocoa, which is primarily for export. The industrial sector is made up of few agro-processing facilities, while the commercial and the service sectors consist of trading in manufactured goods, foodstuffs and the rendering of services like hairdressing, transportation and other footloose businesses. About 61.1% of the labour force is employed in the agricultural sector, 8.4% in industry with the commercial and service sector absorbing 11.7%. The number of people employed in the agricultural sector gives an indication of the rural nature of the district. This also implies that any intervention in the agricultural sector stands to benefit majority of the people. The agricultural sector thus deserves a lot of attention.

AGRICULTURE

Agriculture in the district is still at the rudimentary stage relying basically on hoes, cutlasses and rainfall. Shifting cultivation, bush burning and bush fallowing are the common farming practices used by farmers. Farmlands are mostly acquired through share cropping (Abunu/Abusa). This forms about 16.4% of acquisition of farmlands in the district. The other forms of land acquisition are leasehold (10.5%), freehold/outright purchase (13.2), while over half (58.8) of farmlands in the district are in family land. Farm sizes are small. Averagely, farm sizes ranges from 1.5 - 2 acres for food crops and five acres for cocoa.

MARKET CENTRE

Commodity flow analysis is intended to establish the commercial or economic interactions within the Asunafo South District and between those outside in terms of the nature of goods and direction of flow to and from the three main periodic markets of Kukuom, Sankore and Kwapong. Goods involved are classified into agricultural and industrial.

Within the district, Kukuom, Sankore and Kwapong still serve as major periodic markets. Agricultural produce are conveyed from all places and settlements within the district to these market centers. These are made up mainly of foodstuffs such as plantain, cassava, cocoyam, yam, maize, okro, pepper etc. Conversely, endogenous outflows consisting of industrial goods move from the periodic markets especially from the Sankore market to all nooks and crannies of the district.

On the other hand, exogenous inflows into the district are made up mainly of industrial goods. Other exogenous inflows include fish products, meat and species of yam which are not readily available or produced in large quantities in the district. Exogenous outflows from the district include agricultural goods. Both the exogenous inflows and outflows analysis shows that the major trading partners of the district in terms of directions of movements of ‘exports’ and ‘imports’ are Accra, Kumasi, Goaso, Mim, Tepa, Sunyani and Techiman. In addition, within the district, the Kukuom and Sankore markets serve as the main points of departure of goods from the district and destinations for goods arriving into the district.

From the foregoing, it is observed that goods that are ‘imported’ into the district are largely industrial goods attracting higher values. On the other hand, agricultural goods constitute the bulk of goods ‘exported’ from the district. These are usually in their raw states with less value, which do not yield much returns to the district. From this perspective, the district is bound to register deficit net trade balance. This situation accordingly calls for the setting up of agro-based industries to add value to the agricultural goods produced and exported from the district.

ROAD NETWORK

The district has about 70km-tarred roads, connecting the major towns with over 200km feeder roads linking the farming communities.  Following the government’s policy of ensuring easy access of products to and from market centers, the Assembly as the final policy implementer has also intensified upgrading of its feeder roads with the help of Assembly’s own acquired Grader.

EDUCATION

The Assembly spends quite a high proportion of its inflows on the provision of educational infrastructure. The categories are Nursery/Kindergarten :( public-81 & private 25), primary schools :( public-81 & private 25), junior high schools: (public-65 & private-5), Senior high schools :( public-2): Tertiary institution: Kwapong NTC. The District Education Directorate currently has 52 staff (both teaching and non-teaching staff)

However, the Assembly has completed about 2 classroom blocks and 12 ongoing projects. The BECE pass rate is shown in the table below:

| YEAR | BOYS% | GIRLS% | AVE TOTAL% |
| --- | --- | --- | --- |
| 2018 | 76.58 | 74.15 | 77.32 |
| 2019 | 77.26 | 70.12 | 77.98 |

HEALTH

The District Health Directorate has 24 Health facilities under its jurisdiction as shown in the table below:

The health sector must applauded for their significant role and interventions during this period of health emergency imposed on the world as a result of COVID-19, the very progress and achievement in combating this pandemic has come about due to the numerous protocols introduced by the Health sector practitioner’s.

| Ownership | Hospital | CHPs | Health Centers | Clinics | Maternity Homes | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Government | 1 | 19 | 1 | 0 | 0 | 21 |
| Mission | 0 | 0 | 0 | 0 | 0 | 0 |
| Private | 2 | 0 | 0 | 0 | 1 | 3 |
| Total | 3 | 19 | 1 | 0 | 1 | 24 |

WATER AND SANITATION

The current water delivery system in the District is a serious development challenge that requires an urgent intervention.

“Water is life” as they say, but the problem of water in the Asunafo South District has become acute and is well known in the national level which urgent steps, concern and support are needed by all stakeholders to reverse this trend, the presence of the Covid-19 indeed had its own effect on the District since, the water systems within the District must improve drastically to help manage the fast spreading virus.

Access to food and water are fundamental human rights, which should be prioritized for all to access for a healthy livelihood.

The availability of and accessibility to improved water is a crucial aspect of the health of households members.

Water Provision and Management

The provision and management of potable water has not been an easy task to the Assembly. The Assembly is currently faced with a number of challenges in its quest to make water accessible to the people. The challenges range from human to natural factors:

- Most water sources dry-up in the dry season, compelling people in those areas to revert to drinking from unwholesome sources, which make them vulnerable to water related diseases.

- The boreholes breakdown constantly because of excessive pressure coupled with the inability of communities to raise enough money for replacement and general maintenance.

- Even though wells appear to be the major source of water, they are mostly left unprotected.  As a result, run-offs trickle down into such unprotected wells making them unsafe for human consumption.

- Because of the limited number of water points, coupled with the general low water table in the District, women spend much of their productive hours in search of water to undertake their domestic chores. Children, and especially the girls, are mostly found helping their mothers to draw water at the expense of their education.

- For economic reasons, most consumers of the pipe system in the District have serious difficulties in paying their water bills. This adversely affects the operation and management of the facility.

- Administratively, the provision and management of water services are hampered by inadequate logistics, transport and remuneration for office and field staff.

In an effort to improve upon people’s access to potable water, the Assembly has collaborated with a number of development partners in the provision of potable water in the District. These partners include the Ghana Water Company Limited (GWCL), Community Water and Sanitation Agency (CWSA), and World Vision – Ghana, among others. The District health management team has complimented these efforts by educating people to keep water sources clean and safe. They also assist in detecting and treating water-borne diseases. Community ownership and management is also being promoted to enhance the sustainability of existing water facilities. Communities that have benefited from some form of water infrastructure, especially boreholes are being trained and provided with basic tools, equipment to undertake regular servicing, and maintenance of their water facilities.

Sanitation and Waste Management

Waste management in the District is far from been desirable. The disposal of both solid and liquid waste, including human excreta, storm water and household refuse are poorly carried out in the District. Though some households bury or burn their refuse, majority use the open surface system for their waste disposal. It is a general practice for people in most communities to defecate in the bush or openly (free range), mainly due to lack of access to convenient toilet facilities.

Where either households or the DA provides toilet facilities, there is however, a problem of timely and regular disposal of human excreta due to the unreliability of the only septic emptier in the District.

Most communities in the District do not also have any proper drainage system. The inadequacy of proper household drains has led to the accumulation of stagnant water with offensive smells in and around residential areas.  Drains are choked with filth giving rise to mosquito breeding especially during the rainy season.

ENERGY

The commonest source of energy for domestic purposes is firewood and charcoal. These are used mainly for cooking, baking and smoking of fish. Other energy sources are fuel used mainly to power water pumps, spraying machines for crops, generators and for vehicles. Some communities in the district also have access to electricity. However, majority of the communities are to be connected to the National electricity grid. Now about 95 percent of communities in the district have access to electricity. There is currently the supply of solar lightening within the deprived communities.

- VISION OF THE DISTRICT ASSEMBLY

The vision of the Asunafo south district Assembly is to have a district in which the people attain high standard of living through improvement in socio-economic services in a highly decentralized and democratic environment.

- MISSION STATEMENT OF THE DISTRICT ASSEMBLY

The Asunafo South District Assembly exists to harness all available resources within its area of jurisdiction to maintain excellence in education, agricultural production and local participation in governance to improve the standard of living of the people.

- KEY ACHIEVEMENTS IN 2020

The District has chopped the following achievements:

EDUCATION

- Completed a 6 Unit Classroom Block with Store, Office Facility and 400 Unit of Dual Desk at Kukuom Presby Primary

- Completed a 3Unit Classroom Block with 4 Seater KVIP at Kukuom Methodist Primary

- Extension of the Male Hostel and a 3 Unit teachers Quarters at Kwapong Nursing Training College

HEALTH SECTOR

- Completed a CHPs Compound with 4 Seater KVIP, a Urinal and Mechanised Borehole at Pafo Nkwanta

- Completed a CHPS compound with Nurses Quarters at Kwapong

WATER SYSTEMS

- Constructed 4 new Borehole and Rehabilitated 14 Boreholes within the District.

TELECOMMUNICATION

- Installation of GIFEX Network at Kokooso, Mintumi, Tetekwao and Dwrowakro.

- REVENUE AND EXPENDITURE PERFORMANCE

(a) Revenue Performance:

The table below shows all revenue financial performance for all funding sources such as IGF, Compensation transfers, Goods and services transfers, Asset transfers, DACF, DDF, MP Common Funds, People with Disability (PWD) Funds and Canadian International Development Agency (CIDA).

| REVENUE PERFORMANCE – ALL REVENUE SOURCES |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ITEM | 2018 |  | 2019 |  | 2020 |  | %Performance at Aug, 2020 |
|  | Budget (GH₵) | Actual (GH₵) | Budget (GH₵) | Actual (GH₵) | Budget (GH₵) | Actual (GH₵) |  |
| Total IGF | 502,243.75 | 467,548.52 | 390,000.00 | 455,034.49 | 422,883.64 | 288,119.11 | 68.13 |
| Compensation transfers | 1,531,174.00 | 1,543,312.32 | 1,948,594.80 | 1,543,312.23 | 1,831,391.51 | 1,253,901.49 | 68.47 |
| Goods and services transfer | 57,773.33 | 72,465.53 | 75,000.00 | 15,248.46 | 67,524.04 | 52,971.94 | 78.45 |
| Asset transfers | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| DACF | 3,302,960.00 | 1,198,898.69 | 3,968,511.44 | 2,466,599.11 | 4,540,269.71 | 1,148,663.84 | 25.31 |
| DDF | 837,000.00 | 630,872.21 | 1,283,475.58 | 1,469,999.84 | 2,048,134.78 | 596,931.11 | 29.15 |
| MAG FUND | 131,343.01 | 115,048.88 | 95,000.00 | 12,178.21 | 222,663.94 | 148,091.12 | 66.51 |
| TOTAL | 6,362,494.09 | 4,028,141.06 | 7,685,581.77 | 5,962,372.34 | 9,132,867.62 | 3,488,678.61 | 38.20 |

The table below indicates Internally Generated Fund Revenue sources:

| REVENUE PERFORMANCE |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ITEM | 2018 |  | 2019 |  | 2020 |  | %Performance as at Aug, 20 |
|  | Budget (GH₵) | Actual (GH₵) | Budget (GH₵) | Actual (GH₵) | Budget (GH₵) | Actual (GH₵) |  |
| RATES | 89,463.75 | 71055.52 | 93,000.00 | 146,552.00 | 99,000.00 | 46,664.09 | 47.14 |
| FEES | 50,780.00 | 32,000.00 | 55,000.00 | 32,000.00 | 85,000.00 | 52,054.00 | 61.24 |
| FINES | 10,000.00 | 5,462.00 | 10,000.00 | 5,462.00 | 5,500.00 | 4851.00 | 88.20 |
| LICENSES | 77,000.00 | 101,457.00 | 85,000.00 | 101,457 | 95,420.00 | 76,322.11 | 79.00 |
| LAND | 270,000.00 | 250,890.00 | 121,000.00 | 250,890.00 | 112,963.64 | 100,604.00 | 89.06 |
| RENT | 5,000.00 | 6,684 | 25,000.00 | 6,684 | 25,000.00 | 7,623.88 | 30.50 |
| MISCELLANEOUS | - | - | 1000 | - |  |  |  |
| TOTAL | 502,243.775 | 467,548.52 | 390,000.00 | 543,045.90 | 422,883.64 | 288,117.11 | 68.14 |

(B) EXPENDITURE PERFORMANCE

| EXPENDITURE PERFORMANCE (ALL DEPARTMENTS) GOG ONLY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Expenditure items | 2018 |  | 2019 |  | 2020 |  | %performance as at Aug. 2020 |
|  | Budget (GH₵) | Actual (GH₵) | Budget (GH₵) | Actual (GH₵) | Budget (GH₵) | Actual (GH₵) |  |
| Compensation | 1,531,174.00 | 1,846,312.33 | 1,877,294.80 | 1,543,312.23 | 1,831,391.50 | 1,253,901.49 | 68.47 |
| Goods and services | 57,773.33 | 72,465.53 | 75,000.00 | 15,248.46 | 67,524..04 | 52,971.94 | 78.45 |
| Assets |  |  |  |  |  |  |  |
| TOTAL | 1,588,947.33 | 1,615,777.86 | 1,952,294.80 | 1,558,560.69 | 1,898,915.63 | 1,306,873.43 | 68.83 |

The table below indicates expenditure performance for GOG funds sources in terms of Compensation, Goods and services, and Assets (compensation transfers, Goods and services transfers, asset transfers, DACF, DDF, MP Common fund, PWD, CIDA).

The table below shows expenditure performance for IGF funds sources in terms of Compensation, Goods and services, and Assets (Rate, Fees, Fines, Rents, Licenses, Land)

| EXPENDITURE PERFORMANCE (ALL DEPARTMENTS) IGF ONLY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Expenditure items | 2018 |  | 2019 |  | 2020 |  | %performance as at Aug, 2019 |
|  | Budget (GH₵) | Actual (GH₵) | Budget (GH₵) | Actual (GH₵) | Budget (GH₵) | Actual (GH₵) |  |
| Compensation | 85,300.00 | 63,396.87 | 71,300.00 | 57,904.83 | 65,358.35 | 32,973.81 | 50.45 |
| Goods and services | 306,557.78 | 312,161.54 | 240,700.00 | 383,129.26 | 357,500.26 | 220,145.30 | 61.58 |
| Assets | 0.00 | 0.00 | 78,000.00 | 102,011.90 | 84,974.56 | 35,000 | 41.19 |
| Total | 391,857.78 | 375,558.41 | 390,000.00 | 543,045.90 | 422883.65 | 288,119.11 | 68.14 |

- ASUNAFO SOUTH’S ADOPTED POLICY OBJECTIVES FOR 2021 LINK TO SUSTAINABLE DEVELOPMENT GOALS (SDGS)

The NMTDPF policy objectives adopted by the Asunafo South District Assembly are as follows:

- Support Entrepreneurship and SME development

- Improve production efficiency and yield

- Diversify and expend the Tourism Industry for Economy development

- Enhance inclusive and equitable access to and Participation in quality education at all Level

- Ensure Affordable, Equitable, Easily accessible and Universal Health Coverage (UHC)

- Improve Access to Improved and Reliable Environmental Sanitation Service

- Strengthen Social Protection, Especially for Children, Women, Persons with Disability and the Elderly

- Promote Proactive Planning for Disaster Prevention and Mitigation

- Promote a sustainable, Spatially Integrated, Balanced and Orderly Development of Human Settlement

- GOAL

The goal of the Asunafo South District is to enhance the socio-economic and political well-being of the people within the District through effective resource mobilization.

- CORE FUNCTIONS

The core functions of the District are outlined below:

- Exercise political and administrative authority in the district, provide guidance, give direction to, and supervise the administrative authorities in the district.

- Performs deliberative, legislative and executive functions.

- Responsible for the overall development of the district and shall ensure the preparation of development plans and annual and medium term budgets of the district related to its development plans.

- Formulate and execute plans, programs and strategies for the effective mobilization of the resources necessary for the overall development of the district.

- Promote and support productive activity and social development in the district and remove any obstacles to initiative and development.

- Initiate programs for the development of basic infrastructure and provide municipal works and services in the district.

- Responsible for the development, improvement and management of human settlements and the environment in the district.

- Responsible, in cooperation with the appropriate national and local security agencies, for the maintenance of security and public safety in the district.

- Ensure ready access to Courts in the district for the promotion of justice.

- Initiate, sponsor or carry out studies that are necessary for the performance of a function conferred by Act 462 or by any other enactment.

- Perform any other functions provided for under any other legislation.

- Take the steps and measures that are necessary and expedient to

- execute approved development plans and budgets for the district;

- guide, encourage and support sub-district local government bodies, public  agencies and local communities to discharge their roles in the execution of approved development plans;

- initiate and encourage joint participation with any other persons or bodies to execute approved development plans;

- promote or encourage other persons or bodies to undertake projects under approved development plans; and

- Monitor the execution of projects under approved development plans, assess, and evaluate their impact on the people’s development, the local, and district and national economy.

- Coordinate, integrate and harmonize the execution of program and projects under approved development plans for the district, any and other development program promoted or carried out by Ministries, departments, public corporations and any other statutory bodies and non-governmental organizations in the district.

- Finally, a District Assembly in the performance of its functions, is subject to the general guidance and direction of the President on matters of national policy, and shall act in co-operation with the appropriate public corporation, statutory body or non-governmental organizations.

- POLICY OUTCOME INDICATORS AND TARGETS

| Outcome Indicator Description | Unit of Measurement | Baseline |  | Latest Status |  | Target |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Year | Value | Year | Value as at July | Year | Value |
| Revenue generation | Amount of IGF generation | 2018 | 467,548.53 | 2019 | 543,045.90 | 2020 | 422,883.69 |
| Project implementation | % implementation of AAP | 2018 | 83% | 2019 | 85% | 2020 | 88% |
| Functionality of District Assembly | Score of FOAT Performance | 2018 | 96% | 2019 | 96% | 2020 | - |
| Improve development control | No. of permit issue | 2018 | 42 | 2019 | 44 | 2020 | 50 |
| Citizenship engagement and participation in decision making | No of public hearings/Town hall meeting/consultative meetings conducted | 2018 | 3 | 2019 | 3 | 2020 | 10 |
|  | No. of fee fixing resolution meetings held | 2018 | 1 | 2019 | 1 | 2020 | 1 |
| Transparency and accountability | Audited financial report made public by | 2018 | Jun. 2018 | 2019 | June. 2020 | 2020 | June. 2021 |
| Access to health delivery service | No. of health facilities | 2018 | 23 | 2019 | 23 | 2020 | 24 |
|  | Doctor to Population ratio | 2018 | 1:5592 | 2019 | 1:39,032 | 2020 | 1:39,910 |
| Increased Public Education on HIV?AIDS | Number of New Infection | 2018 | 122 | 2019 | 146 | 2020 | 89 |
| Teaching and learning improved | no. of classroom constructed | 2018 | 4 | 2019 | 2 | 2020 | 1 |
|  | % of pupil passing BECE | 2018 | 77.82 | 2019 | 77.98 | 2020 |  |
| Water Coverage | % of pop. Served with safe water | 2018 | 73% | 2019 | 78% | 2020 | 85% |
| Sanitation coverage | % of pop. Served with safe excreta disposal facilities | 2018 | 37% | 2019 | 37% | 2020 | 56% |
| Gender mainstreaming | No. of women groups organized and supported | 2018 | 15 | 2019 | 24 | 2020 | 35 |
| Access to Agricultural Extension services | No. of farm and home visits conducted | 2018 | 2160 | 2019 | 1995 | 2020 | 3500 |

- REVENUE MOBILIZATION STRATEGIES FOR KEY REVENUE SOURCES IN 2019

| REVENUE SOURCE | KEY STRATEGIES |
| --- | --- |
| - RATES (Basic Rates/Property Rates/Cattle Rates) | - Sensitize cattle owners (Fulani herdsmen) and other ratepayers on the need to pay Cattle/Basic/Property rates. - Update data on all cattle owners in the district - Activate Revenue taskforce to assist in the collection of cattle rates |
| - LANDS | - Sensitize the people in the district on the need to seek building permit before putting up any structure. - Establish a unit within the Works Department solely for issuance of building permits |
| - LICENSES | - Sensitize business operators to acquire licenses and also renew their licenses when expired |
| - RENT | - Numbering and registration of all Government bungalows - Sensitize occupants of Government bungalows on the need to pay rent. - Issuance of demand notice |
| - FEES AND FINES | - Sensitize various market women, trade associations and transport unions on the need to pay fees on export of commodities - Formation of revenue monitoring team to check on the activities of revenue collectors, especially on market days. |
| - INVESTMENT (Bulldozer & Grader) | - Position a Revenue Collector at the sand winning site. - Improving on monitoring on the activities of the operators of the bulldozer and grader. |
| - REVENUE COLLECTORS | - Quarterly rotation of revenue collectors - Setting target for revenue collectors - Engaging the service of the Chief Local Revenue Inspector (at RCC) to build the capacity of the revenue collectors - Sanction underperforming revenue collectors - Awarding best performing revenue collectors. |

# PART B: BUDGET PROGRAMME SUMMARY

## PROGRAMME 1: MANAGEMENT AND ADMINISTRATION

- BUDGET PROGRAMME OBJECTIVES

The objectives of this program are as follows:

- To provide administrative support for the Assembly

- To formulate and translate policies and priorities of the Assembly into strategies for efficient and effective service delivery

- Improve resource mobilization and financial management

- Provide timely reporting, monitoring, and evaluation (M&E) of projects and programmes.

- To provide efficient human resource management of the District.

- BUDGET PROGRAMME DESCRIPTION

The Management and Administration program is responsible for all activities and program relating to Human Resource Management, General Services, Planning and Budgeting, Finance and Revenue Mobilization, Procurement/Stores, Transport, Public Relations, Training and Travels, ICT, Security and Legal. This program also includes the operations of the Town/Area councils in the district, which include Kukuom area Council, Kwapong, Aboum, Kokooso, Sankore and Asarekrom Area Councils.

The Central Administration Department is the Secretariat of the District Assembly and responsible for the provision of support services, effective and efficient general administration and organization of the District Assembly. The Department manages all sections of the assembly including records, estate, transport, logistics and procurement, budgeting functions and accounts, stores, security and human Resources Management.  The Department also coordinates the general administrative functions, development planning and management functions, rating functions, statistics and information services generally, and human Resource Planning and Development of the District Assembly. Units under the central administration to carry out this program are spelt out below.

- The Finance Unit leads in the management and use of financial resources to achieve value for money and keeps proper accounts records.

- The Human Resource Unit is mainly responsible for managing, developing capabilities and competencies of each staff as well as coordinating human resource management programmes to efficiently deliver public services.

- The Budget Unit facilitates the preparation and execution of budgets of the District Assembly by:

- Preparing, collating and submitting annual estimates of decentralized departments in the District.

- Translating national medium term programme into the district specific investment programme; and

- Organizing in-service-training programmes for the staff of the departments in budget preparation, financial management and dissemination of information on government financial policies.

- The unit also verify and certify the status of district development projects before request for funds for payment are submitted to the relevant funding; prepare rating schedules of the District Assembly; collate statistical inputs that will enhance the preparation of the budget; and  monitor programmes and projects of the Assembly as a measure to ensure economic utilization of budgetary resources.

- The Planning Unit is responsible for strategic planning, efficient integration and implementation of public policies and programmes to achieving sustainable economic growth and development. The unit is the secretariat of District Planning and Co-ordination unit (DPCU).

- The Internal Audit Unit provides reliable assurance and consulting services to management on the effectiveness of the control system in place to mitigate risk and promote the control culture of the Assembly.

- Procurement and stores facilitate the procurement of Goods and Services, and assets for the District. They also ensure the safe custody and issue of store items.

- The Information services unit, which serves the Assembly in Public Relations, promotes a positive image of the District with the broad aim of securing for Assembly, public goodwill, understanding and support for overall management of the district.

Kukuom, Sankore, Aboum, Kokooso and Asarekrom Area Councils have been strengthened to bring more meaning into the decentralization process and hence responsible for grassroots support and engagement in planning, budgeting and resources mobilization.

Staff for the delivery of this program is 41 (33 are on GoG pay roll and 9 on IGF pay roll).

BUDGET SUB-PROGRAMME SUMMARY

PROGRAMME1: Management and Administration

SUB-PROGRAMME 1.1 General Administration

- BUDGET SUB-PROGRAMME OBJECTIVE

- To facilitate and coordinate activities of department of the Assembly

- To provide effective support services

- BUDGET SUB-PROGRAMME DESCRIPTION

The general Administration sub-program oversees and manages the support functions for the Asunafo South District Assembly. The sub-program is mainly responsible for coordinating activities of decentralized departments and providing support services. The sub-program provides transportation, records, security, public relations, adequate office equipment, stationery, and other supporting logistics.

A total of 30 staff are to execute this sub-program comprising of 4 Administrative officers (1 Deputy Director, 1 Assistant Director I, Assistant Director IIA, Assistant Director IIB), 5 Executive officers, 1 Radio Operator, 3 Typists, 7 Watchmen, 8 Drivers, 2 cleaners. However, one Typist, 4 Watchmen, 1 Driver on IGF and rest are on GOG Payroll.  Funding for this program is mainly IGF, DACF, DDF, GoG and Donors whereas the Area councils dwell mainly on ceded revenue from internally generated revenue. The departments of the assembly and the public are beneficiaries of the sub-program.

- BUDGET SUB-PROGRAMME RESULTS STATEMENT

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-programme. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.

| Main Outputs | Output Indicator | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2019 | 2020 | Budget Year 2021 | Indicative Year 2022 | Indicative Year 2023 | Indicative Year 2024 |
| Regular Management meetings Held | No. of management meetings held | 12 | 12 | 12 | 12 | 12 | 12 |
| Meetings Entity Tender Committee Held | No. of Entity Tender Committee meetings held | 4 | 4 | 4 | 4 | 4 | 4 |
| Meetings of District Security Committee Held | No. of District Security Committee meetings held | 20 | 25 | 15 | 18 | 15 | 12 |
| Meetings of Public Relations and Complaints Committee (PRCC) | No. of Public Relations and Complaints Committee (PRCC) Meetings Held | 4 | 4 | 4 | 4 | 4 | 4 |

- BUDGET SUB-PROGRAMME OPERATIONS AND PROJECTS

The table lists the main Operations and projects to be undertaken by the sub-program

| Operations |  | Projects |
| --- | --- | --- |
| Servicing and Maintenance of Official Vehicles and Motorbikes |  | Completion of 1No. 3- storey Administration Block at Kukuom |
| Internal management and running of the office |  | Construction of 1No.3unit semi –detached staff quarters at Kukuom |
| Furnish some residences of the District Assembly and other Decentralized Departments |  | Renovation of official Bungalow at Residency |
| Support Security Agency to fight crime |  |  |
| Organise National Day Celebrations (Independence Day, Republic Day, Farmers Day, etc.) |  |  |
| Organise regular Management meetings |  |  |
| Organize Entity Tender Committees meetings |  |  |
| Organize District Security Committee meetings |  |  |
| Organize Public Relations and Complaints Committee (PRCC) meetings |  |  |

BUDGET SUB-PROGRAMME SUMMARY

PROGRAMME1: Management and Administration

SUB-PROGRAMME 1.2 Finance and Revenue Mobilization

- BUDGET SUB-PROGRAMME OBJECTIVE

- Improve financial management and reporting through the promotion of efficient Accounting system

- Ensure effective and efficient mobilization of resources and its utilization

- BUDGET SUB-PROGRAMME DESCRIPTION

The sub-program seeks to ensure effective and efficient resource mobilization and management. The Finance and Revenue mobilization sub-program comprises of two units namely, the Accounts/Treasury, budget units and internal audit. Each Unit has specific rolls they play in delivering the said outputs for the sub-program. The account unit collects records and summarizes financial transactions into financial statements and reports to assist management and other stakeholders in decision-making. They also receive, keep safe custody and disburse public funds. This unit together with the Budget unit sees to the payment of expenditures within the District. The budget unit issue warrants of payment and participating internally revenue generation of the Assembly.

The internal audit unit ensures that payment vouchers submitted to the treasury are duly registered and checking all supporting documents to payment vouchers, to ensure they are complete before payments are effected. This is to strengthen the control mechanisms of the Assembly.

This major activity helps to ensures reconciliations and helps in providing accurate information during the preparation of monthly financial statement, which is later submitted for further actions. Three officers, comprising two Accountants, a Senior Accountant and an Internal Auditor, proficiently man the sub-program. Funding for the Finance sub-program is from Internally Generated Revenue (IGF), GoG and DACF.

CHALLENGES

The following are the key Challenges to be encountered in delivering this sub-program:

- Inadequate motorbikes for revenue mobilisation.

- Inadequate office room for accounts officers.

- BUDGET SUB-PROGRAMME RESULTS STATEMENT

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-program. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.

| Main Outputs | Output Indicator | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2019 | 2020 | Budget Year 2021 | Indicative Year 2022 | Indicative Year 2023 | Indicative Year 2024 |
| Regular Management meetings Held | No. of management meetings held | 5 | 4 | 12 | 12 | 12 | 12 |
| Revenue collection monitored and supervised | No. of visits to market Centre | 5 | 10 | 10 | 15 | 15 | 15 |
| Level of Implementation of Revenue Improvement Action Plan (RIAP) improved | % of Implementation of the RIAP | 88% | 95% | 56% | 100% | 100% | 100% |
| Monthly Financial reports prepared | No. of monthly financial reports prepared and submitted by the 15th day of the ensuing month | 12 | 12 | 12 | 12 | 12 | 12 |
| Accounts and records of funds are maintained and submitted for Audit | No. of times Accounts and records are audited | 4 | 4 | 4 | 4 | 4 | 4 |

- Budget Sub-Programme Operations and Projects

The table lists the main Operations and projects to be undertaken by the sub-programme.

| Operations |  | Projects |
| --- | --- | --- |
| Regular monitoring and supervision of revenue collection |  |  |
| Preparation of revenue improvement action |  |  |
| Keeping proper records of accounts |  |  |
| Evaluation of property rate |  |  |

BUDGET SUB-PROGRAMME SUMMARY

PROGRAMME1: Management and Administration

SUB-PROGRAMME 1.3 Planning, Budgeting and Coordination

- Budget Sub-Programme Objective

- Facilitate, formulate and coordinate  plans and budgets and

- Monitoring of projects and programmes.

- Budget Sub-Programme Description

The sub-program is responsible for preparation of comprehensive, accurate and reliable action plans and budgets.  The sub-program will be delivered by conducting needs assessment of Area councils and communities; hold budget committee meetings, DPCU meetings, stakeholder meetings, public hearings to ensure participatory planning and budgeting. The two main units for the sub-program include the planning unit and budget unit as well as the expanded DPCU. Funds to carry out the program include IGF, DACF, and DDF. Effective delivery of this sub-program will benefit not only the community members but also development partners and the departments of the assembly.

Plans and budgets of decentralized departments are not easy to come by and thus posing a hindrance towards achieving the objectives of this sub-program. Other challenges include lack of motorbikes to undertake effective M&E, lack of commitment and teamwork from departments, inadequate knowledge on new planning and budgeting reforms by the decentralized departments and political interference. Four officers comprising of one Budget Analyst, three Planning Officers, proficiently manage the sub-program.  Funding for the planning and budgeting sub-program is from GOG, IGF and DACF.

The sub-program will be manned by 4 officers comprising of 1 Budget Analyst, 3 Assistant Budget Analyst, 1Principal Planning Officers, 1 Planning Officers, 1 Assistant Planning . The main challenges in carrying out the sub-program include lack of collaboration with other decentralized departments and non-adherence to rules and regulations.

- Budget Sub-Programme Results Statement

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-program. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.1

| Main Outputs | Output Indicator | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2019 | 2020 | Budget Year 2021 | Indicative Year 2022 | Indicative Year 2023 | Indicative Year 2024 |
| Fee fixing resolution prepared | Fee fixing resolution prepared and gazetted by | 31st Dec. | 31st Dec. | 31st Dec. | 31st Dec. | 31st Dec. | 31st Dec. |
| Monitoring of projects and programmes | No. of site visits undertaken | 4 | 4 | 4 | 4 | 4 | 4 |
| Plans and Budgets produced and reviewed | Annual Action Plan prepared by | Sept. | July | June | June | June | June |
|  | District Composite Budget prepared by | October | October | October | October | October | October |
|  | AAP and composite budget reviewed by | 30th June | 30th June | 30th June | 30th June | 30th June | 30th June |

- Budget Sub-Programme Operations and Projects

The table lists the main Operations and projects to be undertaken by the sub-programme

| Operations |  | Projects |
| --- | --- | --- |
| Organise stakeholder meetings |  |  |
| Budget committee meetings |  |  |
| Organise DPCU meetings |  |  |
| Organise public hearings |  |  |
| Prepare District Medium Term Development Plan (2018-2021) |  |  |
| Prepare AAP and District Composite Budget (Medium Term Expenditure Framework – MTEF) |  |  |
| Review AAP and composite budget |  |  |
| Prepare District Water, Sanitation and Health Plan |  |  |

BUDGET SUB-PROGRAMME SUMMARY

PROGRAMME1: Management and Administration

SUB-PROGRAMME 1.4 Legislative Oversights

- Budget Sub-Programme Objective

To perform deliberative and legislative functions in the district

- Budget Sub-Programme Results Statement

The table indicates the main outputs, its indicators and projections by which the Districts measure the performance of this sub-program. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.

| Main Outputs | Output Indicator | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2019 | 2020 | Budget Year 2021 | Indicative Year 2022 | Indicative Year 2023 | Indicative Year 2024 |
| General Assembly meetings Held | No. of General Assembly meetings held | 3 | 3 | 3 | 4 | 4 | 4 |
| Meetings of the Sub-committees held | No. of meetings of the Sub-committees held | 4 | 4 | 4 | 4 | 4 | 4 |
| Executive Committee meetings held | No. of Executive Committee meetings held | 3 | 3 | 3 | 4 | 4 | 4 |

- Budget Sub-Programme Operations and Projects

The table lists the main Operations and projects to be undertaken by the sub-program

| Operations |  | Projects |
| --- | --- | --- |
| Organize and service regular Assembly meetings |  |  |
| Organize Executive Committee meetings |  |  |
| Organise meetings of the Sub-committees |  |  |

BUDGET SUB-PROGRAMME SUMMARY

PROGRAMME1: Management and Administration

SUB-PROGRAMME 1.5 Human Resource Management

- Budget Sub-Programme Objective

The objective of the sub-programme is

- Coordinate overall human resources programmes of the district.

- Budget Sub-Programme Description

The Human resource management sub-Programme seeks to manage, develop capabilities and competences of staff and coordinate human resource programmes for efficient delivery of public service. The sub-Programme would be carried out through ensuring regular updates of staff records, staff needs assessment, ensuring general welfare of staff, ensuring inter and intra departmental collaboration to facilitate staff performance and development, organizing staff trainings to build their capabilities, skills and knowledge.

The human resource unit has strength of two officers comprising of one Human resource Assistant and 1Senior Personnel Officer. Funds to deliver the human resource sub-Programme include IGF, DACF and DDF capacity building. The main challenge faced in the delivery of this sub-Programme is the weak collaboration in human resource planning and management with key stakeholders also Logistics Constraints

- Budget Sub-Programme Results Statement

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-programme. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.

| Main Outputs | Output Indicator | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2019 | 2020 | Budget Year 2021 | Indicative Year 2022 | Indicative Year 2023 | Indicative Year 2024 |
| Accurate and comprehensive HRMI data updated and submitted to RCC | No. of updates and submissions done | 12 | 12 | 11 | 12 | 12 | 12 |
| Capacity of staff built on public procurement | No. of staff trained on public procurement | - | - | - | 4 | 4 | 4 |
| Junior staff supported to undertake secretariat courses at Gov’t secretariat school, Accra | No. of staff | - | - | 1 | 3 | 3 | 3 |
| Staff assisted in performance appraisal | Number of staff appraised | 109 | 123 | 123 | 123 | 123 | 123 |
| Ensure efficiency in service delivery | No. of staff trained /supported for short courses | - | - | 1 | 5 | 5 | 5 |

- Budget Sub-Programme Operations and Projects

The table lists the main Operations and projects to be undertaken by the sub-programme

| Operations |  | Projects |
| --- | --- | --- |
| Personnel and Staff management |  |  |
| Human Resource planning |  |  |
| Human Resource management |  |  |
| Human Resource training and development |  |  |

BUDGET PROGRAMME SUMMARY

## PROGRAMME 2: INFRASTRUCTURE DELIVERY AND MANAGEMENT

- Budget Programme Objectives

- To exercise district-wide responsibility in planning, management and promotion of harmonious, sustainable and cost effective development of human settlements in accordance with sound environmental and planning principles.

- To provide socioeconomic infrastructure  and ensure periodic review of plans & programmes for construction and general maintenance of all public properties and drains

- Budget Programme Description

The programme is responsible for provision of physical and socioeconomic infrastructure while promoting a sustainable human settlement development on principle of efficiency, orderliness, safe and healthy growth of communities.  Key departments in carrying the programme include the Physical Planning Department and the District Works Department.

The physical planning is responsible:

- Planning and management of human settlements; provision of planning services to public authorities and private developers;

- Development of layouts plans (planning schemes) to guide orderly development;

- Collaboration with survey department, prepare acquisition plans when stool land is being acquired;

- Responsible for physical/spatial planning of customary land in conjunction with the stool/skin; and

- Responsible for development control through granting of permit.

- The District Works department carry out such functions in relation to feeder roads, water, rural housing etc.

- The department advises the Assembly on matters relating to works in the district;

- Assist in preparation of tender documents for civil works projects;

- Facilitate the construction of public roads and drains;

- Advice on the construction, repair, maintenance and diversion or alteration of street;

- Assist to inspect projects under the Assembly with departments of the Assembly;

- Provide technical advice for the machinery and structural layout of building plans to facilitate escape from fire, rescue operation and fire management; and

- Provide technical and engineering assistance on works undertaken by the Assembly and owners of premises.

The District Assembly however has one physical planning officer and nine staff to carry out the infrastructure delivery and management Programme. The Programme will be funded using funds from IGF, DACF, and DDF.

BUDGET SUB-PROGRAMME SUMMARY

PROGRAMME2: Infrastructure Delivery and Management

SUB-PROGRAMME 2.1 Physical and Spatial Planning

- Budget Sub-Programme Objective

- To facilitate the implementation of such polices in relation to physical planning, land use and development within the framework of national polices.

- Budget Sub-Programme Description

This bub-programme seeks to ensure planning, management and promotion of harmonious, sustainable and cost effective development of human settlements in accordance with sound environmental and planning principles. Specific functions of the sub-programme include:

- Preparation of physical plans as a guide for the formulation of development policies and decisions and to design projects in the district.

- Identify problems concerning the development of land and its social, environmental and economic implications;

- Advise on setting out approved plans for future development of land at the district level;

- Advise on preparation of structures for towns and villages within the district;

- Assist to offer professional advice to aggrieved persons on appeals and petitions on decisions made on their building;

- Facilitate consultation, co-ordination and harmonization of developmental decisions into a physical development plan;

- Assist to provide the layout for buildings for improved housing layout and settlement;

- Ensure the prohibition of the construction of new buildings unless building plans submitted have been approved by the Assembly;

- Advise the Assembly on the siting of bill boards, masts and ensure compliance with the decisions of the Assembly;

- Advise on the acquisition of landed property in the public interest; and

- Undertake street naming, numbering of house and related issues.

The organizational unit that will be involved is the Town and Country Planning unit and t Asunafo South District has one (1) staff ; Technical Officer.

The sub-programme is funded through the DACF, GOG and the Internally Generated Revenue. The larger community and other departments of the Assembly stand to benefit greatly in this sub-programme. The main challenge confronting the sub-Programme is the lack of staff to operate and supervise the implementation of programme and projects under the sub-programme. Inadequate resource both financial and in human resource to prepare base maps.

- Budget Sub-Programme Results Statement

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-programme. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.

| Main Outputs | Output Indicator | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2019 | 2020 | Budget Year 2021 | Indicative Year 2022 | Indicative Year 2023 | Indicative Year 2024 |
| Valuation of Properties in Kukuom, Sankore, Nobekaw, Kwapong Townships | No. of properties valuated | - | - | - | 50 | 65 | 77 |
| Preparation of Base Maps and Local Plans | Number of communities with base maps | 2 | 2 | 2 | 6 | 6 | 6 |
|  | Number of communities with local plans | 3 | 3 | 3 | 6 | 6 | 6 |
| Street Named and Property Addressed | Number of streets named | 8 | - | - | 5 | 6 | 10 |
|  | Number of properties addressed | - | 80 | 200 | 300 | 450 | 500 |
| Statutory planning committee meeting organized | No. of statutory planning committee meetings organized | 1 | 2 | 4 | 4 | 4 | 4 |
| Create public awareness on development control | No. of public awareness organized | - | 2 | - | 4 | 4 | 4 |

- Budget Sub-Programme Operations and Projects

The table lists the main Operations and projects to be undertaken by the sub-programme

| Operations |  | Projects |
| --- | --- | --- |
| Valuation of Properties in Kukuom, Nobekaw, Kwapong, Sankore Township |  |  |
| Preparation of Base Maps and Local Plans |  |  |
| Street Named and Property Addressed |  |  |
| Statutory planning committee meeting organized |  |  |
| Create public awareness on development control |  |  |
| Issuance of development permits |  |  |

BUDGET SUB-PROGRAMME SUMMARY

PROGRAMME2: Infrastructure Delivery and Management

SUB-PROGRAMME 2.2 Infrastructure Developments

- Budget Sub-Programme Objective

- To facilitate the implementation of such polices in relation to feeder roads, water and sanitation rural housing and public works within the framework of national polices.

- Budget Sub-Programme Description

The sub-programme is delivered through facilitating the construction, repair and maintenance of project on roads, water systems, building etc. The sub-programme also  prepare project cost estimates on roads, buildings, water and sanitation for award of contract; supervise   all civil and building works to ensure quality, measure works for good project performance.  The Department also checks quality performance and recommends claims for preparation of payment Certificate/Fluctuations and Variations; rehabilitation and construction of boreholes, reshaping of roads and street lightening across the District; and facilitate the identification of Communities to be connected on to the National Grid.

The Department of Works of the District Assembly is a merger of the Public Works Department, Department of Feeder Roads and District Water and Sanitation Unit, Department of Rural Housing and the Works Unit of the Assembly. The beneficiaries to the bub-Programme include the public, contractors and other departments of the Assembly.

There are 9staff in the Works Department executing the sub-Programme and comprises of 1Assistant Engineer, 1Chief work superintendent, 1 work superintendent, 1Tradesman Grade I, 2 Foreman, 2 Senior Technician Engineer,1Electrician on GOG pay-roll.  Funding for this Programme is mainly DDF, DACF, GOG and IGF

Key challenges of the department include delay in release of funds, limited capacity (water and sanitation engineers, hydro geologists) to effectively deliver water and sanitation project, difficult hydro-geological terrain results in low success rate in borehole drilling, inadequate personnel and logistics(especially motorbikes) for monitoring of operation and maintenance of existing systems and other infrastructure. Another key challenge is inadequate and late release of funds. This leads to wrong timing of operations and projects thereby affecting implementation of projects and operations.

- Budget Sub-Programme Results Statement

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-programme. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.

| Main Outputs | Output Indicator | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2019 | 2020 | Budget Year 2021 | Indicative Year 2022 | Indicative Year 2023 | Indicative Year 2024 |
| Project inspection | No. of site meetings organised | 12 | 10 | 20 | 20 | 20 | 20 |
| Increase electricity coverage | No. of communities connected to the National Grid | 60 | 55 | 15 | 15 | 15 | 15 |
| Portable water coverage improved | No. of boreholes provided | 4 | 4 | 20 | 20 | 20 | 20 |
|  | No. of borehole mechanized | - | 4 | 4 | 10 | 12 | 15 |
| WSMTs formed and trained | No. of WSMTs formed and trained | - | 8 | 15 | 15 | 15 | 15 |
| Improved condition of Feeder Road | Km of Motorable road | 122.9Km | 139.2Km | 191.6Km | 200Km | 259Km | 320 Km |

- Budget Sub-Programme Operations and Projects

The table lists the main Operations and projects to be undertaken by the sub-programme

| Operations |  | Projects |
| --- | --- | --- |
| Routine project inspection |  | Construction of mechanise Borehole at Siana, Asarekrom & Sikafrebogya |
| Preparation of tender documents |  | Supply and installation of streetlight in Kukuom, Kwapong, Nobekaw and Sankore |
| Tracking progress of work on developmental projects |  | Reshaping of Feeder Roads |

BUDGET PROGRAMME SUMMARY

## PROGRAMME 3: SOCIAL SERVICES DELIVERY

- Budget Programme Objectives

- To provide equal access to quality basic education to all children of school - going age at all levels

- To improve access to health service delivery.

- Facilitate in the integrating the disadvantaged, vulnerable and excluded in mainstream of development.

- Works in partnership in the communities to improve their well-being through promoting social development with equity for the disadvantaged, the vulnerable, persons with disabilities and excluded.

- Budget Programme Description

Social Service Delivery is one of the key Programmes of the Assembly. This Programme seeks to take an integrated and holistic approach to development of the District and the Nation as a whole. There are four sub-Programmes under this Programme namely: Education and Youth Development, Health delivery and Social Welfare and Community Development.

The education, Youth and Sport Department of the Assembly is responsible for pre-school, special school, basic education, youth and sports, development or organization and library services in the district. The department therefore assists the Assembly in the formulation and implementation of programmes in such areas of education and youth development.

The Department of Health in collaboration with other departments assist the Assembly to deliver context specific health care interventions by providing accessible, cost effective and efficient health service at the primary and secondary care levels in accordance with approved  national policies by ensuring prudent management of resources.

The Social Welfare and Community Development Department assist the Assembly to formulate and implement social welfare and community development policies within the framework of national policy.

Extreme poverty continues to work against the economic gains that Ghana has chalked over the past two decades. It is estimated that about 10% of Ghanaians live under extreme poverty conditions. This means that they are neither able to afford daily subsistence requirement nor afford education and basic health for themselves and their children.

This phenomenon perpetuates generational poverty. In order to ensure equitable distribution of national resources and mainstreaming of the extremely poor, Government developed and started implementing the National Social Protection Strategy (NSPS) in 2007. In Asunafo South District, 200 households are benefitting from conditional and unconditional cash transfer under the Livelihood Empowerment against Poverty (LEAP) Programme; a component of the NSPS. Extremely poor Older Persons above 65 years have been enrolled onto the LEAP and are entitled to unconditional cash transfer.

The total number of personnel under this budget Programme is 1,659.

BUDGET SUB-PROGRAMME SUMMARY

PROGRAMME3: SOCIAL SERVICES DELIVERY

SUB-PROGRAMME 3:1 Education and Youth Development

- Budget Sub-Programme Objective

- To ensure inclusive and equitable access to education at all levels

- Provide relevant quality pre-tertiary education to all children

- Budget Sub-Programme Description

The Education Youth Development sub-programme intends to produce well-balanced individuals with requisite knowledge, skill, value and attitude to become functional and productive citizens for the total development of the District and Ghana at large.

This sub-programme is carried through:

- Formulation and implementation of policies on Education in the District within the framework of National Policies and guidelines;

- Advise the District Assembly on matters relating to preschool, primary, Junior High Schools in the District and other matters that may be referred to it by the District Assembly;

- Facilitate the appointment, disciplining, posting and transfer of teachers in pre-schools, basic schools and special schools in the district;

- Liaise with the appropriate authorities for in-service training of pupil teachers and encouraging teachers to undergo advance studies relevant to the field;

- Supply and distribution of textbooks in the district

- Advise on the construction, maintenance and management of public schools and libraries in the district;

- Advise on the granting and maintenance of scholarships or bursaries to suitably qualified pupils or persons to attend any school or other educational institution in Ghana or elsewhere;

- Assist in formulation and implementation of youth and sports policies, programmes and activities of the District Assembly;

Organisational units in carrying the sub-programme include the Basic Education Unit, Non-Formal Education Unit, Youth and Sport Unit. The department responsible for the sub-programme is the District Education Directorate.

In carrying out this sub-programme, funds would be sourced from GoG, DACF and Donor support. The community, development partners and departments are the key beneficiaries to the sub-programme. The department has 1,483 staff consisting of 55 Administration officers and 1,428 Teachers: - 278 Teachers at Kindergarten, 549 Teachers at the primary schools, 447 Teachers at the Junior High Schools and 154 Teachers at the Senior High Schools /Technical

Challenges in delivering the sub-programme include the following:

- Inadequate and late release of funds. This leads to wrong timing of operations and projects thereby affecting implementation of projects and operations.

- Poor and inaccessible road networks hindering monitoring and supervision of schools.

- Lack of staff commitment.

- Wrong use of technology by schoolchildren – Mobile phones, TV programmes etc.

- Socio-economic practices – elopement, betrothals, early marriage etc.

- Budget Sub-Programme Results Statement

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-programme. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.

| Main Outputs | Output Indicator |  | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2019 | 2020 | Budget Year 2021 | Indicative Year 2022 | Indicative Year 2023 | Indicative Year 2024 |
| Enrolment increased | Gross enrolment Rate | KG | 69.2% | 66.7% | 82.7% | 88.3% | 91.2% | 92% |
|  |  | Primary | 89.8% | 87.2% | 88.2% | 91.7% | 92.0% | 93% |
|  |  | JHS | 48.1% | 49.3% | 51.9% | 63.4% | 65.8% | 77% |
|  |  | SHS | 50% | 78% | 90% | 90% | 95% | 95% |
|  | Gender Parity Index | KG | 1.67 | 0.74 | 0.23 | 1.0 | 1.0 | 1.0 |
|  |  | Primary | 3.36 | 4.65 | 2.8 | 1.0 | 1.0 | 1.0 |
|  |  | JHS | 8.51 | 6.50 | 5.69 | 2.0 | 2.0 | 2.0 |
|  |  | SHS | 9.24 | 20.14 | 13.55 | 5.0 | 5.0 | 5.0 |
| Literacy and Numeracy levels improved | BECE pass rate |  | 83.17% | 84.08% | 85.45% | 100% | 100% | 100% |
|  | Percentage of students with reading ability |  | 35% | 40% | 42% | 45% | 50% | 55% |
| Schools monitored | Percentage of schools visited for inspection |  | 92% | 95% | 98.5% | 100% | 100% | 100% |
| Organized quarterly DEOC meetings | No. of meetings organised |  | 4 | 3 | 4 | 4 | 4 | 4 |
| Provision of educational facilities | No. of classroom block with ancillaries constructed |  | 3 | 5 | 8 | 6 | 10 |  |
|  | No. of teachers quarter constructed |  | 2 | 2 | 2 | 4 | 4 | 4 |
|  | No. of dining halls constructed |  | 0 | 2 | 1 | 1 | 0 | 0 |

- Budget Sub-Programme Operations and Projects

The table lists the main Operations and projects to be undertaken by the sub-programme

| Operations |  | Projects |
| --- | --- | --- |
| Financial support (Scholarships) |  | Completion of 1No 3unit classroom block at Motopenso |
| Support for brilliant but needy students |  | Construction of 1No. 3unit classroom Block with ancillary facility at Noberkaw Methodist JHS |
| Support for District Education Oversight Committee (DEOC) |  | Construction of 1N0. 3unit Classroom Block with ancillary Facilities at Kukuom Methodist |
| Support for Sports and cultural Development |  | Construction of 1No. 3-unit classroom Block with ancillary facilities at Kukuom Presby |
| Organise Independence day celebration |  | Supply of 2000 Dual Desks at D/W |
| Organise Best Teacher Awards |  | Construction of 3-unit classroom block with ancillary facilities at Aboum DA JHS |
| Conduct regular monitoring and supervision of education operations and projects |  | Construction and Completion of Teachers’ quarters at Opongkrom |
| Provide adequate office stationery and other logistics |  | Completion of Teachers’ Quarters with 2No. Toilet and Bathroom at Naketey |
| My First Day at School |  | Construction of 1No. Teachers’ quarters at Yankye |
|  |  | Completion of 1No. 3-unit classroom Block at Siiso |
|  |  | Completion of 1No. 3-unit classroom Block at Abonyereso |
|  |  | Construction of 1No. 3-unit Classroom Block at Sankore SHS |
|  |  | Construction of 1No. 3-unit Classroom Block at Oseikrom |
|  |  | Construction of 1No. 6unit Classroom block at Kukuom Presby Primary & supply of 400No. dual desk |
|  |  | Construction of 1No. 3-unit Classroom Block at sisoo JHS |
|  |  | Construction of 1No. 3-unit Classroom at Kukuom Anglican KG |
|  |  | Completion of 1No. 3-unit Classroom Block with 4-seater KVIP and urinal at Kukuom |
|  |  | Construction of 1No. 3-unit Classroom Block at Siiso Bowjiase |
|  |  | Construction of 1No. 3-unit Classroom Block at Sankore SDA |
|  |  | Construction of 1No. 3-unit Classroom Block at Asampanaye with KVIP |
|  |  | Construction of 1No. 3-unit Classroom Block at Noberkaw DA |
|  |  | Construction of 1No. 6unit classroom Block with ancillary facilities at Kukuom Agric SHS |
|  |  | Construction of 1No. 6unit classroom Block at Anwiam |

BUDGET SUB-PROGRAMME SUMMARY

PROGRAMME3: SOCIAL SERVICES DELIVERY

SUB-PROGRAMME 3.2: Health Delivery

- Budget Sub-Programme Objective

- To achieve a healthy population that can contribute to socio-economic development of the district and Ghana as a whole.

- Budget Sub-Programme Description

This would be carried out through provision and prudently managing comprehensive and accessible health services with special emphasis on primary health care at the district, sub-district and community levels in accordance with national health policies. The sub-programme also formulate, plan and implement district health policies within the framework of national health policies and guidelines provided by the Minister of Health. The sub-programme seeks to:

- Ensure the construction and rehabilitation of clinics and health centres or facilities;

- Assist in the operation and maintenance of all health facilities under the jurisdiction of the district;

- Undertake health education and family immunization and nutrition programmes;

- Coordinate works of health centres or posts or community based health workers;

- Promote and encourage good health, sanitation and personal hygiene;

- Facilitate diseases control and prevention;

- Discipline, post and transfer health personnel within the district.

- Facilitate activities relating to mass immunization and screening for diseases treatment in the district.

- Facilitate and assist in regular inspection of the district for detection of nuisance of any condition likely to be offensive or injurious to human health;

- Establish, install, build and control institutional/public latrines, lavatories, urinals and wash places and licensing of persons who are to build and operate;

- Establish, maintain and carry out services for the removal and treatment of liquid waste;

- Establish, maintain and carry out the removal and disposal of refuse, filth and carcasses of dead animals from any public place;

- Assist in the disposal of dead bodies found in the district.

- Regulate any trade or business which may be harmful or injurious to public health or a source of danger to the public or which otherwise is in the public interest to regulate;

- Provide for the inspection of meat, fish, vegetables and other foodstuff and liquids of whatever kind or nature, whether intended for sale or not and to seize, destroy and otherwise deal with such foodstuff or liquids as are unfit for human consumption;

- Provide, maintain, supervise and control slaughter houses and pounds and all such matters and things as may be necessary for the convenient use of such slaughter houses;

- Advise on the prevention of the spreading and extermination of tsetse fly, mosquitoes, rats, bugs and other vermin in the district; and

- Advise on the establishment and maintenance of cemeteries and crematoria.

The units of the organization in undertaking this sub-programme include the Environmental Health Unit. Funds to undertake the sub-programme include GoG, DACF, DDF, Community members, development partners and departments are the beneficiaries of this sub-programme. The District Health Directorate in collaboration with other departments and donors would be responsible for this sub-programme. The department has staff strength of 142 officers. They  comprise of 47 Enrolled nurses, 46 Community Health Nurses, 7 Diploma Nurses, 11 Midwives, a Physician Assistant, and a Medical Assistant;  an Accountant and 2 Account officers; a Pharmacy Technician, 4 Administrators, 9 Disease Control Officers; a Health information officer, a Human Resource Officer, a Nutrition Officer, 2 Typists, 3 Health Assistants, 3 Orderlies, and 2 Watchmen.  The environmental health Unit has a total staff of 29 comprising 1Senior Environment Health officer,2 Chief Environmental Health Assistants , 1Principal Environment Health officer,1 Environment Health officer,  9Environmental Health Assistants Officers, 9 Sanitary Labourers,  5 Conservancy Labourers and 1 Refuse Labourer.

Challenges in executing the sub-programme include:

- Donor polices are sometimes challenging

- Low funding for infrastructure development

- Limited office and staff accommodation and those available are dilapidated

- Deplorable state of the District Health Directorate.

- Low sponsorship to health personnel to return to the district and work

- Inequitable distribution of health personnel (doctor, nurses)

- Delays in re-imbursement of funds (NHIS) to health centres to function effectively

- Common fund disbursement is silent as to a percentage of the DACF that should be committed to environment health and sanitation issues

- Lack of machinery for sanitation management (Pay-loader for refuse evacuation, septic-tank-emptier for liquid waste management)

- Lack of sanitary land-fill sites

- Lack of liquid waste treatment plants (waste stabilisation pond)

- Inadequate means of transport for execution and monitoring of health activities.

- Insufficient sanitary logistics.

- Lack of motorbikes for monitoring.

- Budget Sub-Programme Results Statement

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-programme. The past data indicates actual performance whilst the projections are the District’s estimate of future performance

| Main Outputs | Output Indicator | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2019 | 2020 | Budget Year 2021 | Indicative Year 2022 | Indicative Year 2023 | Indicative Year 2024 |
| Access to health service delivery improved | Number of functional Health centres constructed | - | 1 | 1 | 3 | 4 | 4 |
|  | No. of nurses quarters constructed/renovated | - | 1 | 3 | 2 | 2 | 2 |
| Increased education to communities on good living | Number of communities sensitised | - | 5 | 6 | 6 | 6 | 6 |
| Reduced incidence of domestic Violence, child protection, rural-urban migration, child labour | Number of communities sensitised | 4 | 6 | 6 | 6 | 6 | 6 |
| Improved Sanitation | No. of communities declared ODF basic | 5 | 4 | 6 | 6 | 6 | 6 |
|  | No. of communities declared ODF proper | 6 | 5 | 6 | 6 | 6 | 6 |
|  | No. of sanitary offenders prosecuted | 4 | - | 10 | 10 | 10 | 10 |
|  | No. of sanitation campaigns organised | 3 | 1 | 4 | 4 | 4 | 4 |
| Food venders medically screened and licenced | No. of venders screened and licenced | 724 | - | 758 | 900 | 1000 | 1000 |
| Stray animals arrested | No. of animals | 15 | 45 | 25 | 30 | 40 | 50 |
| Sanitation campaigns organised | No. of campaigns | 3 | 10 | 4 | 4 | 4 | 4 |

- Budget Sub-Programme Operations and Projects

The table lists the main Operations and projects to be undertaken by the sub-programme.

| Operations |  | Projects |
| --- | --- | --- |
| Support for National Immunization Day (NID) |  | Completion of Male & Female Ward at Kukuom |
| Malaria prevention (Roll back Malaria) activities |  | Completion of Health Administration Block at Kukuom |
| Support District Response Initiative (DRI) on HIV & AIDS |  | Construction of CHPS Compound at Asibrem |
| Facilitate the formation of WATSAN groups |  | Construction of 1No. CHPs Compound at Adwumamu |
| Institutional Latrines maintenance and Liquid waste management |  | Extension of Male Hostel with 3No. Teacher’s Quarters at Kwapong NTC |
| Support the repairs of broken down boreholes in communities |  | Construction of CHPS Compound at Weijakrom |
| Assist households to construct 250 household Latrines |  | Construction of 1No. Maternity Block at Kwapong |
| Sensitize 100 selected communities on dangers of open defecations (CLTS) |  | Construction of 1No. 4unit Nurses Quarters at Naketey |
| Development and Management of Waste Landfill Sites |  |  |
| Institute monthly and quarterly clean up exercises in all five sub-districts and communities |  |  |
| Refuse collection and disposal (solid waste management) |  |  |

BUDGET SUB-PROGRAMME SUMMARY

PROGRAMME3: SOCIAL SERVICES DELIVERY

SUB-PROGRAMME 3.3: Social Welfare and Community Development

- Budget Sub-Programme Objective

- Empower communities to shape their future by utilisation of their skills and resources to improve their standard of living.

- To integrate the vulnerable, Persons with Disability, the excluded and Disadvantaged into the mainstream of society.

- To reduce extreme poverty and enhance the potential of the poor to contribute to National Development.

- To achieve the overall social, economic and cultural re-integration of older persons to enable them to participate in national development in security and dignity.

- To protect and promote the right of children against harm and abuse

- Budget Sub-Programme Description

The sub-programme seeks to improve community’s well-being through utilization of their skills and resources and promoting social development with equity for the disadvantaged, the vulnerable, persons with disabilities and excluded. The department consists of two units; they are the Community Development Unit and Social Welfare Unit.

The community development unit under the department assist to organize community development programmes to improve and enrich rural life through:

- Literacy and adult education classes;

- Voluntary contribution and communal labour for the provision of facilities and services such as water, schools, library, community centres and public places of convenience or;

- Teaching deprived or rural women in home management and child care.

Units under the organization carrying out the sub-programme are the Social Welfare Unit and Community Development Unit. The public including the rural populace are the main beneficiaries of services rendered by this sub-programme.

The Social Welfare unit performs the functions of juvenile justice administration, supervision and administration of Orphanages and Children Homes and support to extremely poor households. The unit also supervises standards and early childhood development centres as well as persons with disabilities, shelter for the lost and abused children and destitute.

Funds sources for this sub-programme include GoG, IGF and DACF. A total of 5officers would be carrying out this sub-programme comprising of 2Community Development Officers, 1Social Development Officer, and 2Mass Education Officers.

Major challenges of the sub-programme include Lack of motorbikes to field officers to reach to the grassroots level for development programmes; delay in release of funds; inadequate office space; inadequate office facilities (computers, printers, furniture etc.)

- Budget Sub-Programme Results Statement

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-programme. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.

| Main Outputs | Output Indicator | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2019 | 2020 | Budget Year 2021 | Indicative Year 2022 | Indicative Year 2023 | Indicative Year 2024 |
| Enrolment more people into LEAP | No. of people enrolled | 214 | 214 | 214 | 230 | 230 | 230 |
| Empower 1,000 community members through self-initiated programme | No. of people mobilized | 47 | 44 | 1000 | 1000 | 1000 | 1000 |
| Organize 30 women groups for local food processing | No. of Groups organized | 4 | 15 | 30 | 30 | 30 | 30 |
| Financial Support to PWDs | No. of PWDs supported financially | 210 | 152 | 500 | 500 | 700 | 850 |
| Reduce the in-take of non-iodate salt | Number of women sensitized | 50 | 55 | 100 | 100 | 200 | 200 |
| Increase the livelihood of community members | Number of people trained on agro-processing (Milling and fortification) | 60 | 50 | 100 | 100 | 100 | 150 |
| Increase education to communities on good living | Number of communities sensitised | 6 | 8 | 12 | 50 | 55 | 60 |
| Reduce incidence of domestic Violence, child protection, rural-urban migration, child labour | Number of communities sensitised | 12 | 10 | 20 | 20 | 30 | 30 |
| Monitor activities of early childhood development centre (conduciveness of the environment, | Number of childhood development centres monitored | 5 | 5 | 15 | 25 | 30 | 30 |
| Attendants in day care trained on psychology of children and how to give children a better start-off | Number of day care centres trained | 10 | 8 | 20 | 30 | 35 | 45 |

- Budget Sub-Programme Operations and Projects

The table lists the main Operations and projects to be undertaken by the sub-programme

| Operations |  | Projects |
| --- | --- | --- |
| Training of groups into income generating activities (Salt iodisation, agro processing, retailing, farming/rearing, |  |  |
| Home visit to educate people on good living – food, child care, family care, clothing, water, hygiene and sanitation |  |  |
| Training of groups on business development, group dynamics, book keeping, |  |  |
| Facilitate adult education groups; child protection ( teenage marriage, child trafficking, child migration, child labour, |  |  |
| Community durbar to sensitize people on Domestic Violence, child protection, rural-urban migration, child labour. |  |  |
| Mainstreaming gender in developmental activities |  |  |
| Support to community volunteer groups |  |  |
| SOCIAL WELFARE |  |  |
| Support to PWDs |  |  |
| Monitor activities of all early childhood centers |  |  |
| Train untrained Day Care attendants in the District |  |  |
| Prepare SER for family tribunal in Bole |  |  |
| Organization of child labour |  |  |
| Formation of child rights committee |  |  |
| Provide homes for the homeless abandoned, or orphaned children |  |  |
| Attend court sittings at Kukuom and prepare SERs for all juvenile cases |  |  |
| Support LEAP programme in the district |  |  |
| Monitor activities of NGOs and submit reports to District Assembly |  |  |
| Undertake hospital service |  |  |
| GENDER |  |  |
| Promote equal participation of women as agents of change to achieve gender equality district wide |  |  |
| Mainstream gender in all public sector departments in the District |  |  |
| Build capacity of women groups in income generating activities district wide |  |  |
| Promote women participation in Farmer Based Organizations (FBO) and women groups district wide |  |  |
| Communicate and campaign, gender disparities in domestic work allocation within households and to reduced child work and child labour by supporting household generating activities district wide |  |  |

BUDGET PROGRAMME SUMMARY

## PROGRAMME 4: ECONOMIC DEVELOPMENT

- Budget Programme Objectives.

- Create an entrepreneurial society through the promotion and growth of micro and small enterprises (MSEs).

- To improve agricultural productivity through modernization along a value chain in a sustainable manner

- Budget Programme Description

The economic development programme aims at provide enabling environment for Trade, Tourism and industrial development in the District. It also seeks to facilitate the modernization of agriculture to achieve self-sufficiency in food security in the District. The sub-programmes under the Economic Development programme include Trade, Tourism and Industrial Development and Agriculture Development.

Trade, Industry and Tourism sub programme under the guidance of the Assembly deal with issues related to trade, cottage industry and tourism in the district. The sub-programme seeks to:

- Facilitate the promotion and development of small scale industries in the District;

- Advise on the provision of credit for micro, small-scale and medium scale enterprises;

- Promote the formation of associations, co-operative groups and other organizations which are beneficial to the development of small-scale industries;

- Assist in offering business and trading advisory information services;

- Facilitate the promotion of tourism in the district;

- Assist to identify, undertake studies and document tourism sites in the district.

- The Agriculture Development sub-programme seeks to:

- Provide agricultural extension services in the areas of natural resources management, and rural infrastructural and small scale irrigation in the district;

- Promote soil and water conservation measures by the appropriate agricultural technology;

- Promote agro-forestry development to reduce the incidence of bush fires;

- Promote an effective and integrated water management

- Assist in developing early warning systems on animals diseases and other related matters to animal production;

- Facilitate and encourage vaccination and immunization of livestock and control of animal diseases;

- Encourage crop development through nursery propagation;

- Develop, rehabilitate and maintain small scale irrigation schemes;

- Promote agro-processing and storage.

Twelve staff from the Department of Agriculture Development will deliver the programme.

BUDGET SUB-PROGRAMME SUMMARY

PROGRAMME4: ECONOMIC DEVELOPMENT

SUB-PROGRAMME 4.1 Trade, Tourism and Industrial development

- Budget Sub-Programme Objective

- Expand opportunities for job creation and improve efficiency and competitiveness of Micro, Small and Medium Enterprises (MSMEs).

- Promote sustainable tourism to preserve historical, cultural and natural heritage and attract tourist.

- Budget Sub-Programme Description

The sub-programme seeks to improve the competitiveness of micro and small enterprises by facilitating the provision of development programmes and integrated support services. The National Board for Small Scale Industries / Business Advisory Centre (BAC) facilitates MSMEs access to Business development service though assisting entrepreneurs to increase their productivity, generate employment, and increase their income levels and contributing significantly towards the socio-economic development of the country. The clients are potential and practising entrepreneurs in growth oriented sectors in the district. Services delivered seek to promote on-farm and off-farm activities. These would include facilitating access to training and other business development services, provision of advisory, counselling and extension services, provision of business information to potential and existing entrepreneurs and promotion of business associations.

Other service to be delivered under the sub-programme include,

- support to the creation of business opportunities;

- provide opportunities for MSMEs to participate in all Public-Private Partnerships (PPPs) and local content arrangements;

- facilitate the establishment of Rural Technology Facilities (RTF)  in the District;

- Develop and market tourist sites, improve accessibility to key centres of population, production and tourist sites;

- promote local festivals in the district and;

- Provide incentives for private investors in hospitality and restaurant.

- The unit that will deliver this sub-programme is the District Assembly since the District does not have Business Advisory unit.

- Budget Sub-Programme Results Statement

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-programme. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.

| Main Outputs | Output Indicator | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2019 | 2020 | Budget Year 2021 | Indicative Year 2022 | Indicative Year 2023 | Indicative Year 2024 |
| Potential and existing entrepreneurs counselled | No. of potential and existing entrepreneurs counselled | 200 | 155 | 250 | 300 | 350 | 400 |
| Potential and existing entrepreneurs trained | No. of individuals trained on boutique tie and dye making | 65 | 55 | 70 | 75 | 80 | 85 |
|  | No. of individuals trained on soup making | 32 | 25 | 40 | 40 | 45 | 45 |
|  | No. of individuals trained on bread baking | - | 16 | 20 | 25 | 25 | 35 |
| Access to credit by MSMEs facilitated | No. of MSMEs who had access to credit | 7 | 16 | 60 | 70 | 80 | 80 |
|  | No. of new businesses established | 20 | 15 | 30 | 35 | 40 | 42 |
| MSE access to participate in trade fairs | No. of SMEs supported to attend trade fairs | - | 1 | 5 | 10 | 12 | 20 |

- Budget Sub-Programme Operations and Projects

The table lists the main Operations and projects to be undertaken by the sub-programme

| Operations |  | Projects |
| --- | --- | --- |
| Training of groups on Group Dynamics, Business Management and Counseling (counterpart support to Business Advisory Centre) |  | Supply of various Equipment and tools to SMEs with the District. |
| Business Forum/LED Activities |  | Construction of 1No. 10unit Lockable market Stores at Sankore |
| Sensitization of communities on Green Economy |  | Construction of Abattoir at Kukuom |

BUDGET SUB-PROGRAMME SUMMARY

PROGRAMME4: ECONOMIC DEVELOPMENT

SUB-PROGRAMME 4.2: Agricultural Development

- Budget Sub-Programme Objective

To modernise agriculture through economic structural transformation evidenced in food security, employment and reduced poverty.

- Budget Sub-Programme Description

The Agricultural Development sub-programme seeks to promote thriving agriculture through research and efficient extension services to farmers, marketers and SMEs. Major services carried out under this sub-programme include

- Demonstrations and research to increase yields of crops and animals and persuade farmers to adopt technologies;

- Introduction of income generation livelihoods such as productive agricultural ventures (cocoa growing activities along the value chain that are income generating) and other alternative livelihoods;

- Promote efficient marketing and adding value to produce;

- Proper management of the environment through soil and water conservation, minimising bush fire, climate change hazards;

- Improve effectiveness and efficiency of technology delivery to farmers; and

- Networking and strengthening leakages between the department and other development partners.

The District Department of Agriculture will be responsible for the delivery of this sub – programme. The department has four units consisting of the following,

- Extension unit, which is in charge of extension of Agricultural Technologies and Information to the farmers and ensuring that these technologies are adopted.

- Women in Agriculture Development (WIAD) unit - responsible for mainstreaming gender issues in agriculture.

- Crop Unit - ensures that good agricultural practices in relation to crop production are adopted and to minimise post-harvest loses.

- Animal production and Health Unit - ensures that good animal husbandry practices and health are adopted.

The Department consist of 12 officers, 2 administrative officer, 4Agriculture officers, 1production officer, 4Technical Officers, 1 Typist, 1 one Driver.

In delivering the sub-programme, funds would be sourced from GoG, DACF, Donor (CIDA) development partners and departments are the beneficiaries of this sub – programme.

Key challenges include

- Inadequate of motorbikes and vehicles for field staff

- Inadequate accommodation for staff in the operational areas

- Inadequate agriculture extension agents (AEAs) and

- Inadequate funding.

- Inadequate District Agric Office space

- Budget Sub-Programme Results Statement

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-programme. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.

| Main Outputs | Output Indicator | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2019 | 2020 | Budget Year 2021 | Indicative Year 2022 | Indicative Year 2023 | Indicative Year 2024 |
| Capacity on extension delivery of FBOs build | No. of FBOs | 20 | 15 | 30 | 35 | 45 | 45 |
| Capacity of Community Animal Health Workers built | No. of CAHW | 5 | 3 | 6 | 7 | 8 | 9 |
| Provision of small irrigation schemes | No. of dug-outs constructed | - | 1 | - | 10 | 17 | 10 |
| Gender mainstreaming Activities | No. of Women Streamed | 131 | 56 | 155 | 200 | 300 | 300 |
|  | No. of Male Streamed | 90 | 27 | 134 | 130 | 150 | 200 |

- Budget Sub-Programme Operations and Projects

The table lists the main Operations and projects to be undertaken by the sub-programme.

| Operations |  | Projects |
| --- | --- | --- |
| Conduct 1,897 farm and homes visits by AEAs, DAOs and DDA |  | Purchase and Supply of Improved and High yielding Palm Oil Seedlings. |
| Conduct demonstrations on improved varieties (maize, sorghum, cowpea, and rice, protein & mineral containing food, and Post-Harvest Managements |  | Purchase and Supply of various Agriculture Inputs. |
| Support to farmers especially the youth to put extra area of land under crop production |  |  |
| Promote the adoption of grading and standardization system for yam, shea nut and tomatoes district wide |  |  |
| Train 15 AEAs on post-harvest technologies |  |  |
| Form and put in place 7 functional Water Users Associations |  |  |
| Sensitize FBOs and out-growers on extension delivery and value chain concept |  |  |
| Capacity of 5nursery operators and support them expand and improve the quality of seedling |  |  |
| Organize campaign on prophylactic treatment of livestock and poultry |  |  |
| Organize mass vaccination against schedule diseases (anthrax, rabbis, blackleg, new castle, coccidiosis, ppr, Africa Swine etc.) |  |  |
| Facilitate the acquisition of improved breeds by livestock and poultry farmers district wide |  |  |

BUDGET PROGRAMME SUMMARY

## PROGRAMME 5: ENVIRONMENTAL AND SANITATION MANAGEMENT

- Budget Programme Objectives

- To plan and implement programmes to prevent and/or mitigate disaster in the District within the framework of national policies

- Budget Programme Description

The programme will deliver the following major services:

- Organize public disaster education campaign programmes to: create and sustain awareness of hazards of disaster; and emphasize the role of the individual in the prevention of disaster;

- Education and training of volunteers to fight fires including bush fires, or take measures to manage the after effects of natural disasters;

- Assist in post-emergency rehabilitation and reconstruction efforts in the event of disasters;

- In consultation and collaboration with appropriate agencies, identify disaster zones and take necessary steps to; educate people within the areas, and prevent development activities which may give rise to disasters in the area;

- Post disaster assessment to determine the extent of damage and needs of the disaster area;

- Co-ordinate the receiving, management and supervision of the distribution of relief items in the district;

- Inspect and offer technical advice on the importance of fire extinguishers;

- The Disaster Management and Prevention Department will be responsible in executing the programme.

BUDGET SUB-PROGRAMME SUMMARY

PROGRAMME5: ENVIRONMENTAL AND SANITATION MANAGEMENT

SUB-PROGRAMME 5.1 Disaster prevention and Management

- Budget Sub-Programme Objective

- To enhance the capacity of society to prevent and manage disasters

- To improve the livelihood of the poor and vulnerable in rural communities through effective disaster management, social mobilisation and income generation.

- Budget Sub-Programme Description

The sub-programme seeks to promote disaster risk reduction as well as climate change risk management. It is also to strengthen Disaster Prevention and Respond mechanisms of the District. The sub-programme is delivered through public campaigns and sensitisations; assisting in post-emergency rehabilitation and reconstruction of efforts; provision of first line response in times of disaster and; formation and training of community-based disaster volunteers. The Disaster Management and Prevention Department is responsible for executing the sub-programme. The larger public at the community levels are the beneficiaries of this sub-programme. Funds will be sourced from IGF, DACF and Central Government supports. Challenges which confront the delivery of this sub-programme are lack of adequate funding, low and unattractive remunerations, and unattractive conditions of work. In all, 16 NADMO officers will carry out the sub-programme.

- Budget Sub-Programme Results Statement

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-programme. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.

| Main Outputs | Output Indicator | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2019 | 2020 | Budget Year 2021 | Indicative Year 2022 | Indicative Year 2023 | Indicative Year 2024 |
| Support to disaster victims | No. of Individuals supported | 5 | - | 5 | 10 | 15 | 20 |
| Training for Disaster volunteers organized | No. of volunteers trained | 30 | 25 | 40 | 45 | 50 | 65 |
| Campaigns on disaster prevention organised | No. of campaigns organised | 3 | 2 | 5 | 8 | 10 | 10 |

- Budget Sub-Programme Operations and Projects

The table lists the main Operations and projects to be undertaken by the sub-programme.

| Operations |  | Projects |
| --- | --- | --- |
| Organize an 8 days field training for 80 Disaster volunteers groups |  |  |
| Train 12 NADMO staffs for effective service delivery |  |  |
| Hold quarterly disaster committee meeting annually |  |  |
| Educating people especially people farming closer to the White Volta to plant only short yielding crops |  |  |
| Educate people to build their houses not on waterways but rather high lands identify flood prone areas. Identify safe havens |  |  |
| Formation anti-bushfire volunteer |  |  |
| Provided early warning system/ signals |  |  |
| Bush – fire campaign |  |  |