ASUNAFO SOUTH DISTRICT ASSEMBLY

[image: image1.png]



APPROVED
COMPOSITE ANNUAL ACTION PLAN
FOR 2021
OCTOBER, 2020
STATEMENT OF APPROVAL OF 2021 ANNUAL ACTION PLAN

The General Assembly of the Asunafo South District Assembly at meeting held on 29TH October, 2020 deliberated on the 2021 Composite Annual Action Plan and subsequently gave approval for it 1mplementation.

Date:…………………………………. 
…………………………………………

HON. OSEI BONSU SNR
(DISTRICT CHIEF EXECUTIVE)

Date:………………………………….

………………………………………

ASAMOAH DAMOAH







      (DISTRICT CO-ORD DIRECTOR)

Date:………………………………….

…………………………………………

HON. 







               


  (PRESIDING MEMBER)

1.0 INTRODUCTION

This Annual Action Plan was extracted from the District Medium Term Development Plan (2018-2021) prepared by the Assembly to accelerate the development process of the District with guidelines from the National Development Planning Commission. Aside the guidelines, the Ghana Shared Growth and Development Agenda II, 2018-2021 formed the main basis for the preparation of the Assemblies Development plan. It contains programmes and projects that the Assembly together with its department has outlined to execute or undertake for the year 2021.

1.1 Size and Location

The Asunafo South District, one of the six districts of the Ahafo Region were carved out from the Asunafo District Assembly after it was split into Asunafo North and South in 2008 with Kukuom as the capital. The district has an estimated land size of about 3737 kilometers square (1442.8 square miles) and is located at the southern part of the Ahafo Region with the eastern frontier forming the geographical and administrative boundary separating the Ahafo Region from the Ashanti Region.

The district shares common boarders with the Asunafo North District to the north and the Juaboso District to the South-West. Other adjoining Districts are the Sefwi-Wiaso District to the South-East, and Atwima Mponua District to the East

1.2 KEY DEVELOPMENT ISSUES

Below are some of the key development issues confronting the District;
· Poor marketing systems

· Inadequate development, investment in processing and value addition

· Poor farm-level practices

· High unemployment among the youth.

· Inadequate seed capital for businesses to grow

· Poor compensation payment to affected persons

· Low level of husbandry practices
· Poor quality of education at all levels

· High number of untrained teachers at the basic level

· Gaps in physical access to quality health care

· Increasing morbidity, mortality and disability due to communicable, non-communicable and emerging diseases

· High incidence of HIV and AIDS among young persons

· Increasing demand for household water supply

· Inadequate maintenance of facilities

· Youth unemployment and underemployment among rural and urban youth

· Poor quality and inadequate road transport network

1.3 COMMUNITY NEEDS AND ASPIRATIONS

Prominent among the needs and aspirations outlined through the various levels of dialogue were the following:

· Extension of electricity to newly developed areas

· Provision of street light.

· Employment opportunities

· Establishment of effective waste management system.

· Provision of proper drainage system.

· Rehabilitation of town roads and feeder roads.

· Provision of adequate school infrastructure

· Provision of adequate market infrastructure

· Extension of water.

· Provision of adequate public toilet facilities.

· Provision of health facility.

· Intensification of Agric Extension Service.

· Provision of micro- credit scheme to boost economic activities.

1.2.4 ADOPTED DEVELOPMENT OBJECTIVES IN DMTDP 2018-2021

· Promote a demand-driven approach to agricultural development
· Enhance the application of science, technology and innovation

· Enhance inclusive and equitable access to, and participation in quality education at all levels

· Ensure affordable, equitable, easily accessible and Universal Health Coverage (UHC)

· Ensure the reduction of new HIV and AIDS/STIs infections, especially the among vulnerable groups

· Improve access to safe and reliable water supply services for all

· Enhance access to improved and reliable environmental sanitation services

· Promote effective participation of the youth in socioeconomic development

· Improve efficiency and effectiveness of road transport infrastructure and services

· Improve decentralised planning

· Strengthen fiscal decentralization
2.0 PLAN IMPLEMENTATION

A total of 143 activities have been outlined for implementation in 2021. The activities will be implementation with the support of Departments of the Assembly, Agencies and Non- governmental Organizations who are working within the jurisdiction of the District. The Departments, Agencies and NGO’s are expected to report quarterly on the status of their respective plans to the DPCU to collate and harmonize a composite report on the implementation of the District Annual Action Plan, 2021. Again, the DPCU will hold quarterly meetings to discuss on the report and finally submit it to the National Development Planning Commission and Regional Co-ordination Council respectively.

3.0 SOURCES OF FUNDS FOR THE IMPLEMENTATION OF THE PLAN

The funds are expected from IGF, DACF, GOG, Ground Rent, and District Development Facility, Development Partners and among others.  It is important to note that, since some departments are not yet fully integrated and operational; some programmes may not be budgeted for in the Assembly’s supplementary budget and annual estimates.

4.0 REVENUE IMPROVEMENT ACTION PLAN

A Revenue Improvement Action Plan has been prepared to effectively mobilize local resources for the implementation of the plan. The plan has identified key activities that will be carried out and these have the potential to improve the Assembly’s Internally Generated Funds. It is expected that when all the activities are implemented, other things being equal the Assembly internally generated revenue will increase averagely by 20 % over the 2020 figure.

Asunafo South District Assembly
Approved Composite Annual Action Plan, 2021
	

	Programmes and Sub-programmes
	Activities (Operations)
	Location
	Output Indicators
	Quarterly Time schedule
	Indicative Budget
	Implementing Agencies

	
	
	
	
	1st
	2nd
	3rd
	4th
	GoG
	IGF
	Donor
	Lead
	Collaborating

	Management and Administration

Planning, Budgeting and Coordination
	1. undertake quarterly auditing of assembly finances
	Kukuom
	Internal audit Unit strengthened
	x
	x
	x
	x
	-
	15,000


	-
	IAU
	EA, AS

	
	2. Undertake auditing of WSMT
	Kukuom, Sankore
	WSMT audited
	x
	x
	
	
	-
	5,000.00
	-
	I.A
	WSMT

	Economic development

Trade, Tourism and industrial Development


	3. Organize training workshop for SMEs on proper book keeping practices
	District wide
	Sizable number of employments has been created
	x
	x
	x
	x
	-
	-
	98,635.00
	BAC
	REP, DA

NBSSI

JICA

Client

	
	4. Identify and train 20 women in tie and dye making
	District wide
	Sizable number of employments has been created
	x
	x
	x
	x
	2,000.00
	-
	83,000.00
	BAC
	IFAD

AFDB

REP

DA

NBSSI

PFI

JICA

Client

	
	5.  Provision of financial support to 20 women in tie and dye making
	District wide
	Developed local economy
	x
	x
	
	
	30,000.00
	-
	800,000.00
	BAC
	IFAD

AFDB

REP, DA

NBSSI

PFI, JICA

Client

	
	6.  Procurement and maintenance of office equipment and logistics
	Kukuom
	Office equipment procured and maintained
	x
	x
	x
	x
	60,000.00

CF
	
	-
	CA
	DPCU

	
	7.  Identify and train 10 women in soap making
	Kukuom 
	1No. Skill Development Centres constructed
	x
	x
	x
	x
	2,000.00
	-
	
	BAC
	DWD,

	
	8.  Provision of financial support to 10 women in soap making
	Kukuom
	1No. Skill Development Centres constructed


	x
	x
	x
	x
	10,000.00
	-
	
	BAC
	DWD,

	
	9. Completion of 3no. Market facilities
	Sankore Kwapong and Kukuom-
	3no. market facility completed
	x
	x
	x
	x
	66,000.00
	
	
	Works, EHU
	Planning

	
	10. Construction of 1No police station
	Abuom
	Police station constructed
	x
	x
	x
	x
	426,105.00
	
	426,105.00
	Works
	GPS

	
	11. Identify tourism potentials in the district
	District wide
	Number of tourist site identified
	x
	x
	x
	x
	5,500.00
	
	
	Planning, DTC
	EHU

	
	12.  Inspection of Hotels and guest houses in the district
	District wide
	Number of hotels and guest houses inspected
	X
	x
	X
	x
	5,000.00
	
	
	EHU; planning
	Fire service, EPA

	
	13. Construction of 1No 6-unit Lockable market stores
	Kukuom
	1no. 6-unit Lockable market stores constructed
	x
	x
	x
	x
	75,000.00
	
	
	Works
	EHU

	
	14. Construction of Abattoir
	Kukuom
	Abattoir constructed
	x
	x
	x
	x
	20,000.00
	
	
	Works
	EHU

	Agricultural Development


	15. Train women on the processing of cassava
	District Wide
	Increased coverage of flagship agriculture

Programme of “Planting for Food and Jobs”:
	x
	x
	x
	x
	
	-
	3,700.00


	DOA
	MAG

	
	16. Provision of technical support to farmers
	District Wide
	Average weekly/daily food prices established
	x
	x
	x
	x
	
	-
	2,400.00


	DOA
	MAG

	
	17. Supply of oil palm seedlings to farmers.
	District Wide
	Realistic, costed annual plans for District Department of Agriculture developed and reported on annually
	x
	x
	x
	x
	
	-
	3,450.00


	DOA
	MAG

	
	18. Conduct research into high productive seedlings
	District Wide
	Improved incentive for and reduced barriers to Private Sector Investment along all aspects of commodity value chain
	x
	x
	x
	x
	
	-
	2,000.00


	DOA
	MAG

	
	19. Train farmers on modern methods of farming
	District Wide
	Increased adoption of productivity -enhancing technologies
	x
	x
	x
	x
	33,196
	-
	20,600.00

(MAG)
	DOA
	MAG

	
	20. 20. Embark on routine visit to demonstration farms
	District Wide
	Increased adoption of productivity -enhancing technologies
	x
	x
	x
	x
	5000
	-
	3,900.00


	DOA
	MAG

	
	21. Purchase of farming tools
	District wide
	
	
	
	
	
	22,000.00
	
	
	DOA
	MAG

	
	22. Create public awareness on bushfires
	District Wide
	Increased adoption of productivity -enhancing technologies
	x
	x
	x
	x
	1,5000.00
	-
	32,587.26


	DOA
	MAG, NADMO

	
	23. Train fire volunteers in the communities
	District Wide
	Increased adoption of productivity -enhancing technologies
	
	
	
	x
	80,000.00
	-
	-
	DOA
	MAG, DA, RDoA

	
	24. Sensitize communities on dangers of environmental pollution
	District Wide
	Increased adoption of productivity -enhancing technologies
	x
	x
	x
	x
	1,500.00
	-
	2,400.00
	DOA
	MAG

	
	25. Carry out Tree planting exercise
	District Wide
	% reduction in post-harvest losses along the maize value chain
	x
	
	x
	
	5,000.00
	
	3,250.00
	DOA
	MAG, NADMO, FC

	
	Subtotal
	
	
	
	
	
	
	863,301
	20,000.00
	1,482,027.26

	
	

	Development Dimension: Social Development

	
	26. Construct 1 No. 6 Unit classroom block, Office & Store by 2021
	Kukuom Methodist Primary
	Classroom blocks constructed.
	x
	x
	x
	x
	1,400,000.00
	
	
	GES
	DA

	
	27. Construction of 1No. 3-Unit Classroom block with office, staff room, 3 seater KVIP, Urinal and supply of Furniture at Kukuom Girl Model School 
	Kukuom Girl Model School
	Classroom blocks with office, staff room, 3 seater KVIP, Urinal and supply of Furniture constructed 
	x
	x
	x
	x
	
	
	200,000.00
	GES
	DA

	
	28. Construction of 1No. 3-Unit Classroom block with office, staff room, 3 seater KVIP, Urinal and supply of Furniture at Kukuom SDA J.H.S
	Kukuom SDA J.H.S
	Classroom blocks with office, staff room, 3 seater KVIP, Urinal and supply of Furniture  constructed  
	x
	x
	x
	x
	
	
	200,000.00
	GES
	DA

	
	29. Construct 1 No. 6 Unit classroom block, Office & Store by 2021
	Kukuom Presby
	Classroom blocks constructed.
	x
	x
	x
	x
	1,400,000.00
	
	
	GES
	DA

	
	30. Completion 1 No. Teacher’s Quarters with 2No.  Toilet & bathroom
	Naketey
	Teachers’ quarters completed
	x
	x
	x
	x
	4,413.50
	
	
	GES
	DA

	
	31. Construction of 1 no. Teacher’s Quarters
	Kwapong
	Teachers’ quarters completed
	x
	x
	x
	x
	50,113.50
	
	
	GES
	DA

	
	32. Completion of 1No 3-unit classroom block
	Motopeneso
	Classroom blocks completed.
	x
	x
	x
	x
	15,654.70
	
	
	GES
	DA

	
	33. Completion of 1No. 3-- unit classroom block


	Kukuom

Anglican KG
	Classroom blocks completed.
	x
	x
	x
	x
	9,521.45
	
	
	GES
	DA

	
	34. Completion of 1No. 3-- unit classroom block with auxiliary facilities
	Abuom DA
	Classroom blocks completed.
	x
	x
	x
	x
	98,521.45
	
	
	GES
	DA

	
	35. Completion of 3-unit classroom block at  Siiso
	Siiso
	Classroom blocks completed.
	x
	x
	x
	x
	77,524.15
	-
	-
	GES
	DA

	
	36. Completion of teachers quarters
	Opongkrom
	Teachers’ quarters blocks completed.
	x
	x
	x
	x
	98,521.45
	
	
	GES
	DA

	
	37. Completion of 3-unit classroom block
	Abonyereso
	Classroom blocks completed.
	x
	x
	x
	x
	77,524.15
	-
	-
	GES
	DA

	
	38. Construction of 1No. 3 Unit Classroom Block
	Sankore ShS
	Classroom blocks completed.
	
	
	
	
	165,290.83
	
	
	DED
	DWD, TA, Assembly Member

	
	39. Construction of 1No. 3 Unit Classroom Block
	Noberkaw DA
	Classroom blocks completed.
	
	
	
	
	165,290.83
	
	
	DED
	DWD, TA, Assembly Member

	
	40. Completion of 1No. 3 Unit Classroom Block with KVIP and Urinal
	Siiso Bowjiase
	Classroom blocks completed.
	
	
	
	
	164,660.75
	
	
	DED
	DWD, TA, Assembly Member
	

	
	41. Completion of 1No. 3 Unit Classroom Block with 4-seater KVIP and Urinal
	Asempaneye
	Classroom blocks completed.
	
	
	
	
	165,290.83
	
	
	DED
	DWD, TA, Assembly Member
	

	
	42. Construction of 1No. 3 Unit Classroom Block with KVIP and Urinal
	Sankore SDA
	
	
	
	
	
	182688.08
	
	
	DED
	DWD, TA, Assembly Member
	

	
	43. Sensitize people on concept and relevance of the District Assembly
	Area/Town council
	Number of sensitization programs held
	X
	X
	X
	X
	15,000.00
	
	
	HR, planning
	SMAID

	
	44. Provide scholarship and Bursaries support to students


	Kukuom
	Educational support provided
	X
	X
	x
	x
	30,000.00
	-
	-
	GES
	DA

	
	45. Support for DEOC activities
	Kukuom
	DEOC activities supported
	X
	X
	X
	x
	10,000.00
	
	
	GES
	DA

	
	46. Support towards sports and youth development
	District wide
	
	
	
	
	
	10,000.00
	
	
	DA
	

	
	47. Organise SPAM using NEA, SEA and BECE results.


	District Wide
	SPAM programme organised
	
	x
	
	
	2,000.00
	-
	1,050.00
	GES
	DA

	
	48. Conduct regular school inspection and disseminate reports in a timely manner
	All schools
	Regular school inspection conducted
	x
	x
	x
	x
	6,000.00
	-
	5,000.00
	GES
	DA

	
	49.  Monitor teacher absenteeism and sanction culprits
	All schools
	Teacher absenteeism monitored and culprits sanctioned
	X
	X
	X
	x
	7,000.00
	-
	9,000.00
	GES
	DA

	Social services delivery

Health delivery


	50. Completion of 1No. CHPS Compound by Dec., 2021
	Tetekwao,


	CHPS compound completed
	x
	x
	X
	x
	20,000.00
	-
	-
	GHS
	Health Department

	
	51. Completion of 1no. CHPS Compound by Dec., 2021
	Pafo
	CHPS compound completed
	x
	x
	X
	x
	20,000.00
	-
	-
	GHS
	Health Department

	
	52. Completion of 1no. CHPS Compound by Dec., 2021
	Weijakrom
	CHPS compound completed
	x
	x
	X
	x
	20,000.00
	-
	-
	GHS
	Health Department

	
	53. Completion and rehabilitation works on 1No. CHPS Compound
	Adwumam
	CHPS compound completed
	x
	x
	X
	x
	20,000.00
	-
	-
	GHS
	Health Department

	
	54. Construction of 1No. Administration Block at Kukuom Hospital
	Kukuom
	Admi block completed
	x
	x
	X
	x
	41,145.00
	-
	-
	GHS
	Health Department

	
	55. Completion of male and female ward
	Kukuom
	ward completed
	x
	x
	X
	x
	24,828.92
	-
	-
	GHS
	Health Department

	
	56. Construction of 1No. CHPS compound
	Asibrem
	CHPS compound constructed
	x
	x
	x
	x
	45,351.83
	62,847.00


	-
	GHS
	Health Department

	
	57. Construction of 1No.CHPS Compound
	Asarekrom
	CHPS compound constructed
	x
	x
	x
	x
	77,516.62
	10,000.00 
	-
	GHS
	Health Department

	
	58. Construction of 1No. 2-Unit Single room self-contain Nurses Quarters at Abuom
	Abuom
	Nurses’ quarters constructed
	x
	x
	x
	x
	89,940.20
	-
	-
	GHS
	Health Department

	
	59. Construction of Maternity Block
	Kwapong
	Maternity block constructed
	x
	x
	x
	x
	182,721.00
	-
	-
	GHS
	DA

	
	60. Emergency response to health-related issues
	District wide
	
	x
	x
	x
	x
	24,848.00
	
	
	GHS
	DA

	
	61. District Response Initiative, education, and sensitization on breast cancer, HIV & Malaria
	District wide
	Reduction in Malaria and HIV/AIDS awareness campaigns organised
	x
	x
	x
	x
	19,755
	-
	-
	GHS
	DA

	Infrastructure Delivery and Management


	62. Rehab and maintenance of 17No. Borehole
	District wide
	Funding for LMWS paid
	x
	x
	x
	x
	-
	10,000.00
	-
	CA
	SWN

DPO

	
	63. Drilling of 4No. Borehole and installation of Afridev hand pump
	District wide
	Number of boreholes drilled
	X
	X
	X
	x
	40,000
	
	
	Works, pln
	DHO

	
	64. Construction of mechanized borehole
	Siana, Asarekrom, Sikafrebogya,  Noberkaw,  Dantano
	Number of boreholes constructed
	X
	X
	X
	x
	100,000.00
	
	
	Works, planning
	DHO

	
	65. Installation of Hand pump at Akwasi-Mframa
	Akwasi-Mframa,
	Number of boreholes drilled and mechanized
	X
	X
	X
	X
	3,018.00
	
	
	Works, planning
	DHO

	
	66. Dislodging of 4 No. public toilets
	Sankore/ Kukuom
	4 No. public toilets dislodged
	X
	X
	X
	X
	3,715.00
	
	
	DHO
	DA

	
	67. Const. of 12-Seater KVIP
	Achiase
	KVIP constructed
	X
	X
	X
	x
	52,283.00
	
	
	EHU
	DA

	
	68. Screening of food vendors, butcher meat sellers, drinking bar operators
	District wide
	No of food venders screened
	x
	x
	x
	x
	-
	3,500.00
	-
	EHU
	DWD, DDHS

	
	69. Daily collection and disposal of refuse (SIP)
	District wide
	Daily refuse collected and disposed
	x
	X
	X
	x
	204,000

CF
	-
	-
	EHU
	CA

	
	70. Arrest of stray animals
	District wide
	Stray Animals Arrested
	X
	X
	X
	x
	2000.0
	
	
	EHU
	CA

	
	71. Construction of public pound
	Kukuom
	Public pound constructed
	X
	X
	X
	X
	2,500


	
	
	EHU
	CA

	
	72. Fumigation of sanitary site & public toilet
	District wide
	Sanitary site & public toilet fumigated
	x
	X
	X
	x
	50,000


	-
	-
	EHU
	CA

	
	73. Intensify routine inspection of projects, programmes and hygiene education, and proper maintenance culture


	District
	Number of projects inspected
	x
	x
	x
	x
	-
	3000.00


	-
	EHU
	Sub-district heads

	
	74. Procurement of Sanitation and office materials
	District Wide
	WSMT and water facilities monitored
	x
	x
	
	
	5000.00


	-
	-
	DWST
	DPCU

	
	75. Sanitation legislation enforcement
	District Wide
	
	x
	x
	x
	x
	
	
	
	DEHU
	DA

	
	76. Office cleaning
	Kukuom
	Healthy and clean environment
	x
	x
	x
	x
	
	2000.00


	
	DEHU
	DA

	
	77. Planting of ornamental plants at the forecourt of the new assembly block
	Kukuom
	To improve aesthetic nature of the environment
	x
	
	
	
	-
	
	
	DEHU
	DA

	
	78. Evacuate refuse dump/ pushing and levelling of 2 final disposal sites
	Sankore/ Kukuom
	Refuse dump evacuated
	X
	X
	X
	x
	60,000.00
	
	
	DEHU
	DA

	SOCIAL SERVICES DELIVERY

(Social Welfare and Community Development)


	79. Education on Disability Act for person with disabilities in District (PWDs) in four zones


	Kukuom
	Education carried out
	x
	x
	x
	x
	2,500.00
	
	
	SWCD
	NCCE,DOVVSU,CSOs

	
	80. Skills training for 3 vulnerable groups


	District wide
	Number of venerable groups trained
	x
	x
	x
	x
	100,000 .00
	
	
	SWCD
	NCCE,NPECLC, GES, GPS,

	
	81. Support to PWDs
	District wide
	
	
	
	
	
	110,000.00
	
	
	SWCD
	

	
	82. Education on domestic violence act and gender base violence among three women groups in three communities


	District wide
	Education carried out
	x
	x
	x
	x
	5,176.00
	
	
	SWCD
	Chiefs, Opinion Leaders,

	
	83. Formation and, training of child protection and gender committee in 2 communities on the issue of child labour and trafficking


	Kamirekrom/ siana
	Child protection and gender committee formed and trained
	x
	x
	x
	x
	2,500.00
	
	
	SWCD/NGO(fair trade)
	PFI (UT Bank-Sunyani, , GPS

	
	84. Supervision of   early childhood development centre in the district
	District wide
	Number of early childhoods centers supervised
	x
	x
	x
	x
	1,500.00


	
	
	SWCD
	Asbly, members,DA, Mastercraft men

	
	85. Education on the children’s Act in three communities in the district
	Kamirekrom, kwabenakuma, Mfrekrom
	Education carried out
	x
	x
	x
	x
	2,147.00
	
	
	SWCD/NGO
	DA, DFMC

	
	86. Update of PWDs Register


	District wide
	PWD register updated
	x
	x
	x
	x
	1,200.00
	
	
	SWCD


	Opinion learders, NHIS, GFD

	
	87. Register and resolve all child and family related cases reported to the district
	District wide
	Number of child and family related cases registered and resolved
	X
	X
	X
	x
	800.00


	
	
	SWCD


	GPS

	
	88. Facilitate the renewal and registration of vulnerable groups under NHIS
	Number of vulnerable groups resisted under NHIS
	
	x
	x
	x
	x
	800.00
	
	
	SWCD
	NHIS, Vulnerable groups

	
	89. Organize gender mainstreaming activities
	District wide
	
	x
	x
	x
	x
	3,000.00
	
	
	SWCD
	NHIS, Vulnerable groups

	
	90. Monitoring of school feeding beneficiary schools


	District assembly
	Number of schools monitored
	x
	x
	x
	x
	1,600.00
	
	
	Stakeholders
	DA, school feedingdesk officer

	
	a. SUBTOTAL
	
	
	
	
	
	
	5,394,861.24
	91,347.00
	415,050.00
	
	

	b. Development Dimension: Environment, Infrastructure and Human Settlement

	Infrastructure Delivery and Management


	91. Construction, spot improvement and upgrading of 92KM feeder roads to the rural communities


	District wide
	Feeder roads improved


	x
	x
	x
	x
	-
	
	179,076,789.04


	Feeder roads, COCOBOARD
	DA

	
	92. 72. Levelling and landscaping the forecourt of the new district assembly block
	Kukuom
	Funding for levelling and landscaping paid
	x
	x
	x
	x
	20,000.00
	
	-


	DWD
	DPCU

	
	93. Reshaping of 25km feeder road from 1000 Acre to Tettehkwaw and others
	1000 Acres to Tettehkwaw
	Feeder roads improved


	
	x
	x
	
	55,000.00
	
	
	DWD
	DPCU

	
	94. Reshaping of 18km feeder road from Amankwakrom to Asibrem and others
	Amankwakrom to Asibrem
	Feeder roads improved


	
	x
	x
	
	45,000.00
	
	
	DWD
	DPCU

	
	95. Support to MTTD for Road Safety Activities
	Kukuom
	MTTU supported
	x
	x
	x
	x
	-
	
	15,000.00


	DWD
	DPCU

	
	96. Erection of road blocks and speed rumps
	Kokooso, Adwumam, Pafo
	Speed rumps erected
	x
	x
	x
	x
	-
	
	80,000.00


	DWD
	DPCU

	
	97. Periodic clearing of pedestrian walkways
	District Wide
	Number of pedestrian ways cleared
	x
	x
	x
	x
	-
	
	185,000.00
	DWD
	DPCU

	
	98. Extension of power and Street Light to communities
	District wide
	Number of communities connected to the national grid
	
	x
	x
	x
	20,0000.00
	_
	_
	NGGL
	DWD

UR

	
	99. Maintenance and Rehabilitation of Streetlight
	District Wide
	Number of streetlights maintained
	
	x
	x
	x
	15,000.00
	
	-
	DWD
	DPCU

	
	100. Community Self Help Projects
	District wide
	Community initiated projects supported
	x
	x
	x
	x
	197,548.00
	-
	-
	DWD
	DCD

	environmental and sanitation management

Natural resource conservation
	101. Organize tree planting in communities/ Embark on reforestation programmes


	District wide
	Communities benefiting from tree planting exercise
	x
	x
	x
	x
	-
	-
	-
	FC
	RDCU, FC

	
	102. Supply of improved and early maturing seedlings
	District wide
	Improved seedlings supplied to plantation farmers
	x
	x
	x
	x
	-
	-
	-
	FC
	DPCU

	
	103. Organize radio talk shows on natural disasters and climate change
	District wide
	Radio talk show organised
	x
	x
	x
	x
	-
	5,300.00


	-
	FC
	DPCU, NADMO

	Infrastructure delivery and management

Physical and Spatial Planning


	104. carry out Street Naming and Property Addressing System
	Kukuom
	SNPS implemented
	x
	x
	x
	x
	13,000.00


	-
	50,000.00


	PPD
	SAT

	
	105. Preparation of Local plans for the district
	District wide
	Local plans prepared
	x
	x
	x
	X
	200,000.00
	
	
	PPD
	PPD, RCC, Trad. Authorities, Depts,

LUSPA

	
	106. Issuance of development permits
	District wide
	
	X
	x
	x
	x
	1,000.00
	
	
	PPD
	PPD, RCC, MLGRD, LGS, Depts,

LUSPA

	
	107. Train staff and Spatial Planning Committee members on new models and Legislation enacted on Physical Development
	Kukuom
	Training conducted
	X
	x
	x
	x
	100,000.00
	
	
	PPD
	PPD, RCC, MLGRD, LGS, Depts,

LUSPA

	
	108. Create public awareness on greening of human settlements
	District wide
	Sensitization carried out
	x
	x
	x
	X
	25,000.00
	
	
	PHD
	PPD, RCC, MLGRD, LGS, Depts,

LUSPA

	
	109. Carry out monthly inspections and weekly planning education


	Kukuom
	Inspections and weekly planning education carried out
	x
	x
	x
	x
	1,674.15
	5000.00
	-
	PPD
	DA

	
	110. Organise technical sub- committee meetings
	Kukuom


	Technical committee meetings held
	x
	x
	x
	x
	-
	13,600.00
	-
	PPD
	DA


	
	111. Statutory planning committee meetings
	Kukuom
	Statutory planning committee meetings held
	X
	X
	X
	x
	
	14,200.00
	
	DPCU
	DA

	
	SUBTOTAL
	
	
	
	
	
	
	873,222.15
	38,100.00
	179,406,789.04
	
	

	Development Dimension: Governance, Corruption and Public Accountability

	Management and Administration

Central Administration
	112. Strengthening of sub district structures
	Kukuom, Kwapong, Sankore, Asarekrom, Abuom and Kokooso


	Sub district structures strengthened
	X
	X
	X
	x
	163,321


	-
	-
	CA
	Area Councils

	
	113. Prepare and implement Revenue improvement Action Plan
	Kukuom
	Improvement in IGF
	x
	x
	x
	x
	-
	98,000.00


	-
	DFO
	RU,DBA

	
	114. Servicing and maintenance of official vehicles/ motorbikes
	kukuom
	Vehicles and motobikes maintained
	X
	x
	x
	x
	
	10,000.00
	
	DFO
	RU,DBA

	
	115. Completion of 1No.  3Bedroom semi-detached quarters
	Residency (Kukuom)
	Office equipment procured and maintained
	x
	x
	x
	x
	60,000.00


	
	-
	CA
	DPCU

	
	116. Renovation of official bungalow at residency (DCE)
	Residency (Kukuom)
	Payment made for works
	x
	x
	x
	x
	47,443.72
	
	
	
	

	
	117. Completion of District Administration Block
	Kukuom
	Administration block completed
	X
	X
	x
	x
	146,339.00
	
	
	works
	

	
	118. Furnishing of the new District Assembly Block
	Kukuom
	Administration block furnished
	X
	X
	x
	x
	800,000
	
	
	PU
	

	
	119. Organize DPCU committee meetings
	Kukuom
	DPCU meetings held
	x
	x
	x
	x
	20,000.00
	
	-
	DPO
	DPCU,



	
	120. Undertake Monitoring, Evaluation and Reporting on Projects
	District wide
	Monitoring activities held
	X
	X
	X
	x
	20,000.00
	
	
	DPO
	DPCU

	
	121. Capacity building and training activities for staff Development
	Kukuom
	Capacity of Staff and training programmes attended
	X
	X
	X
	X
	
	
	
	CA
	Depts of Assembly

	
	122. Organize regular press meetings/Town Hall Meetings and public hearings.
	Kukuom, kwapong,
	Press meetings organized
	x
	x
	x
	x
	
	
	-
	DPCU
	ANDA

	
	123. Organise General, Executive, sub-committee
	Kukuom
	General, Executive and sub-committee meetings organised
	x
	x
	x
	x
	-
	60,000.00
	-
	DA
	DPCU

	
	124. Preparation of MTDP 2022-2025, composite Annual Action Plan and budget for 2022
	Kukuom
	2021 Composite Action plan and budget prepared.
	
	x
	x
	
	15,000.00


	10,000.00 
	-
	DBA, DPO
	Depts

	
	125. Organise quarterly Budget C’ttee meetings
	Kukuom
	Budget committee meeting held
	X
	X
	X
	X
	
	10,000.00
	
	DBU
	Planning

	
	126. Organize quarterly Entity Tender Committee meetings
	Kukuom
	Entity tender committee meeting held
	X
	x
	x
	x
	
	25,000.00
	
	PU
	DA

	
	127. Organise quarterly management and staff meetings
	Kukuom
	Management and staff meetings held
	x
	x
	x
	X
	
	5,000.00
	
	Planning, HR
	

	
	128. Organise audit committee meetings
	kukuom
	Meetings organised
	
	
	
	
	15,000.00
	
	
	AIC
	

	
	129. Organise quarterly radio sensitisation programmes on the evils of corruption and the ethos of anti-corruption
	Kukuom
	Sensitization programs held
	X
	x
	x
	x
	
	2,000.00
	
	Planning, HR
	NCCE

	
	130. Organise 1no. stakeholder’s engagement meeting with Council of churches and Islamic clerks on inclusion of anti-corruption sermons and teachings
	Kukuom
	Number of stake holder’s engagement held
	x
	x
	x
	X
	20,000.00
	
	
	Planning
	HR

	
	131. Organize bi-Annual District LEAP Implementing Committee (DLIC) Meeting
	Kukuom
	LEAP implementation committee meeting held
	x
	x
	X
	X
	1,000.00
	
	
	SWCD
	

	
	132. Organize quarterly PRCC meeting
	Kukuom
	Number of PRCC meetings held
	X
	x
	X
	x
	1,000.00
	
	
	
	

	
	133. Hold quarterly DISEC meetings
	Kukuom
	Number of DISEC meetings held
	x
	x
	x
	X
	10,000.00
	
	
	DA
	Security services

	
	134. Support to security activities
	District wide
	
	
	
	
	
	35,000.00
	
	
	DA
	Security services

	
	135. Organize National Celebrations
	District Wide
	Independence Day celebration held
	x
	x
	x
	X
	45,000.00
	
	
	DA
	

	
	SUBTOTAL
	
	
	
	
	
	
	1,399,104
	220,000.00
	0.00
	
	

	
	GRAND TOTAL
	
	
	
	
	
	
	8,530,488

	369,447.00
	181,303,866.30
	
	


13

