ASUNAFO SOUTH DISTRICT ASSEMBLY

IN GOD WE TRUST

REPUBLIC OF GHANA

COMPOSITE BUDGET

FOR 2023-2026

PROGRAMME BASED BUDGET ESTIMATES

FOR 2023

ASUNAFO SOUTH DISTRICT ASSEMBLY

Table of Contents

PART A: STRATEGIC OVERVIEW OF THE ASSEMBLY	4

Establishment of the District	4

Population Structure	4

Vision	4

Mission	4

Goals	4

Core Functions	4

District Economy	4

Key Issues/Challenges	5

Key Achievements in 2022	5

Revenue and Expenditure Performance	5

Adopted National Medium Term Development Policy Framework (NMTDPF) Policy Objectives	8

Policy Outcome Indicators and Targets	8

Revenue Mobilization Strategies	8

PART B: BUDGET PROGRAMME/SUB-PROGRAMME SUMMARY	9

PROGRAMME 1: MANAGEMENT AND ADMINISTRATION	9

PROGRAMME 2: SOCIAL SERVICES DELIVERY	19

PROGRAMME 3: INFRASTRUCTURE DELIVERY AND MANAGEMENT	29

PROGRAMME 4: ECONOMIC DEVELOPMENT	35

PROGRAMME 5: ENVIRONMENTAL MANAGEMENT	39

PART C: FINANCIAL INFORMATION	43

# PART A: STRATEGIC OVERVIEW OF THE ASSEMBLY

## Establishment of the District

The Asunafo South District is one of the Six (6) District/Municipal Assemblies in the Ahafo Region of the Republic of Ghana. The Legislative Instrument 1773 in line with government’s objective of deepening decentralization established the district in November 2004. The district capital is sited at Kukuom.

## POPULATION STRUCTURE

According to the 2021 Population and Housing Census of Ghana, the population of the district is 91,693. The males form 46,947 representing 51.2% and 44,746 females representing 48.8%.

The district has rural population of 62,124 and urban population of 29,569. This shows that the district is rural in nature with scattered settlements. The total land size of the district is 1019 k𝐦𝟐 with 268.53 k𝐦𝟐 covered by forest reserves. This area forms about 3.1% of the total regional land area of Ahafo.

## VISION

The vision of the Asunafo south district Assembly is “To become a safe and vibrant institution providing efficient services to the citizens.”

## MISSION

The Asunafo South District Assembly exists to harness all available resources within its area of jurisdiction to maintain excellence in education, agricultural production and local participation in governance to improve the standard of living of the people.

## GOALS

The goal of the Asunafo South District Assembly is to enhance the socio-economic and political well-being of the people within the District through effective resource mobilization

CORE FUNCTIONS

Section 12(1-19) and 13(1-8) of the Local Governance Act, 2016 (Act 936) broadly outlines the mandate and functions of the district Assemblies.

To Formulate and execute plans, programmes and strategies for the effective mobilization of the resources necessary for the overall development of the District.

Promote and support productive activities and social development in the District and remove any obstacle to initiative and development.

Initiate programmes for the development of basic infrastructure and provide good services in the District.

Responsible for the development, improvement and management of human settlement and the environment in the District.

In collaboration with the appropriate National and Local security agencies, be responsible for the maintenance of security and public safety in the District.

## Ensure ready access to courts in the District for the promotion of justice.

## Initiate, sponsor or carry out such study as may be necessary for the discharge of any of the functions conferred by the Act or any other enactment; and

## Perform such other functions as may be provided under any other enactment.

## DISTRICT ECONOMY

The economy of Asunafo South District is made up of agriculture, industry, commerce and the service sectors. Agriculture is the predominant economic activity. However, this is done largely at the subsistence level except cocoa, which is primarily for export.

The industrial sector is made up of few agro-processing facilities, while the commercial and the service sectors consist of trading in manufactured goods, foodstuffs and the rendering of services like hairdressing, transportation and other footloose businesses. About 61.1% of the labour force is employed in the agricultural sector, 8.4% in industry with the commercial and service sector absorbing 11.7%. The number of people employed in the agricultural sector gives an indication of the rural nature of the district. This also implies that any intervention in the agricultural sector stands to benefit majority of the people. The agricultural sector thus deserves a lot of attention.

AGRICULTURE

Agriculture in the district is still at the rudimentary stage relying on hoes, cutlasses and rainfall. Shifting cultivation, bush burning and bush fallowing are the common farming practices used by farmers. Farmlands are mostly acquired through share cropping (Abunu/Abusa). This forms about 16.4% of acquisition of farmlands in the district. The other forms of land acquisition are leasehold (10.5%), freehold/outright purchase (13.2), while over half (58.8) of farmlands in the district are in family land. Farm sizes are small. Averagely, farm sizes ranges from 1.5 - 2 acres for food crops and five acres for cocoa.

ROAD NETWORK

The district has about 70km-tarred roads, connecting the major towns with over 200km feeder roads linking the farming communities.  Following the government’s policy of ensuring easy access of products to and from market centers, the Assembly as the final policy implementer has also intensified upgrading of its feeder roads with the help of Assembly’s own acquired Grader.

ENERGY

The commonest source of energy for domestic purposes is firewood and charcoal. These are used mainly for cooking, baking and smoking of fish. Other energy sources are fuel used mainly to power water pumps, spraying machines for crops, generators and for vehicles. Some communities in the district also have access to electricity. However, majority of the communities are to be connected to the National electricity grid. Now about 95 percent of communities in the district have access to electricity. There is currently the supply of solar lightening within the deprived communities.

HEALTH

The District Health Directorate has 25 Health facilities under its jurisdiction as shown in the table below:

| Ownership | Hospital | CHPs | Health Centers | Clinics | Maternity Homes | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Government | 1 | 18 | 3 | 0 | 0 | 22 |
| Mission | 0 | 0 | 0 | 0 | 0 | 0 |
| Private | 2 | 0 | 0 | 0 | 1 | 3 |
| Total | 3 | 18 | 3 | 0 | 1 | 25 |

The health sector must be applauded for their significant role and interventions during this period of health emergency imposed on the world as a result of COVID-19, the very progress and achievement in combating this pandemic has come about due to the numerous protocols introduced by the Health sector practitioner’s.  Common communicable diseases in the district include Malaria, Upper Resp. Tract Infections (URTI), Rheumatism & Joint Pains, Diarrhea, Anemia, Skin Diseases etc.

EDUCATION

The Assembly spends quite a high proportion of its inflows on the provision of educational infrastructure. The categories are Nursery/Kindergarten :( public-81 & private 25), Senior high schools :( public-2): Tertiary institution: Kwapong NTC. The District Education Directorate currently has 52 staff (both teaching and non-teaching staff)

MARKET CENTRES

Commodity flow analysis is intended to establish the commercial or economic interactions within the Asunafo South District and between those outside in terms of the nature of goods and direction of flow to and from the three main periodic markets of Kukuom, Sankore and Kwapong. Goods involved are classified into agricultural and industrial.

Within the district, Kukuom, Sankore and Kwapong still serve as major periodic markets. Agricultural produce are conveyed from all places and settlements within the district to these market centers. These are made up mainly of foodstuffs such as plantain, cassava, cocoyam, yam, maize, okro, pepper etc. Conversely, endogenous outflows consisting of industrial goods move from the periodic markets especially from the Sankore market to all nooks and crannies of the district.

On the other hand, exogenous inflows into the district are made up mainly of industrial goods. Other exogenous inflows include fish products, meat and species of yam that are not readily available or produced in large quantities in the district. Exogenous outflows from the district include agricultural goods. Both the exogenous inflows and outflows analysis shows that the major trading partners of the District in terms of directions of movements of ‘exports’ and ‘imports’ are Accra, Kumasi, Goaso, Mim, Tepa, Sunyani and Techiman. In addition, within the district, the Kukuom and Sankore markets serve as the main points of departure of goods from the district and destinations for goods arriving into the district.

From the foregoing, it is observed that goods that are ‘imported’ into the district are largely industrial goods attracting higher values. On the other hand, agricultural goods constitute the bulk of goods ‘exported’ from the district. These are usually in their raw states with less value, which do not yield much returns to the district. From this perspective, the district is bound to register deficit net trade balance. This situation accordingly calls for the setting up of agro-based industries to add value to the agricultural goods produced and exported from the district

WATER AND SANITATION

The current water delivery system in the District is a serious development challenge that requires an urgent intervention.

“Water is life” as they say, but the problem of water in the Asunafo South District has become acute and is well known in the national level of which urgent steps, concern and support are needed by all stakeholders to reverse this trend. The presence of the Covid-19 indeed had its own effect on the District since; the water systems within the District must improve drastically to help manage the fast spreading virus.

Access to food and water are fundamental human rights, which should be prioritized for all to access for a healthy livelihood.

The availability of and accessibility to improved water is a crucial aspect of the health of household’s members.

##### WATER PROVISION AND MANAGEMENT

The provision and management of potable water has not been an easy task to the Assembly. The Assembly is currently faced with a number of challenges in its quest to make water accessible to the people. The challenges range from human to natural factors:

Most water sources dry-up in the dry season, compelling people in those areas to revert to drinking from unwholesome sources, which make them vulnerable to water related diseases.

The boreholes breakdown constantly because of excessive pressure coupled with the inability of communities to raise enough money for replacement and general maintenance.

Even though wells appear to be the major source of water, they are mostly left unprotected.  As a result, run-offs trickle down into such unprotected wells making them unsafe for human consumption.

Because of the limited number of water points, coupled with the general low water table in the District, women spend much of their productive hours in search of water to undertake their domestic chores. Children, and especially the girls, are mostly found helping their mothers to draw water at the expense of their education.

For economic reasons, most consumers of the pipe system in the District have serious difficulties in paying their water bills. This adversely affects the operation and management of the facility.  Administratively, the provision and management of water services are hampered by inadequate logistics, transport and remuneration for office and field staff.

In an effort to improve upon people’s access to potable water, the Assembly has collaborated with a number of development partners in the provision of potable water in the District. These partners include the Ghana Water Company Limited (GWCL), Community Water and Sanitation Agency (CWSA), and World Vision – Ghana, Water and Sanitation Hygiene (WASH) among others. The District health management team has complimented these efforts by educating people to keep water sources clean and safe. They also assist in detecting and treating water-borne diseases. Community ownership and management is also being promoted to enhance the sustainability of existing water facilities. Communities that have benefited from some form of water infrastructure, especially boreholes are being trained and provided with basic tools, equipment to undertake regular servicing, and maintenance of their water facilities.

##### SANITATION AND WASTE MANAGEMENT

Waste management in the District is far from been desirable. The disposal of both solid and liquid waste, including human excreta, storm water and household refuse are poorly carried out in the District. Though some households bury or burn their refuse, majority use the open surface system for their waste disposal. It is a general practice for people in most communities to defecate in the bush or openly (free range), mainly due to lack of access to convenient toilet facilities.

Where either households or the DA provides toilet facilities, there is however, a problem of timely and regular disposal of human excreta due to the unreliability of the only septic emptier in the District.

Most communities in the District do not also have any proper drainage system. The inadequacy of proper household drains has led to the accumulation of stagnant water with offensive smells in and around residential areas.  Drains are choked with filth giving rise to mosquito breeding especially during the rainy season.

ENVIRONMENT

The people derive mainly their livelihoods from the environment thus, the land for farming, animal husbandry and the settlements. Comparing the district’s population and its daily socio-economic requirement, much pressure is exerted on the scarce natural resources on meeting the growing demands. Population and development are inextricably related as changes in one extreme invariably affect the other. Every action of humanity has some environmental impact (either negative or positive). Pollution is a result of human activities on the environment. The main pollution is on the land, water and air.

| ## BUDGET PROGRAMS | ## FOCUS AREA IN MEDIUM TERM PLAN | ## Adopted Issues from MTNDPF 2022- 2025 |
| --- | --- | --- |
| ## Economic Development | ## Private Sector development | - Limited access to credit for MSMEs - Low entrepreneur culture among the youth |
|  | ## Agricultural and Rural Development | - Low application of technology especially among smallholder farmers leading to comparatively lower yields - Seasonal variability in food supply and prices - Low level of good husbandry practices |
| ## Social Services | ## Education and Training | - Inadequate school infrastructure - Inadequate supervision and monitoring of schools |
|  | ## Health and Health Services | - Gaps in physical access to health infrastructure and services - Inadequate and inequitable distribution of critical staff mix |
|  |  | - Increasing morbidity, mortality, and disability - High COVID-19 risk factor - High HIV and AIDS stigmatization and Discrimination - Limited knowledge of HIV and AIDS/STIs, especially among vulnerable groups |
|  | ## Water and Environmental Sanitation | - Inadequate access to water services - Increasing demand for household water supply - Inadequate Investments - Poor sanitation and waste management - Poor hygiene practices - Inadequate access to improved toilet facilities |
| ## Social Services | ## Child Protection and Development ## Disability-Inclusive Development | - Limited awareness on child rights and Development issues - Inadequate coverage and targeting of social protection programmes for children - Inadequate and inequitable access to and support for inclusive and special education for PWDs and people with special needs at all levels |
| ## Environment, infrastructure and Human Settlement | ## Transportation: Air, Water and Road | - Poor road maintenance/rehabilitation culture - Inadequate road infrastructure |
|  | ## Human Settlements Development and Housing | - Inadequate spatial plans - Weak enforcement of building regulations at the MMDA level |
|  | ## Local Governance and Decentralization | - Ineffective sub-district structures - Limited capacity and opportunities for revenue mobilization - Untapped revenue sources at the MMDAs - Weak involvement and participation of citizenry in planning and budgeting - Weak capacity of CSOs to participate effectively in public dialogue |

| ## Programmes/ projects | ## Location | ## Sources of funds |
| --- | --- | --- |
| ## Constructed 6 No. Limited Mechanized Boreholes | ## Abodom, Kwapong Zongo, New Sawreso CHPS, Siana, Noberkaw and Dantano | ## DACF |
| ## Constructed 1 No. Borehole fitted with handpump | ## Mmeso | ## DACF |
| ## Completed 1 No. 3 unit classroom block with office, toilet facility and dual k at Kukuom SDA | ## Kukuom | ## DDF |
| ## Completed 1 No. CHPS compound | ## Pafo Nkwanta | ## DACF |
| ## Completed 1 No. CHPS compound | ## Adwumam | ## DDF |
| ## Extension of electricity to 29 communities | ## Kukuom Tanoso, Alhajikrom,Sankore extension, Tadieso among others | ## DACF |
| ## PWDs support | ## 28 beneficiaries | ## DACF |
| ## Educational support | ## 56 Students | ## DACF, MPCF |

## REVENUE AND EXPENDITURE PERFORMANCE

REVENUE PERFORMANCE

Table 1: REVENUE PERFORMANCE -IGF ONLY

| REVENUE PERFORMANCE- IGF ONLY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ITEM | 2020 |  | 2021 |  | 2022 |  |  |
|  | Budget | Actual | Budget | Actual | Budget | Actual as at August | % performance as at August |
| Property Rate | 99,000.00 | 146,552.90 | 99,000.00 | 46,207.00 | 73,872.61 | 16,640.00 | 22.53% |
| Basic rates |  |  |  |  |  |  |  |
| Fees | 85,000.00 | 32,034.94 | 37103.00 | 22,863.00 | 56,600.00 | 16,655.00 | 29.43% |
| Fines | 5,500.00 | 5,750.00 | 14,000.00 | 7,385.00 | 27,500.00 | 4,390.00 | 15.96% |
| Licenses | 95,420.00 | 108,213.00 | 161,151.28 | 113,271.09 | 179,226.19 | 62,985.00 | 35.14% |
| Land | 112,963.64 | 155,353.65 | 70,400.00 | 53,631.00 | 48,000.00 | 17,518.00 | 36.49% |
| Stool land |  |  | 180,666.67 | 217,000.00 | 220,000.00 | 110,000.00 | 50.00% |
| Rent | 25,000.00 | 7,130.00 | 16,500.00 | 16,780.00 | 35,000.00 | 13,368.00 | 38.19% |
| TOTAL | 422,883.64 | 455,034.49 | 578,820.95 | 477,137.77 | 640,198.80 | 241,556.00 | 37.73% |

Table 1 above indicates IGF revenue performance of 2020 and 2021 were 108.00% and 82.00% of the estimated respectively.  The Assembly had realized an amount of GH¢241,556.00 out of the 2022 target of GH¢640,198.80 representing 38.00% as at August 2022.

| TABLE 2: REVENUE PERFORMANCE – ALL REVENUE SOURCES |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| REVENUE PERFORMANCE- ALL REVENUE SOURCES |  |  |  |  |  |  |  |
| ITEM | 2020 |  | 2021 |  | 2022 |  |  |
|  | Budget | Actual | Budget | Actual | Budget | Actual as at August | % performance as at Aug. |
| IGF | 422,883.64 | 455,034.49 | 578,820.95 | 477,137.77 | 640,198.80 | 241,556.00 | 37.73% |
| Compensation Transfer | 1,831,391.51 | 1,831,391.52 | 2,339,911.44 | 2,339,911.44 | 2,732,659.13 | 1,821,772.72 | 66.67% |
| Goods and Services Transfer | 67,524.04 | 52,971.94 | 75,601.00 | 43,141.06 | 99,118.00 | 25,319.92 | 25.55% |
| Assets Transfer | 0 | 0 | 0 | 0 | 25,180.00 | 0 | 0 |
| DACF | 3,968,511.44 | 2,466,599.11 | 4,346,061.50 | 1,190,080.08 | 4,386,758.36 | 1,087,819.42 | 24.80% |
| DACF-RFG | 2,048,134.78 | 585,329.01 | 1,914,383.13 | 1,465,192.00 | 1,183,992.00 | 264,828.65 | 22.37% |
| MAG | 222,6634 | 202,612.72 | 155,196.00 | 117,312.48 | 70,813.53 | 56,657.88 | 80.01% |
| Total | 9,132,867.62 | 5,509,153.55 | 9,409,974.02 | 5,632,774.83 | 9,138.719.82 | 3,497,954.62 | 38.28% |

Table 2 above illustrates the total revenue performance of the Assembly for the period. The total revenue performance stood at 60.32% and 59.86% for 2020 and 2021 respectively. As at August 2022, actual total revenue was GH¢3,497,954.62 which represented 38.28% of the estimates for the year. Out of this amount, IGF contributed GH¢241,556.00 while the remaining amount of GH¢3,256,398.62 was received from Grants and Donor.

| EXPENDITURE |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| TABLE 3: EXPENDITURE PERFORMANCE-ALL SOURCES |  |  |  |  |  |  |  |
| EXPENDITURE PERFORMANCE (ALL DEPARTMENTS) ALL FUNDING SOURCES |  |  |  |  |  |  |  |
| Expenditure | 2020 |  | 2021 |  | 2022 |  |  |
|  | Budget | Actual | Budget | Actual | Budget | Actual as at August | % age |
| Compensation | 1,896,749.86 | 1,905,258.69 | 2,470,241.09 | 2,430,066.28 | 2,825,352.73 | 1,872,820.00 | 66.29% |
| Goods and Services |  |  | 2,429,092.43 | 827,555.98 | 2,154,742.89 | 1,120,777.94 | 52.01% |
|  | 240,700.00 | 386,550.72 |  |  |  |  |  |
| Assets | 6,995,417.76 | 1,995,859.91 | 4,510,640.37 | 2,161,096.22 | 4,158,624.20 | 499,883.00 | 12.02% |
| Total | 9,132,867.62 | 4,287,973.09 | 9,409,867.62 | 5,418,718.48 | 9,138,719.82 | 3,493,480.94 | 38.23% |

As at August, 2022, actual expenditure from all sources was GH¢3,493,480.94 which represented 38.23% of the overall budget of GH¢9,138,719.82.

## ADOPTED MEDIUM TERM NATIONAL DEVELOPMENT POLICY FRAMEWORK (MTNDPF) POLICY OBJECTIVES

The NMTDPF policy objectives adopted by the Asunafo South District Assembly are as follows:

- Support Entrepreneurship and SME Development - Modernize and enhance agricultural production systems - Promote livestock and poultry development for food security and income generation - Enhance inclusive and equitable access to, and participation in quality education at all levels - Ensure affordable, equitable, easily accessible and Universal Health Coverage (UHC) - Ensure reduction of HIV and AIDS/STIs infections, especially among the vulnerable - Improve access to safe, reliable and sustainable water supply services for all - Enhance access to improved and sustainable environmental sanitation services - Promote sustainable spatially integrated development of human settlements - Attain gender equality and equity in political, social and economic development - Deepen political, financial and administrative decentralization - Develop quality, reliable, sustainable & resilient infrastructure - Promote culture and youth development - Address recurrent devastating floods

POLICY OUTCOME INDICATORS AND TARGETS

TABLE 4: POLICY OUTCOME INDICATORS AND TARGETS

| Outcome Indicator Description | Unit of Measure | Baseline 2020 |  | Past Year 2021 |  | Latest Status 2022 |  | Medium Term Target |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target | Actual | Target | Actual | Target | Actual as at August | 2023 | 2024 | 2025 | 2026 |
| Strengthened local participation in decision making | No. of DA Sub-Structures functional | - | - | 3 | 4 | 6 | 6 | 6 | 6 | 6 | 6 |
| Local Governance and decentralization enhanced | Number of social accountability fora held | 4 | 2 | 4 | 3 | 4 | 2 | 4 | 4 | 4 | 4 |
| Equitable access to education, participation in quality education (Net Enrolment Rate (NER)) | KG | 55 | 50.09 | 60 | 58.4 | 65 | 57.1 | 70 | 70 | 75 | 75 |
|  | PRIMARY | 60 | 57.6 | 65 | 62.1 | 65 | 61.2 | 70 | 70 | 75 | 75 |
|  | JHS | 30 | 25.4 | 30 | 27.9 | 30 | 26.3 | 32 | 35 | 40 | 40 |
| Access to Primary Health care | NO. of Functional CHPS Compound | 28 | 14 | 28 | 16 | 28 | 18 | 28 | 28 | 28 | 28 |
| Enhance the participation of science and technology and innovation along the value chain | Total number of farmers who benefited from agricultural technology | 28000 | 24562 | 28000 | 26250 | 28000 | 19813 | 28000 | 30000 | 30000 | 30000 |
| Increased vulnerability support for PWDs in the District, vulnerable | No. of PWDs supported | 60 | 30 | 60 | 42 | 60 | 28 | 60 | 70 | 70 | 70 |
| Disaster prevention and mitigation | No. of community fora held | 7 | 5 | 10 |  | 5 | 3 | 10 | 15 | 24 | 25 |
| Feeder road construction and reshaping | Kilometre of feeder roads reshaped | 30 | 12 | 30 | 24 | 20 | 12 | 25 | 34 | 26 | 24 |

## REVENUE MOBILIZATION STRATEGIES FOR 2023

| REVENUE SOURCE | KEY STRATEGIES |
| --- | --- |
| - RATES (Basic Rates/Property Rates/Cattle Rates) | - Sensitize cattle owners (Fulani herdsmen) and other ratepayers on the need to pay Cattle/Basic/Property rates. - Update data on all cattle owners in the district - Activate Revenue taskforce to assist in the collection of cattle rates - Property rate Improvement Team formed |
| - LANDS | - Sensitize the people in the district on the need to seek building permit before putting up any structure. - Establish a unit within the Works Department solely for issuance of building permits |
| - LICENSES | - Sensitize business operators to acquire licenses and also renew their licenses when expired - To intensify data collection on property/business within the District |
| - RENT | - All stores data/records of the Assembly are to be updated for effective monitoring of payments. - Numbering and registration of all Government bungalows - Sensitize occupants of Government bungalows on the need to pay rent. - Issuance of demand notice |
| - FEES AND FINES | - Sensitize various market women, trade associations and transport unions on the need to pay fees on export of commodities - Formation of revenue monitoring team to check on the activities of revenue collectors, especially on market days. - Prosecute Defaulters |
| - INVESTMENT (Bulldozer & Grader) | - Position a Revenue Collector at the sand winning site. - Improving on monitoring on the activities of the operators of the bulldozer and grader. |
| - REVENUE COLLECTORS | - Quarterly rotation of revenue collectors - Setting target for revenue collectors - Engaging the service of the Chief Local Revenue Inspector (at RCC) to build the capacity of the revenue collectors - Sanction underperforming revenue collectors - Awarding best performing revenue collectors. |

# PART B: BUDGET PROGRAMME/SUB-PROGRAMME SUMMARY

## PROGRAMME 1: MANAGEMENT AND ADMINISTRATION

BUDGET PROGRAMME OBJECTIVES

The objectives of this program are as follows:

Ensure full political, administrative and fiscal decentralization

To formulate and translate policies and priorities of the Assembly into strategies

To integrate and institutionalize planning and budgeting through participatory process

Ensure effective and efficient mobilization of resources and its utilization

To develop capacity of staff to deliver quality services

There are five sub-Programmes namely:

Central Administration

Finance and Audit

Planning, Budgeting and Statistic

Legislative Oversights

Human Recourses

BUDGET PROGRAMME DESCRIPTION

The program seeks to perform the core functions of ensuring good governance and balanced development of the District through the formulation and implementation of policies, planning, coordination, monitoring and evaluation in the area of local governance. The Program is being implemented and delivered through the offices of the Central Administration. The various units involved in the delivery of the program include; General Administration Unit, Planning and Budget Unit, Finance & Procurement Unit, Human Resource and Records Unit and the Sub- Structures of the Assembly. It seeks to provide administrative and logistic support services for the smooth operation of other departments.

Kukuom, Sankore, Kwapong, Aboum, Kokooso and Asarekrom Area Councils have been strengthened to bring more meaning into the decentralization process and hence responsible for grassroots support and engagement in planning, budgeting and resources mobilization.

Staff for the delivery of this program is 126 (109 are on GoG pay roll and 16 on IGF pay roll).

The programmme is to be funded with transfers from the Central Government (sector specific transfers and salaries), District Assembly Common Fund (DACF), Donor funds, District Development Facility (DDF) and the Internally Generated fund – IGF.

SUB-PROGRAMME 1.1 GENERAL ADMINISTRATION

BUDGET SUB-PROGRAMME OBJECTIVE

The objectives of the General Administration sub program are;

- Ensure full political, administrative and fiscal decentralization

- To facilitate and coordinate activities of department of the Assembly

BUDGET SUB- PROGRAMME DESCRIPTION

The general Administration sub-program oversees and manages the support functions for the Asunafo South District Assembly. The sub-program is mainly responsible for coordinating activities of decentralized departments and providing support services. The sub-program provides transportation, records, security, public relations, adequate office equipment, stationery, and other supporting logistics.

The core function of the General Administration unit is to facilitate the Assembly’s activities with the various departments, quasi institution, and traditional authorities.

Beneficiaries of the sub programme are the staff of the Assembly and the general public. The challenges include inadequate funds and logistics.

A total staff strength of Eighty Six (86) is expected to ensure the implementation of this sub-programme.

BUDGET SUB-PROGRAMME RESULTS STATEMENT

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-programme. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.

TABLE 5: BUDGET SUB-PROGRAMME RESULTS STATEMENT

| Main Outputs | Output Indicators | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2022 | 2022 as at Aug | 2023 | 2024 | 2025 | 2026 |
| Organization of General Assembly meeting | Number of General Assembly Meetings held (Minutes) | 3 | 1 | 4 | 4 | 4 | 4 |
| Entity Tender Committee Meetings Held | No. of Entity Tender Committee meetings held | 4 | 3 | 4 | 4 | 4 | 4 |
| Sensitization/consultative for AAP, RIAP, CB, etc | Number of sensitizations/ consultative fora held on (Minutes, Reports) | 3 | 2 | 4 | 4 | 4 | 4 |
| Meetings of District Security Committee Held | No. of District Security Committee meetings held | 25 | 15 | 25 | 25 | 25 | 25 |
| Meetings of Public Relations and Complaints Committee (PRCC) | No. of Public Relations and Complaints Committee (PRCC) Meetings Held | 4 | 2 | 4 | 4 | 4 | 4 |
| Annual progress report prepared | Submission date of Annual Report | 7/2/20 | 8/2/21 | 7/2/22 | 8/2/23 | 8/2/24 | 5/2/25 |

BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

TABLE 6: BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

| Standardized Operations | Standardized Projects |
| --- | --- |

| Protocol services |  | Completion of 1No. 3- storey Administration Block at Kukuom |
| --- | --- | --- |
| Legislative enactment and oversight |  | Construction of 1No.3unit semi –detached staff quarters at Kukuom |
| Administrative and technical meetings |  | Renovation of official Bungalow at Residency |
| Security management |  |  |
| Support to traditional authorities |  |  |
| Citizen participation in local governance |  |  |
| Plan and budget preparation |  |  |
| Legal Services |  |  |

SUB-PROGRAMME 1.2 FINANCE AND AUDIT

Budget Sub-Programme Objective

Ensure full political, administrative and fiscal decentralization

Improve financial management and reporting through the promotion of efficient Accounting system

Ensure effective and efficient mobilization of resources and its utilization

Ensure periodic audit system the formed with the standardizes accounting practise

BUDGET SUB- PROGRAMME DESCRIPTION

The sub-program seeks to ensure effective and efficient resource mobilization and management. The Finance and Revenue mobilization sub-program comprises of two units namely, the Accounts/Treasury, internal audit. Each Unit has specific rolls they play in delivering the said outputs for the sub-program. The account unit collects records and summarizes financial transactions into financial statements and reports to assist management and other stakeholders in decision-making. They also receive, keep safe custody and disburse public funds. This unit together with the Budget unit sees to the payment of expenditures within the District. The budget unit issue warrants of payment and participating internally revenue generation of the Assembly.

The internal audit unit ensures that payment vouchers submitted to the treasury are duly registered and checking all supporting documents to payment vouchers, to ensure they are complete before payments are effected. This is to strengthen the control mechanisms of the Assembly.

This major activity helps to ensures reconciliations and helps in providing accurate information during the preparation of monthly financial statement, which is later submitted for further actions. Forty Three officers, comprising 1 Finance Officer, 3 Accountants, 1 Senior Accountant,1 Senior Internal Auditor,1 Internal Auditor, 5 Assistant Internal Auditors, 2 Audit Trainee, 1 Senior Revenue Superintendent,3 Revenue Superintendent, 5  Higher Revenue Inspector, 4 Revenue Inspector   and 16 IGF collectors proficiently man the sub-program. Funding for the Finance sub-program is from Internally Generated Revenue (IGF), GoG and DACF.

CHALLENGES

The following are the key Challenges to be encountered in delivering this sub-program:

- Inadequate motorbikes for revenue mobilisation.

- Inadequate Logistics support to the programme

BUDGET SUB-PROGRAMME RESULTS STATEMENT

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-program. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.

TABLE 7: BUDGET SUB-PROGRAMME RESULTS STATEMENT

| Main Outputs | Output Indicators | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2022 | 2022 Aug | 2023 | 2024 | 2025 | 2026 |
| Revenue collection monitored and supervised | No. of visits to market Centre | 20 | 12 | 30 | 30 | 30 | 30 |
| Level of Implementation of Revenue Improvement Action Plan (RIAP) improved | % of Implementation of the RIAP | 95% | 45% | 100% | 100% | 100% | 100% |
| Monthly Financial reports prepared | No. of monthly financial reports prepared and submitted by the 15th day of the ensuing month | 12 | 7 | 12 | 12 | 12 | 12 |
| Accounts and records of funds are maintained and submitted for Audit | No. of times Accounts and records are audited | 4 | 2 | 4 | 4 | 4 | 4 |

BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

Table 8: Budget Sub-Programme Standardized Operations and Projects

| Standardized Operations | Standardized Projects |
| --- | --- |
| Treasury and accounting activities |  |
| Internal audit operations |  |
| Revenue collection and management |  |

SUB-PROGRAMME 1.3 Planning, Budgeting, Coordination and Statistics

Budget Sub-Programme Objective

Ensure full political, administrative and fiscal decentralization

To integrate and institutionalize planning and budgeting through participatory process

Facilitate, formulate and coordinate plans and budgets and

To ensure monitoring and evaluation of all development projects and programmes.

BUDGET SUB- PROGRAMME DESCRIPTION

The sub-program is responsible for preparation of comprehensive, accurate and reliable action plans and budgets.  The sub-program will be delivered by conducting needs assessment of Area councils and communities; hold budget committee meetings, DPCU meetings, stakeholder meetings, public hearings and data collections to ensure participatory planning and budgeting. The three main units for the sub-program include the planning unit, budget unit and statistic department. Funds to carry out the program include IGF, DACF, and DDF. Effective delivery of this sub-program will benefit not only the community members but also development partners and the departments of the assembly.

Plans and budgets of decentralized departments are not easy to come by and thus posing a hindrance towards achieving the objectives of this sub-program. Other challenges include lack of motorbikes to undertake effective M&E, lack of commitment and teamwork from departments, inadequate knowledge on new planning and budgeting reforms by the decentralized departments and political interference. Four officers comprising of one Budget Analyst, three Planning Officers, proficiently manage the sub-program.  Funding for the planning and budgeting sub-program is from GOG, IGF and DACF.

The sub-program will be manned by sixteen officers comprising of, nine Assistant Budget Analyst, one Principal Planning Officers, four Assistant Planning and one Assistant Statistician. The main challenges in carrying out the sub-program include lack of collaboration with other decentralized departments and non-adherence to rules and regulations.

BUDGET SUB-PROGRAMME RESULTS STATEMENT

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-program. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.1

TABLE 11: BUDGET SUB-PROGRAMME RESULTS STATEMENT

| Main Outputs | Output Indicators | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2021 | 2022 as at Aug | 2023 | 2024 | 2025 | 2026 |
| Fee fixing resolution prepared | Fee fixing resolution prepared and gazetted by | 31st Dec. | 31st Dec. | 31st Dec. | 31st Dec. | 31st Dec. | 31st Dec. |
| Monitoring of projects and programmes | No. of site visits undertaken | 4 | - | 4 | 4 | 4 | 4 |
| Plans and Budgets produced and reviewed | Annual Action Plan prepared by | Sept. | July | June | June | June | June |
|  | District Composite Budget prepared by | October | October | October | October | October | October |
|  | AAP and composite budget reviewed by | 30th June | 30th June | 30th June | 30th June | 30th June | 30th June |

BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

TABLE 12: BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

| Standardized Operations | Standardized Projects |
| --- | --- |

| Budget preparation and Coordination |  |  |
| --- | --- | --- |
| Budget implementation and performance reporting |  |  |
| - Rating and Billing |  |  |
| Data Collection, analysis and management |  |  |
| Data and information dissemination |  |  |
| MTDP and AAP prepared |  |  |
| Training on methods and statistical concept |  |  |
| Monitoring and Evaluation of projects |  |  |

SUB-PROGRAMME 1.4 Legislative Oversights

Ensure full political, administrative and fiscal decentralization

To provide adequate legal services to support the effective and efficient implementation of policies.  Provide legislative oversight responsibilities for the Assembly, Sub-structures and other agencies.

BUDGET SUB PROGRAMME DESCRIPTION

This Sub-programme provides adequate technical and logistical support to enhance legal performance of the Assembly. It also ensures that all agreements, contracts and engagements of the Assembly are undertaken in accordance with the required legal provisions and policies to ensure the desired results are achieved.

BUDGET SUB-PROGRAMME RESULTS STATEMENT

TABLE 13: BUDGET SUB-PROGRAMME RESULTS STATEMENT

| Main Outputs | Output Indicators | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2021 | 2022 as at Aug | 2023 | 2024 | 2025 | 2026 |
| General Assembly meetings Held | No. of General Assembly meetings held | 3 | 1 | 4 | 4 | 4 | 4 |
| Meetings of the Sub-committees held | No. of meetings of the Sub-committees held | 4 | 2 | 4 | 4 | 4 | 4 |
| Executive Committee meetings held | No. of Executive Committee meetings held | 3 | 1 | 4 | 4 | 4 | 4 |

BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

TABLE 14: BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

| Standardized Operations | Standardized Projects |
| --- | --- |
| Legislative enactment and oversight |  |
| Justice delivery and legal services |  |

SUB-PROGRAMME 1.5 HUMAN RESOURCE MANAGEMENT

The objective of the sub-programme are to;

Ensure full political, administrative and fiscal decentralization

Coordinate the overall human resources programmes of the district.

To develop capacity of staff to deliver quality services.

BUDGET SUB- PROGRAMME DESCRIPTION

The Human resource management sub-Programme seeks to manage, develop capabilities and competences of staff and coordinate human resource programmes for efficient delivery of public service. The sub-Programme would be carried out through ensuring regular updates of staff records, staff needs assessment, ensuring general welfare of staff, ensuring inter and intra departmental collaboration to facilitate staff performance and development, organizing staff trainings to build their capabilities, skills and knowledge.

The human resource unit has strength of three officers comprising of one Human Resource Officer, Assistant Human Resource Officer and 1Senior Personnel Officer. Funds to deliver the human resource sub-Programme include IGF, DACF and DDF capacity building. The main challenge faced in the delivery of this sub-Programme is the weak collaboration in human resource planning and management with key stakeholders also Logistics Constraints

BUDGET SUB-PROGRAMME RESULTS STATEMENT

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-programme. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.

Table 9: Budget Sub-Programme Results Statement

| Main Outputs | Output Indicators | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2021 | 2022 as at August | 2023 | 2024 | 2025 | 2026 |
| Accurate and comprehensive HRMI data updated and submitted to RCC | No. of updates and submissions done | 12 | 7 | 12 | 12 | 12 | 12 |
| Capacity of staff built on public procurement | No. of staff trained on public procurement | - | - | 4 | 4 | 4 | 4 |
| Appraisal of staff annually | Number of staff appraisal conducted | 151 | 120 | 151 | 151 | 151 | 151 |
| Junior staff supported to undertake secretariat courses at Gov’t secretariat school, Accra | No. of staff | - | 1 | 3 | 3 | 3 | 3 |
| Staff assisted in performance appraisal | Number of staff appraised | 86 | 20 | 50 | 50 | 50 | 50 |
| Ensure efficiency in service delivery | No. of staff trained /supported for short courses | - | 1 | 5 | 5 | 5 | 5 |

BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

The table lists the main Operations and projects to be undertaken by the sub-programme

TABLE 10: BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

| Standardized Operations | Standardized Projects |
| --- | --- |
| Personnel and Staff management |  |
| Performance Management |  |
| Training and Development |  |
| Staff Training and skills development |  |
| Recruitment and career progression management |  |

PROGRAMME 2: SOCIAL SERVICES DELIVERY

Budget Programme Objectives

- Enhance inclusive & equitable access & participation in education at all levels

- Ensure sustainable, equitable and easily accessible healthcare services

- Establish an effective and efficient social protection system

- To register infant and death person

Accelerate the provision of improve environmental sanitation

BUDGET PROGRAMME DESCRIPTION

Social Service Delivery is one of the key Programmes of the Assembly. This Programme seeks to take an integrated and holistic approach to development of the District and the Nation as a whole. There are five sub-Programmes under this Programme namely:

- Education, Youth and sports services

- public health services and management,

- Social Welfare and Community Development,

- Birth and death registration services and

- Environmental health and sanitation services.

The education, Youth and Sport Department of the Assembly is responsible for pre-school, special school, basic education, youth and sports, development or organization and library services in the district. The departments therefore assist the Assembly in the formulation and implementation of programmes in such areas of education and youth development.

The Department of Health in collaboration with other departments assist the Assembly to deliver context specific health care interventions by providing accessible, cost effective and efficient health service at the primary and secondary care levels in accordance with approved national policies by ensuring prudent management of resources.

The Social Welfare and Community Development Department assist the Assembly to formulate and implement social welfare and community development policies within the framework of national policy.

Extreme poverty continues to work against the economic gains that Ghana has chalked over the past two decades. It is estimated that about 10% of Ghanaians live under extreme poverty conditions. This means that they are neither able to afford daily subsistence requirement nor afford education and basic health for themselves and their children.

This phenomenon perpetuates generational poverty. In order to ensure equitable distribution of national resources and mainstreaming of the extremely poor, Government developed and started implementing the National Social Protection Strategy (NSPS) in 2007. In Asunafo South District, 200 households are benefitting from conditional and unconditional cash transfer under the Livelihood Empowerment against Poverty (LEAP) Programme; a component of the NSPS. Extremely poor Older Persons above 65 years have been enrolled onto the LEAP and are entitled to unconditional cash transfer.

The total number of personnel under this budget Programme is Eight (8).

The programmme is to be funded with transfers from the Central Government (sector specific transfers, District Assembly Common Fund (DACF), Donor funds, District Development Facility (DDF) and the Internally Generated fund (IGF).

SUB-PROGRAMME 2.1 Education, Youth and Sports Services

BUDGET SUB-PROGRAMME OBJECTIVE

- To ensure inclusive and equitable access to education at all levels

- To formulate and implement policies on Education in the District within the framework of National Policies and guidelines.

BUDGET SUB- PROGRAMME DESCRIPTION

The Education and Youth Development sub-programme is responsible for pre-school, special school, basic education, youth and sports development or organization and library services at the District level

This sub-programme is carried through:

- Formulation and implementation of policies on Education in the District within the framework of National Policies and guidelines;

- Advise the District Assembly on matters relating to preschool, primary, Junior High Schools in the District and other matters that may be referred to it by the District Assembly;

- Facilitate the appointment, disciplining, posting and transfer of teachers in pre-schools, basic schools and special schools in the district;

- Liaise with the appropriate authorities for in-service training of pupil teachers and encouraging teachers to undergo advance studies relevant to the field;

- Supply and distribution of textbooks in the district

- Advise on the construction, maintenance and management of public schools and libraries in the district;

- Advise on the granting and maintenance of scholarships or bursaries to suitably qualified pupils or persons to attend any school or other educational institution in Ghana or elsewhere;

- Assist in formulation and implementation of youth and sports policies, programmes and activities of the District Assembly;

Organisational units in carrying the sub-programme include the Basic Education Unit, Non-Formal Education Unit, Youth and Sport Unit. The department responsible for the sub-programme is the District Education Directorate with funding from GOG, DACF, Donor support and the district’s IGF.

The community, development partners and departments are the key beneficiaries to the sub-programme. This sub program is undertaken by 1,483 staff.

Challenges in delivering the sub-programme include the following:

- Inadequate and late release of funds hence leading to wrong timing of operations and projects thereby affecting implementation of projects and operations.

- Poor and inaccessible road networks hindering monitoring and supervision of schools.

- Lack of staff commitment.

BUDGET SUB-PROGRAMME RESULTS STATEMENT

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-programme. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.

TABLE 15: BUDGET SUB-PROGRAMME RESULTS STATEMENT

| Main Outputs | Output Indicator |  | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 |
| Enrolment increased | Gross enrolment Rate | KG | 92.2% | 95% | 96% | 96.5% | 97% | 98% |
|  |  | Primary | 84.3% | 95.1% | 97% | 98% | 98% | 98% |
|  |  | JHS | 52.5% | 86% | 90% | 92% | 95% | 98% |
|  |  | SHS | 78% | 90% | 90% | 95% | 95% | 98% |
|  | Gender Parity Index | KG | 0.74 | 0.23 | 1.0 | 1.0 | 1.0 | 1.0 |
|  |  | Primary | 4.65 | 2.8 | 1.0 | 1.0 | 1.0 | 1.0 |
|  |  | JHS | 6.50 | 5.69 | 2.0 | 2.0 | 2.0 | 2.0 |
|  |  | SHS | 20.14 | 13.55 | 5.0 | 5.0 | 5.0 | 5.0 |
| Literacy and Numeracy levels improved | BECE pass rate |  | 63.04% |  | 100% | 100% | 100% | 100% |
|  | Percentage of students with reading ability |  | 40% | 42% | 45% | 50% | 55% | 60% |
| Schools monitored | Percentage of schools visited for inspection |  | 95% | 98.5% | 100% | 100% | 100% | 100% |
| Organized quarterly DEOC meetings | No. of meetings organised |  | 3 | 4 | 4 | 4 | 4 | 4 |
| Provision of educational facilities | No. of classroom block with ancillaries constructed |  | 5 | 8 | 6 | 10 | 10 | 10 |
|  | No. of teachers quarter constructed |  | 2 | 2 | 4 | 4 | 4 | 4 |
|  | No. of dining halls constructed |  | 2 | 1 | 1 | 0 | 0 | 0 |

BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

TABLE 16: BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

| Standardized Operations | Standardized Projects |
| --- | --- |

| Financial support (Scholarships) |  | Procurement and Supply of 850 Dual Desks to the Basic Schools District wide |
| --- | --- | --- |
| Support for brilliant but needy students |  | Construction of 1No 3unit classroom block with office, staff common room, 3 seater KVIP and supply furniture at Kukuom Girls Model |
| Support for District Education Oversight Committee (DEOC) |  | Construction of 1No 3unit classroom block with office, staff common room, 3 seater KVIP and supply furniture at Kukuom SDA. |
| Development of youth, sports and culture |  | Completion of 1No. 3 Unit Classroom Block with 4 Seater KVIP & Urinal at Asempaneye |
| Support to teaching and learning delivery |  | Completion of 1No. 3 Unit Classroom Block at Kukuom Anglican (KG) |
| Supervision and inspection of Education Delivery |  | Completion of 1No. 3Unit Classroom Blk. At Siiso |
| My First Day at School |  | Completion of 1No. 3 Unit Classroom Block with 4 Seater KVIP & Urinal at Siiso Bowjiase |
|  |  | Completion of Teacher's Quarters with 2No. Toilet & Bathroom at Nakete |
|  |  | Completion of 1No. 3 Unit Classroom Block with 4 Seater KVIP & Urinal at Sankore SDA |
|  |  | Renovation of 1no. 6unit classroom Block at kukuom methoist primary |
|  |  | Completion of 1No. 3 Uint Classroom Block at Noberkaw |
|  |  | Completion of 1No. 3 Unit Classroom Block with 4 Seater KVIP and Urinal at Kukuom Methodist Primary |
|  |  | Completion of 2No. 3Unit Teacher's Quarters at Sikafremogya |
|  |  | Completion of 1No. 3Unit Classroom Block at Siiso |
|  |  | Completion of 1No 6 Unit Classroom Block at Kukuom Agric SHS |
|  |  | Completion of 1No. 3Unit Classroom Block with 4 Seater KVIP & Urinal and Supply of Furnitures at Abuom D/A JHS |

SUB-PROGRAMME 2.2 PUBLIC HEALTH SERVICES AND MANAGEMENT

Budget Sub-Programme Objective

- The objective of this sub program is to ensure sustainable, equitable and easily accessible healthcare services to the people within the district.

BUDGET SUB- PROGRAMME DESCRIPTION

This would be carried out through provision and prudently managing comprehensive and accessible health services with special emphasis on primary health care at the district, sub-district and community levels. The Sub-Programme also seeks to increase health infrastructure for efficient health care service delivery in the district.

The sub-programme seeks to:

- Ensure the construction and rehabilitation of clinics and health centres or facilities;

- Assist in the operation and maintenance of all health facilities under the jurisdiction of the district;

- Undertake health education and family immunization and nutrition programmes;

- Coordinate works of health centres or posts or community based health workers;

- Promote and encourage good health, sanitation and personal hygiene;

- Facilitate diseases control and prevention;

- Discipline, post and transfer health personnel within the district.

- Facilitate activities relating to mass immunization and screening for diseases treatment in the district.

- Facilitate and assist in regular inspection of the district for detection of nuisance of any condition likely to be offensive or injurious to human health;

- Regulate any trade or business which may be harmful or injurious to public health or a source of danger to the public or which otherwise is in the public interest to regulate;

The funding source for this programme are Internally Generated Fund, District Assemblies’ Common Fund, District Development Facility and donor support. Community members, development partners and departments are the beneficiaries of this sub-programme.

The District Health Directorate in collaboration with other departments and donors would be responsible for this sub-programme.

Challenges in executing the sub-programme include:

- Donor polices are sometimes challenging

- Low funding for infrastructure development

- Limited office and staff accommodation and those available are dilapidated

- Low sponsorship to health personnel to return to the district and work

- Inequitable distribution of health personnel (doctor, nurses)

BUDGET SUB-PROGRAMME RESULTS STATEMENT

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-programme. The past data indicates actual performance whilst the projections are the District’s estimate of future performance

TABLE 17: BUDGET SUB-PROGRAMME RESULTS STATEMENT

| Main Outputs | Output Indicators | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2021 | 2022as at Aug | 2023 | 2024 | 2025 | 2026 |
| Access to health service delivery improved | Number of functional Health centres constructed | 1 | 1 | 3 | 4 | 4 | 4 |
|  | No. of nurses quarters constructed/renovated | 1 | 2 | 2 | 2 | 2 | 2 |
| Increased education to communities on communicable diseases | Number of communities sensitised | 2 | 6 | 2 | 2 | 2 | 2 |
| Train health staff on health delivery | Number of health staff trained | 27 | - | 10 | 15 | 15 | 20 |

BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

TABLE 18: BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

| Standardized Operations | Standardized Projects |
| --- | --- |

| Support for National Immunization Day (NID) |  | Completion of Male & Female Ward at Kukuom |
| --- | --- | --- |
| Malaria prevention activities |  | Extension of Male Hostel with 3 No. Teacher's Quarters at Kwapong |
| District response initiative (DRI) on HIV/AIDS |  | Construction of CHPS Compound at Weijakrom |
| Public Health services |  | Construction of 1No. Maternity Block at Kwapong |
| Support to COVID 19 |  | Construction of Maternity Block at Noberko |
|  |  | Completion of Health Cerntre at Anwiam |

SUB-PROGRAMME 2.3 SOCIAL WELFARE AND COMMUNITY DEVELOPMENT

Budget Sub-Programme Objective

- Empower communities to shape their future by utilisation of their skills and resources to improve their standard of living.

- To integrate the vulnerable, Persons with Disability, the excluded and Disadvantaged into the mainstream of society.

- Establish an effective and efficient social protection system.

BUDGET SUB- PROGRAMME DESCRIPTION

The sub-programme seeks to improve community’s well-being through utilization of their skills and resources and promoting social development with equity for the disadvantaged, the vulnerable, persons with disabilities and excluded. The sub programme is undertaken by two units; they are the Community Development Unit and Social Welfare Unit.

The community development unit assists to organize community development programmes to improve and enrich rural life through:

- Literacy and adult education classes;

- Voluntary contribution and communal labour for the provision of facilities and services such as water, schools, library, community centres and public places of convenience or;

- Teaching deprived or rural women in home management and child care.

The Social Welfare unit aims at the promotion and protection of rights of children seek justices and administration of child related issues and provide community care for disabled and needy adults.  The Social Welfare unit performs the functions of juvenile justice administration, supervision and administration of Orphanages and Children Homes and support to extremely poor households. The unit also supervises standards and early childhood development centres as well as persons with disabilities, shelter for the lost and abused children and destitute.

The public including the rural populace are the main beneficiaries of services rendered by this sub-programme. Fund sources for this sub-programme include GoG, IGF and DACF. A total of 5officers would be carrying out this sub-programme

Major challenges of the sub-programme include Lack of motorbikes to enable field officers to reach the grassroots level for development programmes; delay in release of funds.

BUDGET SUB-PROGRAMME RESULTS STATEMENT

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-programme. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.

TABLE 19: BUDGET SUB-PROGRAMME RESULTS STATEMENT

| Main Outputs | Output Indicators | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2021 | 2022 as at August | 2023 | 2024 | 2025 | 2026 |
| Enrolment of more people into LEAP | No. of people enrolled | - | - | 150 | 150 | 150 | 150 |
| Organize 30 women groups for local food processing | No. of Groups organized | 15 | 30 | 30 | 30 | 30 | 30 |
| Financial Support to PWDs | No. of PWDs supported financially | 150 | 28 | 150 | 200 | 200 | 200 |
| Increase the livelihood of community members | Number of people trained on agro-processing | 50 | 100 | 100 | 100 | 150 | 150 |
| Monitor activities of early childhood development centre (conduciveness of the environment, | Number of childhood development centres monitored | 5 | 15 | 25 | 30 | 30 | 50 |
| Attendants in day care trained on psychology of children and how to give children a better start-off | Number of day care centres trained | 8 | 20 | 30 | 35 | 45 | 50 |

BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

TABLE 20: BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

| Standardized Operations | Standardized Projects |
| --- | --- |

| Social intervention programs |  |  |
| --- | --- | --- |
| Gender empowerment and mainstreaming |  |  |
| Community mobilization |  |  |
| Child right promotion and protection |  |  |
| Combating domestic violence and human trafficking |  |  |

SUB-PROGRAMME 2.4 BIRTH AND DEATH REGISTRATION SERVICES

BUDGET SUB-PROGRAMME OBJECTIVE

The objectives of the birth and death registry are

- To register infant births.

- To register deaths that occur

BUDGET SUB- PROGRAMME DESCRIPTION

The sub program is designed to educate and sensitize the Public on Infant birth registration and death registration especially in Kukuom and Sankore Registries. It is important that the Public will know the purpose and benefits of infants’ registration and death registrations. This sub program is being undertaken by the Birth and Death Registry.

TABLE 21: BUDGET SUB-PROGRAMME RESULTS STATEMENT

| Main Outputs | Output Indicators | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2021 | 2022 as at August | 2023 | 2024 | 2025 | 2026 |
| Public Education and Sensitization of Infant birth registration and death registration | Number of infant births registered | 100% | 90% | 100% | 100% | 100% | 100% |
|  | Number of infant deaths registered | 100% | 80% | 100% | 100% | 100% | 100% |

BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

Table 22: Budget Sub-Programme Standardized Operations and Projects

| Standardized Operations | Standardized Projects |
| --- | --- |
| Maximum registration and certification of infants |  |
| Purpose and benefits of infants’ registration and death registrations |  |

SUB-PROGRAMME 2.5 ENVIRONMENTAL HEALTH AND SANITATION SERVICES

Budget Sub-Programme Objective

  - Improve access to sanitation

  - Manage waste, reduce pollution and noise

  - Accelerate the provision of improve environmental sanitation

BUDGET PROGRAMME DESCRIPTION

The sub programme is carried out by the Environmental Health Unit of the Assembly.  The unit seeks to provide environmental and sanitation services within the district. The programme is to make sure and manage the liquid and solid waste across the district.

The programme manage by twenty two staff. The funding source for this sub programme are Internally Generated Fund, District Development Facility, and District Assemblies’ Common Fund. The general public is the beneficiary of environmental health and sanitation services sub programme.

The challenges for the sub programme are apathy on the part of citizens towards improved sanitation and inadequate funding.

TABLE 23: BUDGET SUB-PROGRAMME RESULTS STATEMENT

| Main Outputs | Output Indicators | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2021 | 2022 as at August | 2023 | 2024 | 2025 | 2026 |
| Improved Sanitation | No. of communities declared ODF basic | - | - | 2 | 2 | 2 | 2 |
|  | No. of communities declared ODF proper | - | - | 1 | 1 | 1 | 1 |
|  | No. of sanitary offenders prosecuted | 23 | - | 10 | 5 | 4 | 2 |
|  | No. of sanitation campaigns organised | - | - | 10 | 10 | 15 | 20 |
| Food vendors medically screened and licenced | No. of venders screened and licenced | 2000 | 1148 | 2000 | 2348 | 2500 | 2500 |
| Stray animals arrested | No. of animals | - | - | 10 | 5 | 5 | 5 |

BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

TABLE 24: BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

| Standardized Operations | Standardized Projects |
| --- | --- |
| Environmental sanitation Management | Rehabilitation of 17No. Borehole within the District |
| Solid waste management | Drilling of 4No. Borehole and Installation of Hand Pump within the District |
| Institutional Latrines maintenance and Liquid waste management | Maintenance of existing Boreholes |
| Sensitize some selected communities on dangers of open defecations (CLTS) |  |
| Development and Management of Waste Landfill Sites |  |
| Institute monthly and quarterly clean up exercises in all five sub-districts and communities |  |
| Refuse collection and disposal (solid waste management) |  |

PROGRAMME 3: INFRASTRUCTURE DELIVERY AND MANAGEMENT

BUDGET PROGRAMME OBJECTIVES

  - Develop human and institutional capacities for land use planning

  - To provide socioeconomic infrastructure and ensure periodic review of plans for construction and general maintenance of all public properties and drains

BUDGET PROGRAMME DESCRIPTION

The programme is responsible for provision of physical and socioeconomic infrastructure while promoting a sustainable human settlement development on principle of efficiency, orderliness, safe and healthy growth of communities.

The various units involved with the delivery of the program include;

- Physical Planning Department

- District Works Department.

- Road and Transport unit

The sub-programme seeks to provide quality infrastructure development and also educating members with road and building regulations,

Fifteen officers would be carrying out this sub-programme, nine works officers, five physical officers and one road and transport officer

The programmme is to be funded with transfers from the Central Government, District Assembly Common Fund (DACF), District Development Facility (DDF) and the Internally Generated fund – IGF. The beneficiaries of this programme are Road Users, Estate Developers, Traditional Authorities, Land Owners, Contractors, Public Infrastructure users and the general public.

SUB-PROGRAMME 3.1 PHYSICAL AND SPATIAL PLANNING DEVELOPMENT

BUDGET SUB-PROGRAMME OBJECTIVE

- To facilitate the implementation of such polices in relation to physical planning, land use and development within the framework of national polices.

BUDGET SUB-PROGRAMME DESCRIPTION

This bub-programme seeks to ensure planning, management and promotion of harmonious, sustainable and cost effective development of human settlements in accordance with sound environmental and planning principles. Specific functions of the sub-programme include:

- Preparation of physical plans as a guide for the formulation of development policies and decisions and to design projects in the district.

- Identify problems concerning the development of land and its social, environmental and economic implications;

- Advise on setting out approved plans for future development of land at the district level;

- Advise on preparation of structures for towns and villages within the district;

- Assist to offer professional advice to aggrieved persons on appeals and petitions on decisions made on their building;

- Facilitate consultation, co-ordination and harmonization of developmental decisions into a physical development plan;

- Assist to provide the layout for buildings for improved housing layout and settlement;

- Ensure the prohibition of the construction of new buildings unless building plans submitted have been approved by the Assembly;

- Advise the Assembly on the siting of bill boards, masts and ensure compliance with the decisions of the Assembly;

- Advise on the acquisition of landed property in the public interest; and

- Undertake street naming, numbering of house and related issues.

The organizational unit that will be involved is the Town and Country Planning unit and t Asunafo South District has one (5) staff; Technical Officer.

The sub-programme is funded through the DACF, GOG and the Internally Generated Revenue. The larger community and other departments of the Assembly stand to benefit greatly in this sub-programme. The main challenge confronting the sub-Programme is the lack of staff to operate and supervise the implementation of programme and projects under the sub-programme. Inadequate resource both financial and in human resource to prepare base maps.

BUDGET SUB-PROGRAMME RESULTS STATEMENT

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-programme. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.

TABLE 25: BUDGET SUB-PROGRAMME RESULTS STATEMENT

| Main Outputs | Output Indicator |  | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2021 | 2022 as at August | 2023 | 2024 | 2025 | 2026 |
| Valuation of Properties in Kukuom, Sankore, Noberkaw, Kwapong Townships | No. of properties valuated |  | - | - | 1385 | 1776 | 1800 | 1800 |
| Preparation of Base Maps and Local Plans | Number of communities with base maps |  | 6 | 8 | 11 | 15 | 18 | 18 |
|  | Number of communities with local plans |  | 7 | 8 | 9 | 11 | 15 | 15 |
| Street Named and Property Addressed | Number of streets named |  | 287 | 287 | 542 | 598 | 620 | 620 |
|  | Number of properties addressed | Businesses | 391 | 391 | 435 | 500 | 540 | 600 |
|  |  | properties | 1385 | 1385 | 1530 | 1840 | 2000 | 2100 |
| Statutory planning committee meeting organized | No. of statutory planning committee meetings organized |  | 4 | 2 | 6 | 6 | 6 | 6 |
| Create public awareness on development control | No. of public awareness organized |  | 2 | 7 | 9 | 9 | 12 | 15 |

BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

TABLE 26: BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

| Standardized Operations | Standardized Projects |
| --- | --- |
| Land use and Spatial planning |  |
| Street Naming and Property Addressing System |  |
| Valuation of Properties |  |
| Preparation of Base Maps and Local Plans |  |
| Statutory planning committee meeting |  |
| Creation public awareness on development control |  |
| Issuance of development permits |  |

SUB-PROGRAMME 3.2 Public Works, Rural Housing and Water Management

Budget Sub-Programme Objective

The objectives of this sub program are to;

  - Facilitate sustainable and resilient infrastructure development & maintenance, and basic service provision.

  - Implement integrated water resources management

BUDGET SUB PROGRAMME DESCRIPTION

The sub-programme is tasked with the responsibility of developing and implementing appropriate strategies and programmes that aims to improve the living conditions of rural dwellers through efficient infrastructures relative to housing and water supply. The department of Works is delivering the sub-programme.  The sub-program operations include;

  - Facilitating the implementation of policies on works and report to the Assembly

  - Assisting to prepare tender documents for all civil works projects to be undertaken by the Assembly through contracts or community initiated projects.

  - Facilitating the construction, repair and maintenance of public buildings and drains along any streets in the major settlements in the district.

  - Facilitating the provision of adequate and wholesome supply of potable water for the entire district

  - Assisting in the inspection of projects undertaken by the District Assembly with relevant Departments of the Assembly.

  - Provide technical and engineering assistance on works undertaken by the Assembly.

The Public Works Service sub programme is carried out with a total staff strength of nine (9).The beneficiaries of this sub programme are Assembly staff, property owners and the general public. The sources of fund for this sub programme are IGF, DACF, GOG and DDF.

Key challenges of the department include delay in release of funds, limited capacity (water and sanitation engineers, hydro geologists) to effectively deliver water and sanitation project, difficult hydro-geological terrain results in low success rate in borehole drilling, inadequate personnel and logistics (especially motorbikes) for monitoring of operation and maintenance of existing systems and other infrastructure. Another key challenge is inadequate and late release of funds. This leads to wrong timing of operations and projects thereby affecting implementation of projects and operations.

SUB-PROGRAMME RESULTS STATEMENT

The table below indicates the main outputs, its indicators and projections by which the Assembly measures the performance of the sub programme;

Table 27: Budget Sub-Programme Results Statement

| Main Outputs | Output Indicators | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2021 | 2022 as at August | 2023 | 2024 | 2025 | 2026 |
| Project inspection | No. of site meetings organised | 12 | 8 | 16 | 18 | 18 | 16 |
| Increase electricity coverage | No. of communities connected to the national grid | 6 | 3 | 4 | 6 | 7 | 4 |
| WSMTs formed and trained | No. of WMTSs formed and trained | 2 | 0 | 4 | 3 | 2 | 4 |
| Improved condition of feeder road | Km of motorable road | 24 | 12 | 16 | 34 | 26 | 24 |
| Portable water coverage improved | No. of boreholes provided | 4 | 2 | 8 | 12 | 8 | 12 |
|  | No. of boreholes mechanized | 2 | 1 | 6 | 4 | 6 | 4 |

Budget Sub-Programme Standardized Operations and Projects

Table 28: Budget Sub-Programme Standardized Operations and Projects

| Standardized Operations | Standardized Projects |
| --- | --- |
| Supervision and regulation of infrastructure development | Maintenance of Street Lights |
| Facilitate the formation of WATSAN groups | Construction of 1No. Community Durbar Ground |
| Logistical Support for the Operations of the Works department | Self Help projects |
| Routine Monitoring of programmes and projects |  |

SUB-PROGRAMME 3.3 ROADS AND TRANSPORT SERVICES

BUDGET SUB-PROGRAMME OBJECTIVE

The objectives of this programme are to;

  - Promote resilient infrastructural development & maintenance, and basic service provision with regards to road network within the area.

  - Ensure sustainable development and management of the transport sector

BUDGET SUB- PROGRAMME DESCRIPTION

This Sub-Program provides basic infrastructure support with regards to roads and transport. It involves the expansion of good road network, reshaping and acceleration of ongoing road projects and provision of awareness creation on safe driving practices.

The programme is mainly delivered road and transport unit under the Works Departments.

The programmme is funded with transfers from the Central Government, DACF, DDF and IGF. The beneficiaries of this programme are Road Users, Estate Developers, Traditional Authorities, Land Owners, Contractors, Public Infrastructure users and the general public.

TABLE 29: BUDGET SUB-PROGRAMME RESULTS STATEMENT

| Main Outputs | Output Indicators | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2021 | 2022 as at August | 2023 | 2024 | 2025 | 2026 |
| Feeder road construction and reshaping | Kilometre of feeder roads reshaped | 24 | 12 | 16 | 34 | 26 | 24 |

BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

TABLE 30: BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

| Standardized Operations | Standardized Projects |
| --- | --- |
| Management of transport services | Routine maintenance and spot Improvement of Feeder Roads |
|  | Reshaping of 20kms of Roads district wide |

PROGRAMME 4: ECONOMIC DEVELOPMENT

BUDGET PROGRAMME OBJECTIVES.

- Create an entrepreneurial society through the promotion and growth of micro and small enterprises (MSEs).

- To improve agricultural productivity through modernization along a value chain in a sustainable manner

Budget Programme Description

The economic development programme aims at providing enabling environment for Trade, Tourism and industrial development in the District. It also seeks to facilitate the modernization of agriculture to achieve self-sufficiency in food security in the District. The sub-programmes under the Economic Development programme include Trade, Tourism and Industrial Development and Agriculture Development.

Trade, Industry and Tourism sub programme under the guidance of the Assembly deal with issues related to trade, cottage industry and tourism in the district. The sub-programme seeks to:

- Facilitate the promotion and development of small scale industries in the District;

- Advise on the provision of credit for micro, small-scale and medium scale enterprises;

- Promote the formation of associations, co-operative groups and other organizations which are beneficial to the development of small-scale industries;

- Assist in offering business and trading advisory information services;

- Facilitate the promotion of tourism in the district;

- Assist to identify, undertake studies and document tourism sites in the district.

The Agriculture Development sub-programme seeks to:

- Provide agricultural extension services in the areas of natural resources management, and rural infrastructural and small scale irrigation in the district;

- Promote soil and water conservation measures by the appropriate agricultural technology;

- Promote agro-forestry development to reduce the incidence of bush fires;

- Promote an effective and integrated water management

- Assist in developing early warning systems on animals’ diseases and other related matters to animal production;

- Facilitate and encourage vaccination and immunization of livestock and control of animal diseases;

- Encourage crop development through nursery propagation;

- Develop, rehabilitate and maintain small scale irrigation schemes;

- Promote agro-processing and storage.

SUB-PROGRAMME 4.1 Trade, Tourism and Industrial Development

Budget Sub-Programme Objective

- Expand opportunities for job creation and improve efficiency and competitiveness of Micro, Small and Medium Enterprises (MSMEs).

- Promote sustainable tourism to preserve historical, cultural and natural heritage and attract tourist.

Budget Sub-Programme Description

The sub-programme seeks to improve the competitiveness of micro and small enterprises by facilitating the provision of development programmes and integrated support services. The National Board for Small Scale Industries / Business Advisory Centre (BAC) facilitates MSMEs access to Business development service though assisting entrepreneurs to increase their productivity, generate employment, and increase their income levels and contributing significantly towards the socio-economic development of the country. The clients are potential and practicing entrepreneurs in growth oriented sectors in the district. Services delivered seek to promote on-farm and off-farm activities. These would include facilitating access to training and other business development services, provision of advisory, counselling and extension services, provision of business information to potential and existing entrepreneurs and promotion of business associations.

Other service to be delivered under the sub-programme include,

- support to the creation of business opportunities;

- provide opportunities for MSMEs to participate in all Public-Private Partnerships (PPPs) and local content arrangements;

- facilitate the establishment of Rural Technology Facilities (RTF) in the District;

- Develop and market tourist sites, improve accessibility to key centres of population, production and tourist sites;

- promote local festivals in the district and;

- Provide incentives for private investors in hospitality and restaurant.

- The unit that will deliver this sub-programme is the District Assembly since the District does not have Business Advisory unit.

Budget Sub-Programme Results Statement

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-programme. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.

Table 31: Budget Sub-Programme Results Statement

| Main Outputs | Output Indicators | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2021 | 2022 as at August | 2023 | 2024 | 2025 | 2026 |
| Support entrepreneurs and SME development | Total beneficiaries of special SME interventions | 155 | 250 | 300 | 350 | 400 | 400 |
| Potential and existing entrepreneurs trained | No. of individuals trained on boutique tie and dye making | 55 | 70 | 75 | 80 | 85 | 90 |
|  | No. of individuals trained on soap making | 25 | 40 | 40 | 45 | 45 | 50 |
|  | No. of individuals trained on bread baking | 16 | 20 | 25 | 25 | 35 | 40 |
| Technical and financial support to artisans and SMEs | Total number of SMEs benefited | 85 | 150 | 200 | 200 | 200 | 200 |
|  | No. of new businesses established | 15 | 30 | 35 | 40 | 42 | 45 |
| MSE access to participate in trade fairs | No. of SMEs supported to attend trade fairs | 1 | 5 | 10 | 12 | 20 | 20 |

Budget Sub-Programme Standardized Operations and Projects

Table 32: Budget Sub-Programme Standardized Operations and Projects

| Standardized Operations | Standardized Projects |
| --- | --- |
| Promotion of Small, Medium and Large scale enterprises |  |
| Business Forum/LED Activities |  |
| Trade Development and Promotion |  |
| Small Business Management Training |  |
| Technical Training in Welding and Fabrications |  |
| Group Development Training in Group Dynamics |  |
| Business Plans Preparation |  |
| Technical Training in Soap Making |  |

SUB-PROGRAMME 4.2 Agricultural Services and Management

Budget Sub-Programme Objective

To modernise agriculture through economic structural transformation evidenced in food security, employment and reduced poverty.

Budget Sub-Programme Description

The Agricultural Development sub-programme seeks to promote thriving agriculture through research and efficient extension services to farmers, marketers and SMEs. Major services carried out under this sub-programme include

- Demonstrations and research to increase yields of crops and animals and persuade farmers to adopt technologies;

- Introduction of income generation livelihoods such as productive agricultural ventures (cocoa growing activities along the value chain that are income generating) and other alternative livelihoods;

- Promote efficient marketing and adding value to produce;

- Proper management of the environment through soil and water conservation, minimising bush fire, climate change hazards;

- Improve effectiveness and efficiency of technology delivery to farmers; and

- Networking and strengthening leakages between the department and other development partners.

The District Department of Agriculture will be responsible for the delivery of this sub – programme. The department has four units consisting of the following,

- Extension unit, which is in charge of extension of Agricultural Technologies and Information to the farmers and ensuring that these technologies are adopted.

- Women in Agriculture Development (WIAD) unit - responsible for mainstreaming gender issues in agriculture.

- Crop Unit - ensures that good agricultural practices in relation to crop production are adopted and to minimise post-harvest loses.

- Animal production and Health Unit - ensures that good animal husbandry practices and health are adopted.

The Department consist of sixteen (16) staff in delivering the sub-programme, funds would be sourced from GoG, DACF, and Donor (CIDA). Development partners, departments and the general public are the beneficiaries of this sub – programme.

Key challenges include

- Inadequate motorbikes and vehicles for field staff

- Inadequate accommodation for staff in the operational areas

- Inadequate agriculture extension agents (AEAs)

- Inadequate funding.

- Inadequate District Agric Office space.

BUDGET SUB-PROGRAMME RESULTS STATEMENT

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-programme. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.

TABLE 33: BUDGET SUB-PROGRAMME RESULTS STATEMENT

| Main Outputs | Output Indicators | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2021 | 2022 as at August | 2023 | 2024 | 2025 | 2026 |
| Promote agriculture as a viable business among the youth | Total number of young people engaged in the planting for food Programme (PFJ) | 6551 | 7427 | 13000 | 15000 | 15000 | 15000 |
| Capacity of Community Animal Health Workers built | No. of CAHW | 3 | 6 | 7 | 8 | 10 | 10 |
| Provision of small irrigation schemes | No. of dug-outs constructed | 1 | - | 10 | 10 | 10 | 10 |
| Gender mainstreaming Activities | No. of Women Streamed | 56 | 155 | 200 | 300 | 300 | 300 |
|  | No. of Male Streamed | 27 | 134 | 130 | 150 | 200 | 200 |
| Access to Agriculture Extension services | Number of Agriculture Extension officers | 12 | 10 | 15 | 15 | 15 | 15 |
|  | Total No. of farmers engaged | 23,761 | 19,945 | 25,000 | 25,000 | 25,000 | 25,000 |
| Support vulnerable farmers with inputs | No. of vulnerable farmers benefited | 23 | 5 | 30 | 30 | 40 | 40 |

Budget Sub-Programme Standardized Operations and Projects

Table 34: Budget Sub-Programme Standardized Operations and Projects

| Standardized Operations | Standardized Projects |
| --- | --- |
| Conduct Field Visits and Supervision Exercises |  |
| Conduct demonstrations on improved varieties (maize, sorghum, cowpea, and rice, protein & mineral containing food, and Post-Harvest Managements |  |
| Promote agriculture as a viable business among the youth |  |
| Improve Post-Harvest Management |  |
| Enhance the application of science, technology and innovation |  |
| Agricultural Research and Demonstration Farms |  |
| Sensitize FBOs and out-growers on extension delivery and value chain concept |  |
| Capacity and support farmers expand and improve the quality of seedling |  |
| Organize campaign on prophylactic treatment of livestock and poultry |  |
| Organize mass vaccination against schedule diseases (anthrax, rabbis, blackleg, new castle, coccidiosis, |  |
| Facilitate the acquisition of improved breeds by livestock and poultry farmers district wide |  |

## PROGRAMME 5: ENVIRONMENTAL MANAGEMENT

BUDGET PROGRAMME OBJECTIVES

- To plan and implement programmes to prevent and/or mitigate disaster in the District within the framework of national policies

Budget Programme Description

The programme will deliver the following major services:

- Organize public disaster education campaign programmes to: create and sustain awareness of hazards of disaster; and emphasize the role of the individual in the prevention of disaster;

- Education and training of volunteers to fight fires including bush fires, or take measures to manage the after effects of natural disasters;

- Assist in post-emergency rehabilitation and reconstruction efforts in the event of disasters;

- In consultation and collaboration with appropriate agencies, identify disaster zones and take necessary steps to; educate people within the areas, and prevent development activities which may give rise to disasters in the area;

- Post disaster assessment to determine the extent of damage and needs of the disaster area;

- Co-ordinate the receiving, management and supervision of the distribution of relief items in the district;

- Inspect and offer technical advice on the importance of fire extinguishers;

- The Disaster Management and Prevention Department will be responsible in executing the programme.

SUB-PROGRAMME 5.1 Disaster Prevention and Management

Budget Sub-Programme Objective

- To enhance the capacity of society to prevent and manage disasters

- To improve the livelihood of the poor and vulnerable in rural communities through effective disaster management, social mobilisation and income generation.

Budget Sub-Programme Description

The sub-programme seeks to promote disaster risk reduction as well as climate change risk management. It is also to strengthen Disaster Prevention and Respond mechanisms of the District. The sub-programme is delivered through public campaigns and sensitisations; assisting in post-emergency rehabilitation and reconstruction of efforts; provision of first line response in times of disaster and; formation and training of community-based disaster volunteers. The Disaster Management and Prevention Department is responsible for executing the sub-programme. The larger public at the community levels are the beneficiaries of this sub-programme. Funds will be sourced from IGF, DACF and Central Government supports. Challenges which confront the delivery of this sub-programme are lack of adequate funding, low and unattractive remunerations, and unattractive conditions of work. In all, 16 NADMO officers will carry out the sub-programme.

Budget Sub-Programme Results Statement

The table indicates the main outputs, its indicators and projections by which the District measures the performance of this sub-programme. The past data indicates actual performance whilst the projections are the District’s estimate of future performance.

Table 35: Budget Sub-Programme Results Statement

| Main Outputs | Output Indicators | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2021 | 2022 as at August | 2023 | 2024 | 2025 | 2026 |
| Support to disaster victims | No. of Individuals supported | - | 5 | 10 | 15 | 20 | 25 |
| Sensitization on natural disasters | Number of sensitization programs held | 18 | 9 | 10 | 10 | 10 | 10 |
| Training for Disaster volunteers organized | No. of volunteers trained | 25 | 40 | 45 | 50 | 65 | 70 |
| Disaster prevention and mitigation | Total No. of community fora held | 320 | 160 | 350 | 350 | 400 | 400 |

Budget Sub-Programme Standardized Operations and Projects

Table 36: Budget Sub-Programme Standardized Operations and Projects

| Standardized Operations | Standardized Projects |
| --- | --- |
| Organize field training for Disaster volunteers groups |  |
| Train NADMO staffs for effective service delivery |  |
| Hold quarterly disaster committee meeting annually |  |
| Educate people to build their houses not on waterways but rather high lands identify flood prone areas. Identify safe havens |  |
| Formation anti-bushfire volunteer |  |
| Provided early warning system/ signals |  |
| Bush – fire campaign |  |

SUB-PROGRAMME 5.2 NATURAL RESOURCES CONSERVATION AND MANAGEMENT

The objectives of this sub program is to

- Develop recreational facilities and promote cultural heritage and nature conservation in the area.

- Conserve natural resources especially the forest reserves

BUDGET SUB PROGRAMME DESCRIPTION

This Sub-Programme aims at the conservation of natural resources to make them useful for future generations.  It focuses on activities that reverse degraded natural resources like planting and nurturing of trees to replace lost ones.

The sub programme is carried out by the forest services division. The beneficiaries of this sub programme are the general public.

SUB-PROGRAMME RESULTS STATEMENT

The table below indicates the main outputs, its indicators and projections by which the Assembly measures the performance of the sub programme;

TABLE 37: SUB-PROGRAMME RESULTS STATEMENT

| Main Output | Output Indicator | Past Years |  | Projections |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2021 | 2022 | Budget Year 2023 | Indicative Year 2024 | Indicative Year 2025 | Indicative Year 2026 |

BUDGET SUB-PROGRAMME STANDARDIZED OPERATIONS AND PROJECTS

Table 38: Budget Sub-Programme Standardized Operations and Projects

| Standardized Operations | Standardized Projects |
| --- | --- |