ASUNAFO SOUTH DISTRICT ASSEMBLY

KUKUOM-AHAFO REGION

APPROVED

COMPOSITE ANNUAL ACTION PLAN

FOR 2022

OCTOBER, 2021

STATEMENT OF APPROVAL OF 2022 ANNUAL ACTION PLAN

The General Assembly of the Asunafo South District Assembly at meeting held on 29TH October, 2021 deliberated on the 2022 Composite Annual Action Plan and subsequently gave approval for its implementation.

Date:…………………………………. 	…………………………………………

HON. ADUSE POKU

(DISTRICT CHIEF EXECUTIVE)

Date:………………………………….		………………………………………

ASAMOAH DAMOAH

(DISTRICT CO-ORD DIRECTOR)

Date:………………………………….		…………………………………………

HON. MOHAMMED ISHMAEL 								              (PRESIDING MEMBER)

1.0 INTRODUCTION

This Annual Action Plan was extracted from the District Medium Term Development Plan (2022-2025) prepared by the Assembly to accelerate the development process of the District with guidelines from the National Development Planning Commission. Aside the guidelines, the Agender for Jobs II formed the main basis for the preparation of the Assemblies Development plan. It contains programmes and projects that the Assembly together with its department has outlined to execute or undertake for the year 2022.

1.1 Size, Location and Population

The Asunafo South District, one of the six districts of the Ahafo Region were carved out from the Asunafo District Assembly after it was split into Asunafo North and South in 2004 with Kukuom as the capital. The district has an estimated land size of about 922 kilometers square and is located at the southern part of the Ahafo Region with the eastern frontier forming the geographical and administrative boundary separating the Ahafo Region from the Ashanti Region.

The district shares common boarders with the Asunafo North District to the north and the Juaboso District to the South-West. Other adjoining Districts are the Sefwi-Wiaso District to the South-East, and Atwima Mponua District to the East

The District has a total population of 91,693 with 51.2% males and 48.8% females according to the 2021 population and housing census data released by the Ghana Statistical Service

1.2 KEY DEVELOPMENT ISSUES

Below are some of the key development issues confronting the District;

- Poor marketing systems

- Inadequate development, investment in processing and value addition

- Poor farm-level practices

- High unemployment among the youth.

- Inadequate seed capital for businesses to grow

- Poor compensation payment to affected persons

- Low level of husbandry practices

- Poor quality of education at all levels

- High number of untrained teachers at the basic level

- Gaps in physical access to quality health care

- Increasing morbidity, mortality and disability due to communicable, non-communicable and emerging diseases

- High incidence of HIV and AIDS among young persons

- Increasing demand for household water supply

- Inadequate maintenance of facilities

- Youth unemployment and underemployment among rural and urban youth

- Poor quality and inadequate road transport network

1.3 COMMUNITY NEEDS AND ASPIRATIONS

Prominent among the needs and aspirations outlined through the various levels of dialogue were the following:

- Extension of electricity to newly developed areas

- Provision of street light.

- Employment opportunities

- Establishment of effective waste management system.

- Provision of proper drainage system.

- Rehabilitation of town roads and feeder roads.

- Provision of adequate school infrastructure

- Provision of adequate market infrastructure

- Extension of water.

- Provision of adequate public toilet facilities.

- Provision of health facility.

- Intensification of Agric Extension Service.

- Provision of micro- credit scheme to boost economic activities.

1.2.4 ADOPTED DEVELOPMENT OBJECTIVES IN DMTDP 2022-2025

- Promote a demand-driven approach to agricultural development

- Enhance the application of science, technology and innovation

- Enhance inclusive and equitable access to, and participation in quality education at all levels

- Ensure affordable, equitable, easily accessible and Universal Health Coverage (UHC)

- Ensure the reduction of new HIV and AIDS/STIs infections, especially the among vulnerable groups

- Improve access to safe and reliable water supply services for all

- Enhance access to improved and reliable environmental sanitation services

- Promote effective participation of the youth in socioeconomic development

- Improve efficiency and effectiveness of road transport infrastructure and services

- Improve decentralized planning

- Strengthen fiscal decentralization

2.0 PLAN IMPLEMENTATION

A total of 167 activities have been outlined for implementation in 2022, With an estimated projects/programmes cost of GH¢10,561,086.66. The activities will be implementation with the support of Departments of the Assembly, Agencies and Non- governmental Organizations who are working within the jurisdiction of the District. The Departments, Agencies and NGO’s are expected to report quarterly on the status of their respective plans to the DPCU to collate and harmonize a composite report on the implementation of the District Annual Action Plan, 2022. Again, the DPCU will hold quarterly meetings to discuss on the report and finally submit it to the National Development Planning Commission and Regional Co-ordination Council respectively.

3.0 SOURCES OF FUNDS FOR THE IMPLEMENTATION OF THE PLAN

The funds are expected from IGF, DACF, GOG, Ground Rent, and District Development Facility, Development Partners and among others.  It is important to note that, since some departments are not yet fully integrated and operational; some programmes may not be budgeted for in the Assembly’s supplementary budget and annual estimates.

4.0 REVENUE IMPROVEMENT ACTION PLAN

A Revenue Improvement Action Plan has been prepared to effectively mobilize local resources for the implementation of the plan. The plan has identified key activities that will be carried out and these have the potential to improve the Assembly’s Internally Generated Funds. It is expected that when all the activities are implemented, other things being equal the Assembly internally generated revenue will increase averagely by 20 % over the 2021 figure.

ASUNAFO SOUTH DISTRICT ASSEMBLY

KUKUOM - AHAFO REGION

ANNUAL ACTION PLAN 2022

| Activity | location | Time Frame Qtr |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | QTR1 | QTR 2 | QTR 3 | QTR 4 | GOG | IGF | Others | New | Ongoing | Lead | Collaborating |
| Goal: Increase the standard of living and overall economic wellbeing for all people |  |  |  |  |  |  |  |  |  |  |  |  |
| Programmes 4: Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-programme 4.1: Trade, Tourism and Industrial Development |  |  |  |  |  |  |  |  |  |  |  |  |
| - Organize business management training for 30 MSME | Kukuom |  | √ | √ | √ | 5,500.00 | 1,000.00 | 500 | √ |  | BAC | GEA |
| - Formalization and Registration of Businesses | Districtwide | √ | √ | √ | √ | 7,000.00 | 2,000.00 | 3,000.00 | √ |  | BAC |  |
| - Organize training on soap and Detergent making for 30 people | Sankore, Kukuom | √ | √ | √ | √ | 9,000.00 | 3,000.00 | 2,500.00 | √ |  | BAC | GEA, CDO |
| - Organize training for 20 Oil Palm producers on modern ways of Palm oil extraction and processing | Kukuom | √ | √ | √ | √ | 4,000.00 | 1,000.00 | 3,000.00 | √ |  | BAC | DPU |
| - Organize management training for 20 Local Trade Associations | District Wide |  | √ | √ | √ | 3,500.00 | 1,500.00 | 2,000.00 | √ |  | BAC | DPU, DAD |
| - Organize Apprenticeship training and Support for 100 MSME | District Wide | √ | √ | √ | √ | 10,000.00 | 5,000.00 | 5,000.00 | √ |  | BAC |  |
| - Registration and accreditation of master crafts | Kukuom, Sankore | √ | √ | √ | √ | 200 | 300 | 1,000.00 | √ |  | BAC |  |
| - Organize OSHEM training for 20 Traditional caterers | Kukuom, Sankore | √ | √ | √ | √ | 2,000.00 | 1,000.00 |  | √ |  | BAC | DEHU |
| - Organize business management training for 30 MSME | Kukuom |  | √ | √ | √ | 2,500.00 | 1,000.00 | 500 | √ |  | BAC | GEA |
| - Update data on business establishment, market surveys of selected food items and others |  | √ | √ | √ | √ | 5,000.00 | 2000 |  | √ |  | Statistics | BACD, DA |
| - Regular inspection and monitoring of Tourism facilities in the District | District wide |  |  |  |  | 1,000.00 | 200 |  | √ |  | GIS, DEHU | , EPA, GNFS |
| - Creation of craft shops near tourism attraction sites. | Kukuom, Sankore | √ | √ | √ | √ | 6,000.00 | 200 |  | √ |  | CNC | DA |
| - Support for community-initiated projects | District wide | √ | √ | √ | √ | 12,000.00 | 5000 |  | √ |  | DWD | DA |
| SUB -TOTAL |  |  |  |  |  | 67,700.00 | 23,200.00 | 17,500.00 |  |  |  |  |
| Sub-programme 1.2: Agriculture Development |  |  |  |  |  |  |  |  |  |  |  |  |
| - Purchase 20 wellington boot for twenty staff members | Kukuom |  | √ |  |  | 600 |  | 900 | √ |  | Dep't of Agric | Central Admin |
| - Collect weekly market data on commodity prices and movement from 2 market outlet by December 2024. | Kukuom Sankore, and Kwapong | √ | √ | √ | √ |  |  | 1,000.00 | √ |  | Dep't of Agric | ASDA |
| - Conduct one Poultry and Livestock survey | All Operational Areas | √ | √ |  |  |  |  | 2,160.00 | √ |  | Dep't of Agric | ASDA |
| - Conduct four (4) quarterly management meetings. | Kukuom | √ | √ | √ | √ |  |  | 120,000.00 | √ |  | Dep't of Agric | ASDA |
| - Conduct four (4) quarterly technical review meetings. | Kukuom | √ | √ | √ | √ |  |  | 2,000.00 | √ |  | Dep't of Agric | ASDA |
| - Participate in one RELC Regional Planning session. | Goaso |  |  | √ |  |  |  | 1,080.00 | √ |  | Dep't of Agric | ASDA |
| - Organize one stakeholder meeting to establish Municipal Agriculture Business Partnership programme | Kukuom | √ |  |  |  |  |  | 3,000.00 | √ |  | Dep't of Agric | RADU,ASDA |
| - Attend three (3) technical review meetings at Regional level. | Goaso | √ | √ | √ | √ |  |  | 1,000.00 | √ |  | Dep't of Agric | RADU , ASDA |
| - Organize one District farmers Day celebration to reward gallant farmers | Kukuom |  |  |  | √ |  |  | 1,000.00 | √ |  | Dep't of Agric | ASDA TA,Assembly Members |
| - Attend nine (9) staff training workshops at Regional level. | Goaso | √ | √ | √ | √ |  |  | 2,200.00 | √ |  | Dep't of Agric | RADU , ASDA |
| - Conduct monitoring and evaluation on all projects by DDA, DCD and other unit heads of the Assembly for all government flagship programmes. | all operational zones |  | √ | √ |  | 70,000 |  |  | √ |  | Dep't of Agric | DPCU, ASDA |
| - Conduct monitoring by DDA, DAOs, on AEAs' activities in the operational areas. | all operational zones | √ | √ | √ | √ |  |  | 4,200.00 | √ |  | Dep't of Agric | ASDA |
| - Conduct four (4) quarterly inspections to agro-input shops | all operational zones | √ | √ | √ | √ |  |  | 4,000.00 | √ |  | Dep't of Agric | ASDA |
| - Conduct field and home visits by AEAs. | All operational Areas of the district | √ | √ | √ | √ |  |  | 15,000.00 | √ |  | Dep't of Agric | ASDA |
| - Organize three (3) zonal RELC meetings. | all 4 zones of the district |  | √ | √ |  |  |  | 400 | √ |  | Dep't of Agric | ASDA |
| - Organize one District RELC meeting. | Kukuom |  |  | √ |  |  |  | 15,000.00 | √ |  | Dep't of Agric | RADU, ASDA |
| - Sensitize farmers and stakeholders on the menace and control of FAW | All Operational Areas of the district | √ | √ | √ | √ |  |  | 1,000.00 | √ |  | Dep't of Agric | ASDA |
| - Organize five training for farmers in communities on safe handling of agro chemicals | Kukuom, Noberkaw, Asufufuo, camp No1, Adomako, Yankye, Anwiam. | √ | √ | √ | √ |  |  | 5,000.00 | √ |  | Dep't of Agric | ASDA |
| - Organize one training for 20 women on mushroom production. | Kukuom, Sankore |  |  |  | √ |  |  | 3,000.00 | √ |  | Dep't of Agric | ASDA, BAC, NBSSI |
| - Train one women FBO on " farming as a business" | Kukuom, Sankore |  |  |  | √ |  |  | 1,500.00 | √ |  | Dep't of Agric | ASDA, BAC, NBSSI |
| - Train twenty (20) women in farming in Soap making | Dantano |  | √ | √ |  |  |  | 3,000.00 | √ |  | Dep't of Agric | ASDA, BAC, NBSSI, SWCD |
| - Organize three (3) trainings for 75 Livestock Farmers on Supplementary Feeding | Sankore Adomakokrom, Dantano, Siana | √ | √ |  |  |  |  | 2,000.00 | √ |  | Dep't of Agric | ASDA, BAC, NBSSI, SWCD |
| - Organize three (3) trainings for 75 Livestock farmers on improved housing | Sankore, Abuom, Dantano |  | √ | √ | √ |  |  | 1,800.00 | √ |  | Dep't of Agric | ASDA, BAC, NBSSI, SWCD |
| - Sensitization and Vaccination of Livestock | All 4 zones of the district | √ | √ | √ | √ |  |  | 900 | √ |  | Dep't of Agric | ASDA |
| - Train 120 farmers in two communities on postharvest management practices | Tanoso, Noberkaw | √ | √ | √ |  |  |  | 900 | √ |  | Dep't of Agric | ASDA |
| - Train thirty- five (35) agro dealers on PFJ modalities | Kukuom | √ | √ | √ | √ |  |  | 10,000.00 | √ |  | Dep't of Agric | ASDA |
| - Attend twenty-seven (27) Radio education and sensitization talk shows on Agriculture related issues. | all 4 zones of the district | √ | √ | √ | √ |  |  | 2,000.00 | √ |  | Dep't of Agric | Information centers |
| - Train two (2) FBOs on integrated soil fertility management (ISFM) | Kukuom | √ | √ |  |  |  |  | 1,500.00 | √ |  | Dep't of Agric | ASDA, RELC, SRI |
| - Establish two demonstrations on maize and rice on ISFM | Kukuom, Kokooso |  | √ | √ |  |  |  | 2,000.00 | √ |  | Dep't of Agric | ASDA, RELC, SRI |
| - Establish two demonstrations on plantain sucker multiplication | Pesewukrom, Abuom |  | √ | √ |  |  |  | 1,500.00 | √ |  | Dep't of Agric | ASDA, RELC, SRI |
| - Establish one varietal demonstration on tomato | Kokooso |  | √ | √ |  |  |  | 2,300.00 | √ |  | Dep't of Agric | ASDA, RELC, SRI |
| - Distribute 500 cockerels to farmers under RFJ | all 4 zones of the district |  | √ | √ |  |  |  | 2,000.00 | √ |  | Dep't of Agric | ASDA |
| - Nurse and distribute 40,000 seedlings (oil palm, coconut,) to 800 farmers | All 4 zones of the district | √ | √ | √ |  |  |  | 2,500.00 | √ |  | Dep't of Agric | ASDA |
| - facilitate the distribution of subsidized input to 40,000 farmers under PFJ | District Wide | √ | √ | √ |  |  |  | 4,000.00 | √ |  | Dep't of Agric |  |
| SUB -TOTAL |  |  |  |  |  | 70,600.00 | 0.00 | 219,840.00 |  |  |  |  |
| SUB -TOTAL 2 |  |  |  |  |  | 138,300.00 | 23,200.00 | 237,340.00 |  |  |  |  |
| Goal: Ensure efficiency, transparency and accountability in decentralized governance |  |  |  |  |  |  |  |  |  |  |  |  |
| Programmes 1: Management and Administration |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-programme 1.1: General Administration |  |  |  |  |  |  |  |  |  |  |  |  |
| - Strengthening of sub district structures | Kukuom, Kwapong, Sankore, Asarekrom, Abuom and Kokooso | √ | √ | √ | √ | 20,000.00 | 2000 |  | √ |  | CA | Other Department |
| - Organize regular town hall meetings / press meetings | Kukuom, Sankore, Kwapong | √ | √ | √ | √ | 10,000.00 | 5000 |  | √ |  | PLG Unit |  |
| - Convene 3no. General Assembly meetings | Kukuom | √ | √ | √ | √ | 25,000.00 | 1000 |  | √ |  | Cent Admin | Other Depts |
| - Convene 3no. EXECO meetings | Kukuom | √ | √ | √ | √ | 10,000.00 | 2000 |  | √ |  | Cent Admin |  |
| - Organize 3no. meetings of 5 statutory sub-committee | Kukuom | √ | √ | √ | √ | 7,000.00 | 1000 |  | √ |  | Cent Admin |  |
| - Organize quarterly Audit Committee meetings | Kukuom | √ | √ | √ | √ | 8,000.00 | 2000 |  | √ |  | Cent Admin | Internal Audit Unit |
| - Organize 1no. 6th March Anniversary celebration | Kukuom | √ | √ | √ | √ | 20,000.00 | 1000 |  | √ |  | Educ Dept | Cent Admin |
| - Organize 1no. Republic Day celebration | Kukuom | √ | √ | √ | √ | 1,000.00 | 1000 |  | √ |  | Cent Admin |  |
| - Organize quarterly Entity Tender Committee meetings | Kukuom | √ | √ | √ | √ | 8,000.00 | 2000 |  | √ |  | Proc Unit | Plg Unit |
| - Organize quarterly management and staff meetings | Kukuom | √ | √ | √ | √ | 10,000.00 | 1000 |  | √ |  | Cent Admin |  |
| - Organize quarterly PRCC meeting | Kukuom | √ | √ | √ | √ | 8,000.00 | 2000 |  | √ |  | Cent Admin | PM |
| - Procure office equipment and stationaries for the Assembly | Kukuom | √ | √ | √ | √ | 20,000.00 | 10,000.00 |  | √ |  | Proc Unit | PLG Unit |
| - Research, Documentation and Development of Heritage Sites Festivals and Sacred Grooves for Tourism | Kukuom, Tanoso – Dantano, Sankore, Asufufuo |  | √ | √ | √ | 5,000.00 | 100 | 10,000.00 | √ |  | CNC | Physical planning & MMDES, Traditional Authorities |
| - Departmental cultural orientation on various Customary/ Traditional Rites and courtesies. | Kukuom | √ | √ | √ | √ | 5,000.00 | 200 |  | √ |  | CNC | DA |
| - Radio Cultural info and education on Traditional/ Cultural Values and Ethics | Districtwide | √ | √ | √ | √ | 1,000.00 | 500 |  | √ |  | CNC |  |
| SUB-TOTAL |  |  |  |  |  | 158,000.00 | 30,800.00 | 10,000.00 |  |  |  |  |
| Sub-programme 1.2: Finance and Audit |  |  |  |  |  |  |  |  |  |  |  |  |
| - Prepare and implement Revenue Improvement Action Plan | Kukuom | √ | √ | √ | √ | 20,000.00 | 1000 |  | √ |  | Finance Dept. | CA |
| - Prepare and submit 12No. monthly trail balances |  | √ | √ | √ | √ |  | 15,000.00 |  | √ |  | Finance Dept. |  |
| - Prepare and submit 2022 Annual Financial Statements |  | √ | √ | √ | √ |  | 20,000.00 |  | √ |  | Internal Audit |  |
| - Undertake quarterly internal Audits of the Assembly |  | √ | √ | √ | √ |  | 2,000.00 |  | √ |  | Internal Audit |  |
| - Preparation of annual internal audit workplan for 2023 |  | √ | √ | √ | √ |  | 500.00 |  | √ |  | Internal Audit |  |
| - Preparation and submission of annual performance audits report |  | √ | √ | √ | √ |  | 500.00 |  | √ |  | Internal Audit |  |
| - Inspection and verification of procured items into stores |  | √ | √ | √ | √ |  | 500.00 |  | √ |  | Internal Audit |  |
| - Capacity building (workshops, conferences and seminars) |  |  |  |  |  | 23,000.00 |  |  | √ |  | Internal Audit |  |
| SUB -TOTAL |  |  |  |  |  | 43,000.00 | 39,500.00 | 0.00 |  |  |  |  |
| Sub-programme 1.3: Human Resource Management |  |  |  |  |  |  |  |  |  |  |  |  |
| - Organize 1no. refresher workshop on Performance Management System for LGS staff | Kukuom | √ | √ | √ | √ | 90,000.00 | 200 |  | √ |  | Cent Admin |  |
| - Organize 1no. training on service protocols for LGS staff | Kukuom | √ | √ | √ | √ | 80,000.00 | 100 |  | √ |  | HRD | PLG Unit |
| - Staff Appraisal for 2022 | Kukuom | √ | √ | √ | √ | 500.00 | 200 |  | √ |  | HRD |  |
| - Salary and Payroll Management | Kukuom | √ | √ | √ | √ | 2,456,907.30 | 500 |  | √ |  | HRD | Finance Dept. ASDA |
| - Prepare and submit 2023 capacity building plans |  |  |  |  |  | 10000 | 200.00 |  | √ |  | HRD |  |
| SUB -TOTAL |  |  |  |  |  | 2,637,407.30 | 1,200.00 | 0.00 |  |  |  |  |
| Sub-programme 1.4: Planning, Budgeting, Coordination and Statistics |  |  |  |  |  |  |  |  |  |  |  |  |
| - Organize quarterly DPCU meetings | Kukuom | √ | √ | √ | √ | 20,000.00 | 1000 |  | √ |  | Plg Unit |  |
| - Organize quarterly Budget C’ttee meetings | Kukuom | √ | √ | √ | √ | 10,000.00 | 1000 |  | √ |  | Budget Unit |  |
| - Preparation of composite Annual Action Plan and budget | Kukuom |  | √ | √ | √ | 10,000.00 | 5000 |  | √ |  | CA | Other Department |
| - Embark on monitoring and evaluation of projects/programmes | Districtwide | √ | √ | √ | √ | 50,000.00 | 5,000.00 |  | √ |  | DPCU | TA, HON. Assembly members |
| - Preparation and submission of 2022 quarterly and annual Progress reports |  | √ | √ | √ | √ | 10,000.00 | 5000 |  | √ |  | Plg Unit |  |
| - Undertake baseline survey of WASH services in the district |  | √ | √ | √ | √ | 0.00 | 10000 | 50,000.00 | √ |  | IRC | DA |
| - Prepare WASH Masterplan for the district |  | √ | √ | √ | √ |  | 2000 | 5,000.00 | √ |  | IRC | DA |
| SUB -TOTAL |  |  |  |  |  | 100,000.00 | 29,000.00 | 55,000.00 |  |  |  |  |
| Sub-programme 1.5: Legislative Oversights |  |  |  |  |  |  |  |  |  |  |  |  |
| - Hold quarterly DISEC meetings | Kukuom | √ | √ | √ | √ | 10,000.00 | 1000 |  | √ |  | Cent Admin | Security Agencies |
| SUB -TOTAL |  |  |  |  |  | 10,000.00 | 1,000.00 | 0.00 |  |  |  |  |
| SUB -TOTAL 2 |  |  |  |  |  | 2,948,407.30 | 101,500.00 | 65,000.00 |  |  |  |  |
| Goal: Create an environment supportive of personal development and wealth creation |  |  |  |  |  |  |  |  |  |  |  |  |
| Programmes 2. Social Services Delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-programme 2.1: Education, Youth &Sports Services |  |  |  |  |  |  |  |  |  |  |  |  |
| - Construction of 2No. 3-unit Classroom Block | Noberkaw Methodist | √ | √ | √ | √ | 600,000.00 |  |  |  | √ | DWD | DED, TA, Assembly Member |
| - Procure Dual Desk | District wide | √ | √ | √ | √ | 200,000.00 |  |  |  | √ | DED | DWD, TA, Assembly Member |
| - Construction of 1No. 3-Unit Classroom Block with office, staff common room, 3-Seater KVIP and supply of Furniture | Kukuom Girls Model School | √ | √ | √ | √ | 248,734.07 |  |  |  | √ | DWD | DED, TA, Assembly Member |
| - Completion of 1No. 3- Unit Classroom Block with Office and Staff Common Room | Nnayinanse JHS | √ | √ | √ | √ | 72,239.10 |  |  |  | √ | DWD | DED, TA, Assembly Member |
| - Renovation of 1No. 6-Unit Classroom Block | Kukuom Methodist Primary | √ | √ | √ | √ | 148,245.50 |  |  |  | √ | DWD | DED, TA, Assembly Member |
| - Construction of 1No. 2 bedroom master's bungalow | Kukuom Agric Senior High School | √ | √ | √ | √ |  |  | 402,833.52 | √ | √ | Ghana Gas | DWD, TA, Assembly Member |
| - Support for GES programmes; mock, SPAM, Teacher Appraisal, M&E etc. | Districtwide | √ | √ | √ | √ | 5,000.00 | 200 |  | √ | √ | GES | ASDA |
| - Organize my First Day at school for KG & Prim. 1 | District Wide | √ | √ | √ | √ | 3,000.00 | 200 |  | √ | √ | Cent Admin | Educ Dept |
| - Conduct School census | Districtwide |  | √ |  | √ | 3,000.00 | 2000 |  | √ | √ | GES |  |
| - Sensitization of parents and teachers on the learning needs of PWDs | District wide | √ | √ | √ | √ | 5,000.00 | 1000 |  | √ | √ | GES | SWCD |
| - Strengthening school management system | District wide |  | √ |  | √ | 5,000.00 | 2000 |  | √ |  | GES | MoE, PTA |
| - Provide scholarship and bursaries support to students | District wide |  |  |  |  | 10,000.00 | 5000 |  | √ |  | GES | ASDA |
| - Apprenticeship/vocational training for the youth (Soap Making, Bee Keeping, Fish Farming) | Anum, Noberkaw, Yankye, Kwapong, Kokooso Agyeikrom Kofibenkrom, Ntonso, Beposo No. 1 | √ | √ | √ | √ | 10,000.00 | 1000 | 30000 | √ |  | GDO, SWCD | DAD, YEA,BAC |
| SUB -TOTAL |  |  |  |  |  | 1,310,218.67 | 11,400.00 | 432,833.52 |  |  |  |  |
| Sub-programme 2.2: Public Health Services and Management |  |  |  |  |  |  |  |  |  |  |  |  |
| - Construction of CHPS Compounds | Amankwakrom | √ | √ | √ | √ |  |  | 543,090.00 |  | √ | DWD | DA, DHD |
| - Construction of 1No. 3bedroom Doctor's bungalow | Sankore Health Center | √ | √ | √ | √ |  |  | 590,991.98 | √ |  | Ghana Gas | DA, GHS |
| - Promote health education and outreach immunization and family planning services | Districtwide | √ | √ | √ | √ | 10,000.00 | 1000 |  | √ | √ | DHD | DA |
| - Support to HIV and AIDS and malaria awareness campaigns | District Wide | √ | √ | √ | √ | 5,000.00 |  |  | √ | √ | DHD | GHS |
| - Support Girls Iron Folic Tablet Supplement (GIFTS) | District Wide | √ | √ | √ | √ | 2,000.00 | 1000 |  | √ | √ | GHS | GES,DA |
| - Orientation of food vendor and school feeding contractors on good nutritional practices | District wide | √ | √ | √ | √ | 5,000.00 | 100 |  | √ | √ | DA | DEHU, school feeding desk officer, DHD |
| SUB -TOTAL |  |  |  |  |  | 22,000.00 | 2,100.00 | 1,134,081.98 |  |  |  |  |
| Sub-programme 2.3: Social Welfare and Community Development |  |  |  |  |  |  |  |  |  |  |  |  |
| - Child Rights Promotion and Protection | Districtwide |  | √ |  | √ | 1,000.00 | 100 |  | √ |  | SWCD | ASDA |
| - Provide financial assistance to 10 vulnerable children | District wide | √ | √ | √ | √ | 50,000.00 | 1000 |  | √ |  | SWCD | ASDA |
| - Organize the celebration of World Child Labour Day | Kukuom | √ | √ | √ | √ | 1,000.00 | 200 |  | √ |  | SWCD | ASDA |
| - Provide financial assistance to 300 PWDs | District wide | √ | √ | √ | √ | 15,000.00 | 1000 |  | √ |  | SWCD | ASDA |
| - Procure 20-wheel chairs for PWDs | District Wide | √ | √ | √ | √ | 20,000.00 | 2000 |  | √ |  | SWCD | ASDA |
| - Resolve 100 child related cases to promote and protect the rights of the child | District Wide | √ | √ | √ | √ | 1,000.00 | 500 |  | √ |  | SWCD | ASDA |
| - Organize 10no. community sensitization on child marriage, teenage pregnancy (child protection) in 10 communities | Kukuom, Noberkaw, Kwapong, Sankore, Asarekrom, Abuom, Kokooso, Siiso, Yankye, Mfrekrom | √ | √ | √ | √ | 3,000.00 | 1000 |  | √ |  | GDO, SWCD | GES, GHS |
| - Organize 1no. capacity building for 60 CCPC members | Kukuom | √ | √ | √ | √ | 10,000.00 |  |  | √ |  | SWCD | ASDA |
| - Organize quarterly child protection review meetings | Kukuom | √ | √ | √ | √ | 1,000.00 | 100 |  | √ |  | SWCD | ASDA |
| - Organize 1no. capacity building for MLIC members on case management, strengthening of referrals and linkage between social systems | Kukuom | √ | √ | √ | √ | 5,000.00 |  |  | √ |  | SWCD | ASDA |
| - Family Tribunal /Juvenile Court Sittings | Kukuom | √ | √ | √ | √ | 5,000.00 | 500 |  | √ |  | SWCD | ASDA |
| - Registration, Supervision/Inspection of Early Childhood Development Centers. | School of the Holy Spirit, Ayipe Emmanuel, Hopland, Rock Academy, Gentle Jesus International | √ | √ | √ | √ | 1,000.00 | 200 |  | √ |  | SWCD | GES, E.H |
| - Implementation of LEAP | The 382 LEAP implementing communities | √ | √ | √ | √ | 3,000.00 |  |  | √ |  | SWCD | Police, GES, TA Opinion Leaders, |
| - Casework with Families | Districtwide | √ | √ | √ | √ | 2,000.00 | 500 |  | √ |  | SWCD | DOVVSU, CHRAJ, TA, Opinion Leaders, Judicial Service |
| - Education on Teenage Pregnancy in 10 communities | Selected communities | √ | √ | √ | √ | 8,000.00 | 2000 |  | √ |  | DGDO | DA |
| - Training of 40 women on bead making |  | √ | √ | √ | √ | 2,000.00 | 1000 |  | √ |  | DGDO | SWCD, BAC |
| - Education and support on Menstrual Hygiene for JHS Students | Districtwide | √ | √ | √ | √ | 2,000.00 | 1000 |  | √ |  | DGDO | SWCD, GES |
| SUB -TOTAL |  |  |  |  |  | 130,000.00 | 11,100.00 | 0.00 |  |  |  |  |
| Sub-programme 2.4: Birth and Death Registration Services |  |  |  |  |  |  |  |  |  |  |  |  |
| - sensitization and registration of births and deaths | District wide | √ | √ | √ | √ | 4,500.00 | 500.00 |  | √ |  | BDD | GHS, traditional Authorities |
| - Capacity building (workshops, conferences and seminars) |  |  |  |  |  | 23,000.00 | 2000 |  | √ |  | Birth & Death Dept. |  |
| SUB -TOTAL |  |  |  |  |  | 27,500.00 | 2,500.00 | 0.00 |  |  |  |  |
| Sub-programme 2.5: Environmental Health and Sanitation Services |  |  |  |  |  |  |  |  |  |  |  |  |
| - Training of water vendors | Districtwide | √ | √ | √ | √ | 5,000.00 | 2000 |  | √ |  | Planning Unit | DWD, WVG |
| - Implementation of SHEP programmes i.e Sanitation, environment and safety systems in schools | Districtwide | √ | √ | √ | √ | 15,000.00 |  |  | √ |  | GES | ASDA, GHS |
| - Screening of food vendors, butcher meat sellers, drinking bar operators and School feeding Operators | Districtwide | √ | √ | √ | √ | 5,000.00 | 2000 |  | √ |  | DEHU | ASDA |
| - Intensify routine inspection and hygiene Education | District Wide | √ | √ | √ | √ |  | 2,000.00 |  | √ |  | DEHU | DGDO, PLg unit, DHD |
| - Fumigate and clearing of sanitary sites and public toilets | District Wide | √ | √ | √ | √ | 10,000.00 |  |  | √ |  | DEHO | DA |
| - Procurement of assorted sanitary tools | Kukuom | √ | √ | √ | √ | 15,000.00 | 1000 |  | √ |  | DA | DEHU |
| - Evacuation of refuse heaps | District Wide | √ | √ | √ | √ | 30,000.00 |  |  | √ |  | DEH | ASDA, Zoomlion Gh. |
| - Daily collection and disposal of refuse (SIP) | Districtwide | √ | √ | √ | √ | 10,000.00 |  |  | √ |  | DEH | ASDA, Zoomlion Gh. |
| - Mechanically push refuse heaps | Districtwide | √ | √ | √ | √ | 50,000 |  |  | √ |  | DWD | DEHU, DPCU |
| - Maintain final disposal site | Sankore | √ | √ | √ | √ | 20,000.00 |  |  | √ |  |  |  |
| - Arrest of stray animals | Districtwide | √ | √ | √ | √ | 500.00 |  |  | √ |  | DEH | Zoomlion Ghana |
| SUB -TOTAL |  |  |  |  |  | 160,500.00 | 7,000.00 | 0.00 |  |  |  |  |
| SUB -TOTAL 2 |  |  |  |  |  | 1,650,218.67 | 34,100.00 | 1,566,915.50 |  |  |  |  |
| Goal: Create an environment supportive of personal development and wealth creation |  |  |  |  |  |  |  |  |  |  |  |  |
| Programmes 3. Infrastructure Delivery and Management |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-programme 3.1: Physical and Spatial Planning Development |  |  |  |  |  |  |  |  |  |  |  |  |
| - Continuation of Street Naming and Property Addressing System | District wide |  |  |  |  | 5,000.00 |  |  |  | √ | DA | MLGRD, T&CPD, VRA, GNFS,Traditional Authorities, Private developers |
| - Preparation of structure and Local plans for the district | Kukuom | √ | √ | √ | √ | 100,000.00 |  |  | √ |  | DA | PPD, RCC, Trad. Authorities, Depts, LUSPA |
| - Strengthen the physical planning and Parks and Gardens Unit with the requisite logistics to perform | Kukuom | √ | √ | √ | √ | 6,000.00 |  |  | √ |  | DA | PPD, RCC, Trad. Authorities, Depts, LUSPA |
| - Train staff and Spatial Planning Committee members on new models and Legislation enacted on Physical Development | Kukuom | √ | √ | √ | √ | 5,000.00 |  |  | √ |  | DA | PPD, RCC, MLGRD, LGS,, Depts, LUSPA |
| - Create public awareness on greening of human settlements | Kukuom | √ | √ | √ | √ | 1,000.00 | 600 |  | √ |  |  | PPD, Trad. Authorities, Depts, Developers |
| - Organize monthly Spatial Planning Committee meetings | Kukuom | √ | √ | √ | √ | 1,000.00 | 500 |  | √ |  | PPD | Plg Unit |
| - Organize monthly Technical sub-committee meetings | Kukuom | √ | √ | √ | √ | 2,000.00 | 500 |  | √ |  | PPD | Plg Unit |
| SUB -TOTAL |  |  |  |  |  | 120,000.00 | 1,600.00 | 0.00 |  |  |  |  |
| Sub-programme 3.2: Public Works, Rural Housing and Water Management |  |  |  |  |  |  |  |  |  |  |  |  |
| - Construction of Staff Quarters | Kukuom | √ | √ | √ | √ | 200,000.00 |  |  | √ |  | DWD | TA, Assembly members |
| - Completion of a police Station | Abuom |  |  |  |  | 295,836.40 |  |  |  |  | DWD | DA, GPS |
| - Completion of the first floor of 3-storey Administration Block | Kukuom | √ | √ | √ | √ | 100,000.00 |  |  |  | √ | DWD | TA, Assembly members |
| - Construction of a police Station/post | Sankore | √ | √ | √ | √ | 300,000.00 |  |  | √ | √ | DWD | DA, GPS |
| - Drilling and construction of boreholes, LMS and pipe systems | Pafo, New Sawereso, Kwapong Zango, Siana, Noberkwa Zango, Abodom, Kwadoma, Nyamebekyere , Mmeso, Berkyekrom, Tettekrom, Mamponteng | √ | √ | √ | √ | 800,000.00 |  |  | √ | √ | DWD | TA, Assembly members, IRC |
| - Reshaping/Spot Improvement/Rehabilitation of 6 km feeder roads | Districtwide | √ | √ | √ | √ | 350,000.00 |  |  | √ | √ | DWD | ASDA, |
| - Facilitate the organization of road safety campaigns | District wide | √ | √ | √ | √ | 15,000.00 | 1000 |  | √ |  | GRSA, MTTD | DA, GPRTU |
| - Construction of speed humps | District Wide | √ | √ | √ | √ | 8,000.00 | 2000 |  | √ | √ | GHA | DA |
| - Clearing of weedy road pedestrians’ walkways | District Wide | √ | √ | √ | √ | 7000 |  |  | √ | √ |  |  |
| - Facilitate the development of Telecommunication Network Infrastructure | District Wide | √ | √ | √ | √ | 5,000.00 |  |  | √ |  | Tel. Comm. Network Operators | ASDA |
| - Extension of electricity | District Wide | √ | √ | √ | √ | 30,000.00 |  |  | √ | √ | DWD | ASDA Assembly Members, NEDCO |
| - Construction of storm drains | Kukuom | √ | √ | √ | √ | 30,000.00 |  |  | √ |  | DWD | ADA, |
| - Desilting of Drains | Kukuom | √ | √ | √ | √ | 10,000.00 |  |  | √ | √ | DEH | ASDA, |
| - Maintenance of street lights | Districtwide | √ | √ | √ | √ | 98,000.00 |  |  | √ | √ | DWD | ASDA, |
| - Rehabilitate Staff bungalows | Kukuom | √ | √ | √ | √ | 85,000.00 |  |  | √ | √ | Wks Dept | Plg Unit/Proc Unit |
| SUB -TOTAL |  |  |  |  |  | 2,333,836.40 | 3,000.00 | 0.00 |  |  |  |  |
| SUB -TOTAL 2 |  |  |  |  |  | 2,453,836.40 | 4,600.00 | 0.00 |  |  |  |  |
| Goal: safeguard the natural environment and ensure a resilient built environment |  |  |  |  |  |  |  |  |  |  |  |  |
| Programmes 5. Mainstream emergency planning and preparedness into the District’s Development Planning agenda at all levels to respond to potential internal and external threats |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-programme 5.1: Disaster Prevention and Management |  |  |  |  |  |  |  |  |  |  |  |  |
| - Intensify disease surveillance at all levels | Districtwide | √ | √ | √ | √ | 5,000.00 | 1000 |  |  | √ | DHD | GHS |
| - Sensitizations on natural disasters | Kukuom, Noberkaw, Kwapong, Sankore and Abuom | √ | √ | √ | √ | 5,000.00 | 2000 |  |  | √ | NADMO | DA, Assembly Members, EPA, Fire Service, TA |
| - Support to disaster victims | District Wide | √ | √ | √ | √ | 20,000.00 |  |  |  | √ | NADMO | DA |
| - Organize outreach covid 19, HTC &TB services in the communities | District wide | √ | √ | √ | √ | 500 | 200 |  |  | √ | GHS | ASDA |
| - Support to COVID-19 vaccination exercise | District Wide | √ | √ | √ | √ | 5,000.00 | 1000 |  | √ | √ | GES | Cent Admin |
| - Embark on community education and sensitization programmes on COVID-19 vaccination | District wide | √ | √ | √ | √ | 5,000.00 | 2000 |  | √ | √ | Cent Admin | Comm Sub-Ct |
| SUB -TOTAL |  |  |  |  |  | 40,500.00 | 6,200.00 | 0.00 |  |  |  |  |
| Sub-programme 5.2: Natural Resource Conservation and Management |  |  |  |  |  |  |  |  |  |  |  |  |
| - Support to the regular visit and protection of the protected forest reserves in the district | Bonsam Bepo reserve, Abonwere reserve | √ | √ | √ | √ | 5,000.00 |  |  | √ |  | FC | DA |
| - organize regular education and sensitization programs, and monitor the activities of small-scale mining in the district | Noberkaw | √ | √ | √ | √ | 2,000.00 | 500 | 20,000.00 | √ |  | DA | EPA, GPS, GIS, TA, Hon. Assembly Members |
| - Regular monitoring of the waterbodies against the activities of small-scale mining Activities | District Wide | √ | √ | √ | √ | 10,000.00 |  | 5,000.00 | √ |  | Pln Unit | EPA |
| - Intensify regulations and bye laws against illegal logging and hunting | Districtwide | √ | √ | √ | √ | 5000 | 500 |  | √ |  | FC | DA, GPS |
| - Support and implement tree planting activities | Districtwide |  | √ | √ |  | 5,000.00 | 1000 |  | √ | √ | FC | ASDA, NADMO |
| - Support the Supply of improved and early maturing tree species seedlings | Districtwide |  | √ | √ |  | 6,000.00 | 400 |  | √ | √ | FC | DDA, ASDA |
| - Organize radio talk shows on natural disasters and climate change | Districtwide | √ | √ | √ | √ |  | 1,000.00 |  | √ |  | FC | DA, DPCU, EPA, NCCE, TA |
| SUB -TOTAL |  |  |  |  |  | 33,000.00 | 3,400.00 | 25,000.00 |  |  |  |  |
| SUB -TOTAL 2 |  |  |  |  |  | 73,500.00 | 9,600.00 | 25,000.00 |  |  |  |  |
| GRAND TOTAL 2 |  |  |  |  |  | 7,264,262.37 | 173,000.00 | 1,894,255.50 |  |  |  | 9,331,517.87 |