ASUNAFO SOUTH DISTRICT ASSEMBLY

KUKUOM-AHAFO REGION

APPROVED

COMPOSITE ANNUAL ACTION PLAN

FOR 2024

OCTOBER, 2023

STATEMENT OF APPROVAL OF 2024 ANNUAL ACTION PLAN

The General Assembly of the Asunafo South District Assembly at meeting held on 18TH October, 2023 deliberated on the 2024 Composite Annual Action Plan and subsequently gave approval for its implementation.

Date:…………………………………. 	…………………………………………

HON. ADUSE POKU

(DISTRICT CHIEF EXECUTIVE)

Date:………………………………….		………………………………………

OLIVER OPOKU YEBOAH

(DISTRICT CO-ORD DIRECTOR)

Date:………………………………….		…………………………………………

HON. MOHAMMED ISHMAEL

(PRESIDING MEMBER)

1.0 INTRODUCTION

This Annual Action Plan was extracted from the District Medium Term Development Plan (2022-2025) prepared by the Assembly to accelerate the development process of the District with guidelines from the National Development Planning Commission. Aside the guidelines, the Agender for Jobs II formed the main basis for the preparation of the Assemblies Development plan. It contains programmes and projects that the Assembly together with its department has outlined to execute or undertake for the year 2024.

1.1 Size, Location and Population

The Asunafo South District, one of the six districts of the Ahafo Region were carved out from the Asunafo District Assembly after it was split into Asunafo North and South in 2004 with Kukuom as the capital. The district has an estimated land size of about 922 kilometers square and is located at the southern part of the Ahafo Region with the eastern frontier forming the geographical and administrative boundary separating the Ahafo Region from the Ashanti Region.

The district shares common boarders with the Asunafo North District to the north and the Juaboso District to the South-West. Other adjoining Districts are the Sefwi-Wiaso District to the South-East, and Atwima Mponua District to the East

The District has a total population of 91,693 with 51.2% males and 48.8% females according to the 2021 population and housing census data released by the Ghana Statistical Service

1.2 KEY DEVELOPMENT ISSUES

Below are some of the key development issues confronting the District;

- Poor marketing systems

- Inadequate development, investment in processing and value addition

- Poor farm-level practices

- High unemployment among the youth.

- Inadequate seed capital for businesses to grow

- Poor compensation payment to affected persons

- Low level of husbandry practices

- Poor quality of education at all levels

- High number of untrained teachers at the basic level

- Gaps in physical access to quality health care

- Increasing morbidity, mortality and disability due to communicable, non-communicable and emerging diseases

- High incidence of HIV and AIDS among young persons

- Increasing demand for household water supply

- Inadequate maintenance of facilities

- Youth unemployment and underemployment among rural and urban youth

- Poor quality and inadequate road transport network

1.3 COMMUNITY NEEDS AND ASPIRATIONS

Prominent among the needs and aspirations outlined through the various levels of dialogue were the following:

- Extension of electricity to newly developed areas

- Provision of street light.

- Employment opportunities

- Establishment of effective waste management system.

- Provision of proper drainage system.

- Rehabilitation of town roads and feeder roads.

- Provision of adequate school infrastructure

- Provision of adequate market infrastructure

- Extension of water.

- Provision of adequate public toilet facilities.

- Provision of health facility.

- Intensification of Agric Extension Service.

- Provision of micro- credit scheme to boost economic activities.

1.2.4 ADOPTED DEVELOPMENT OBJECTIVES IN DMTDP 2022-2025

- Promote a demand-driven approach to agricultural development

- Enhance the application of science, technology and innovation

- Enhance inclusive and equitable access to, and participation in quality education at all levels

- Ensure affordable, equitable, easily accessible and Universal Health Coverage (UHC)

- Ensure the reduction of new HIV and AIDS/STIs infections, especially the among vulnerable groups

- Improve access to safe and reliable water supply services for all

- Enhance access to improved and reliable environmental sanitation services

- Promote effective participation of the youth in socioeconomic development

- Improve efficiency and effectiveness of road transport infrastructure and services

- Improve decentralized planning

- Strengthen fiscal decentralization

2.0 PLAN IMPLEMENTATION

A total of 251 activities have been outlined for implementation in 2024, With an estimated projects/programmes cost of GH¢14,948,062.90. The activities will be implementation with the support of Departments of the Assembly, Agencies and Non- governmental Organizations who are working within the jurisdiction of the District. The Departments, Agencies and NGO’s are expected to report quarterly on the status of their respective plans to the DPCU to collate and harmonize a composite report on the implementation of the District Annual Action Plan, 2024. Again, the DPCU will hold quarterly meetings to discuss on the report and finally submit it to the National Development Planning Commission and Regional Co-ordination Council respectively.

3.0 SOURCES OF FUNDS FOR THE IMPLEMENTATION OF THE PLAN

The funds are expected from IGF, DACF, GOG, Ground Rent, and District Development Facility, Development Partners and among others.  It is important to note that, since some departments are not yet fully integrated and operational; some programmes may not be budgeted for in the Assembly’s supplementary budget and annual estimates.

4.0 REVENUE IMPROVEMENT ACTION PLAN

A Revenue Improvement Action Plan has been prepared to effectively mobilize local resources for the implementation of the plan. The plan has identified key activities that will be carried out and these have the potential to improve the Assembly’s Internally Generated Funds. It is expected that when all the activities are implemented, other things being equal the Assembly internally generated revenue will increase averagely by 20 % over the 2023 figure.

ASUNAFO SOUTH DISTRICT ASSEMBLY

KUKUOM - AHAFO REGION

ANNUAL ACTION PLAN 2024

| Activity | location | Time Frame Qtr |  |  |  |  |  |  | Programme Status |  | Implementing Institution/Department |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | QTR1 | QTR 2 | QTR 3 | QTR 4 | GOG | IGF | OTHERS | New | Ongoing | Lead | Collaborating |
| Goal: Increase the standard of living and overall economic wellbeing for all people |  |  |  |  |  |  |  |  |  |  |  |  |
| Programmes 4: Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-programme 4.1: Trade, Tourism and Industrial Development |  |  |  |  |  |  |  |  |  |  |  |  |
| - Provide Ghana Enterprise Agency (GEA) grant for 20 entrepreneurs under the Ghana Jobs and Skills (GJS) | 6 area councils | √ | √ | √ | √ | 10,000.00 | 0 | 2,000.00 | √ |  | BAC | DA, GEA |
| - Formalization, Registration and certification of Businesses | 6 area councils | √ | √ | √ | √ | 0 | 0 | 30,000.00 | √ |  | BAC | DPU |
| - Organize a community Base Training (CBT) on soap and Detergent making for 40 people | Kukuom | √ | √ | √ | √ | 8,000.00 | 1,000.00 | 1,000.00 | √ |  | BAC/Agric | DA, GDO |
| - Organize Business Adversary and counselling sections for 40 youth | 6 area councils | √ | √ | √ | √ | 3,000.00 | 1,000.00 |  | √ |  | BAC | DPU |
| - Registration and certification of master crafts National Vocational and Training Institute (NVTI) | Kukuom, Sankore | √ | √ | √ | √ | 0 | 1,000.00 | 3,000.00 | √ |  | BAC |  |
| - Regular inspection and monitoring of Tourism facilities in the district | 6 area councils |  |  |  |  | 1,210.00 | 242 | 0 | √ | √ | GIS, DEHU | , EPA, GNFS |
| - Creation of craft shops near tourism attraction sites. | Kukuom, Sankore | √ | √ | √ | √ | 7,260.00 | 242 | 0 | √ |  | CNC | DA |
| SUB -TOTAL |  |  |  |  |  | 29,470.00 | 3,484.00 | 36,000.00 |  |  |  |  |
| Sub-programme 4.2: Agricultural Services and Management |  |  |  |  |  |  |  |  |  |  |  |  |
| - 8. Maintenance of office Equipment and Purchase of Stationery for office use | Kukuom | √ | √ | √ | √ | 1,500.00 | 500 | 0 | √ |  | DDA | ASDA |
| - Undertake monthly field monitoring visits to collect relevant data | Kukuom, Noberkaw, Adomakokrom, Kwapong,Sankore | √ | √ | √ | √ | 2,000.00 | 0 | 0 | √ |  | DDA | ASDA |
| - Organize farmers’ day celebration |  | √ | √ | √ | √ | 70,000.00 |  |  | √ |  | DDA | ASDA |
| - Undertake weekly market data/information collection exercise on major food commodities and input availability and prices in the district | Kukuom, Kwapong,Sankore | √ | √ | √ | √ | 2,400.00 | 0 | 0 | √ |  | DDA | ASDA |
| - Conduct quarterly M&E results dissemination and communication | Sankore,Kukuom, Abuom, Kwapong | √ | √ | √ | √ | 1,800.00 | 500 | 0 | √ |  | DDA | ASDA |
| - Produce 4 quarterly, 1 mid-year, 1 annual progress and 3 situational reports | Kukuom | √ | √ | √ | √ | 1,400.00 | 0 | 0 | √ |  | DDA | ASDA |
| - Organize monthly staff technical review meetings for 38 staff | Kukuom | √ | √ | √ | √ | 12,720.00 | 0 | 0 | √ |  | DDA | ASDA |
| - Conduct 12 District Management and Planning meetings every two weeks | Kukuom | √ | √ | √ | √ | 2,400.00 | 0 | 0 | √ |  | DDA | ASDA |
| - DDA to attend 12 monthly Regional Technical Review Meetings | Goaso | √ | √ | √ | √ | 2,400.00 | 600 | 0 | √ |  | DDA | ASDA |
| - DOAs to attend 12 Regional Planning sessions, meetings and workshops | Goaso | √ | √ | √ | √ | 6,400.00 | 0 | 0 | √ |  | DDA | ASDA |
| - Organize Mid-year and end-of-year review meetings with DPCU and stakeholders (30 participants) by | Kukuom | √ | √ | √ | √ | 5,000.00 | 0 | 0 | √ |  | DDA | ASDA |
| - Undertake TEDMAG training activities | Kukuom | √ | √ | √ | √ | 11,100.00 | 0 | 0 | √ |  | DDA | ASDA |
| - DDA to carry-out 48 supervisory and monitoring visits | Kwapong,Sankore, Abuom, Anwiam | √ | √ | √ | √ | 8,800.00 | 2,000.00 | 0 | √ |  | DDA | ASDA, GIZ |
| - District Management Team to carryout 4 monitoring visits | 6 area councils | √ | √ | √ | √ | 4,800.94 | 2,000.00 | 0 | √ |  | DDA | ASDA |
| - DAOs to carry-out 480 backstopping and monitoring visits | Kwapong,Sankore, Abuom, Anwiam, Adomakokrom, Camp No 1 | √ | √ | √ | √ | 20,000.00 | 0 | 0 | √ |  | DDA | ASDA, GIZ |
| - Monitoring of PFJ programme, FAW menace and other activities in the District every month | Kwapong,Sankore, Abuom, Anwiam, Adomakokrom, Camp No 1 | √ | √ | √ | √ | 2,000.00 | 1,000.00 | 0 | √ |  | DDA | ASDA, VSO |
| - Conduct 2 trainings for 20 technical staff each on Record Keeping and Results-Oriented Reporting | Kukuom | √ | √ | √ | √ | 5,000.00 | 0 | 0 | √ |  | DDA | ASDA |
| - Strengthen capacity of 35 technical staff on 2024 PFJ modalities and fertilizer subsidy distribution | Kukuom | √ | √ | √ | √ | 2,500.00 | 0 | 1,000.00 | √ |  | DDA | ASDA, GIZ |
| - Conduct one technical training for 20 DAOs/AEAs on Fall Armyworm | Kukuom | √ | √ | √ | √ | 2,500.00 | 0 | 0 | √ |  | DDA | ASDA |
| - Conduct at least 5 farm and home visits by AEAs a week | Kwapong,Sankore, Abuom, Anwiam, Adomakokrom, Camp No 1, Noberkaw | √ | √ | √ | √ | 24,000.00 | 0 | 0 | √ |  | DDA | ASDA |
| - AEAs conduct 4 demonstrations and organize field days on GAPs in maize production in 4 communities | Sankore, Abuom, Anwiam, Adomakokrom, Camp No 1, Noberkaw | √ | √ | √ | √ | 3,200.00 | 0 | 0 | √ |  | DDA | ASDA |
| - AEAs conduct 4 demonstrations and organize field days on GAPs in tomatoes/pepper production in 4 communities | Tanoso,Noberkaw ,Kukuom, Gyedim | √ | √ | √ | √ | 3,200.00 | 0 | 0 | √ |  | DDA | ASDA, VSO |
| - AEAs conduct 2 demonstrations and organize field days on plantain paring/split corm and multiplication | Sankore, Ejisu | √ | √ | √ | √ | 1,600.00 | 0 | 0 | √ |  | DDA | ASDA |
| - AEAs conduct 4 demonstrations and organize field days on GAPs in rice production in 4 communities | Anwiam,Dantano,Noberkaw,Camp No1 | √ | √ | √ | √ | 3,200.00 | 0 | 2,000.00 | √ |  | DDA | ASDA, GIZ |
| - Conduct 5 field days for farmers on safe use of agro-chemical, fertilizers and use of PPEs in 5 communities | Noberkaw, Asibrem, Agyarekrom, Asarekrom | √ | √ | √ | √ | 3,000.00 | 0 | 1,000.00 | √ |  | DDA | ASDA, GIZ |
| - Sensitize 1000 farmers and stakeholders on the menace and control of Rice diseases | Sankore, Abuom, Anwiam, Adomakokrom, Camp No 1, Noberkaw, Sikafrebogya, Asibrem, Atekyem | √ | √ | √ | √ | 3,200.00 | 1,500.00 | 0 | √ |  | DDA | ASDA, VSO |
| - Train and support 50 farmers in Snail production as an additional livelihood | Kukuom,Noberkaw,Kwapong,Abuom,Abetenwom,Agyarekrom,Ejisu,Siiso | √ | √ | √ | √ | 2,500.00 | 0 | 1,000.00 | √ |  | DDA | ASDA, GIZ |
| - Organize training for 5 FBOs in group dynamics and development | Kwapong,Agyarekrom,Atekyem,Kwadoma,Amankwaakrom | √ | √ | √ | √ | 3,000.00 | 0 | 1,000.00 | √ |  | DDA | ASDA, GIZ |
| - Train 2 women FBO in two Communities on Bar Soap making | Nkawie, Marfokrom | √ | √ | √ | √ | 3,600.00 | 0 | 1,000.00 | √ |  | DDA | ASDA, GIZ |
| - Organize 4 Zonal RELC Planning Sessions with stakeholders | Sankore,Abuom,Kwapong,Kukuom | √ | √ | √ | √ | 1,200.00 | 0 | 0 | √ |  | DDA | ASDA, RDOA |
| - Organize 2-Day District RELC Planning Sessions with stakeholders along the value chain | Kukuom | √ | √ | √ | √ | 3,330.00 | 0 | 0 | √ |  | DDA | ASDA, RDOA |
| - Organize 3 study tours each for 35 farmers and staff to improved Agricultural centers | Wenchi, Kumasi, | √ | √ | √ | √ | 4,860.00 | 0 | 0 | √ |  | DDA | ASDA |
| - Train 450 farmers in 15 communities on the menace and control of Fall Armyworms (FAW) | Kwapong, Sankore, Abuom, Anwiam, Adomakokrom, Camp No 1 | √ | √ | √ | √ | 6,000.00 | 1,000.00 | 0 | √ |  | DDA | ASDA, VSO |
| - Organize 3 field training for 75 farmers on ICPM (identification and control) | Dodowa, Pafo, Kokooso | √ | √ | √ | √ | 1,800.00 | 0 | 0 | √ |  | DDA | ASDA |
| - Organize training for women extension volunteers from 20 communities to act as Service Agents | Kwapong, Abuom, Sankore, Anwiam, Kokooso | √ | √ | √ | √ | 1,440.00 | 0 | 0 | √ |  | DDA | ASDA, VSO |
| - Carry out 2 trainings for 50 women on Financial Management and Record Keeping of farm activities | Toapae, Kwadoma | √ | √ | √ | √ | 2,683.00 | 0 | 0 | √ |  | DDA | ASDA |
| - Conduct 2 trainings for 50 women on non-traditional agriculture (mushroom farming) | Abuom, Asarekrom,Kukuom, Kamirekrom, Kwapong,Sankore, Anwiam, Adomakokrom, Camp No 1, Noberkaw, Anwiam, | √ | √ | √ | √ | 3,500.00 | 0 | 0 | √ |  | DDA | ASDA, VSO |
| - Carryout Yield assessment of major food crops | Kwapong,Sankore, Abuom, Anwiam, Adomakokrom, Camp No 1, Noberkaw | √ | √ | √ | √ | 3,000.00 | 0 | 0 | √ |  | DDA | ASDA |
| - Organize 8 Plant Health Clinics for farmers in 4 communities | Kukuom | √ | √ | √ | √ | 1,600.00 | 0 | 0 | √ |  | DDA | ASDA |
| - Organize 3 trainings for 75 farmers on post-harvest management of grains and vegetables | Kukuom, Anwiam, Kwapong, Sankore | √ | √ | √ | √ | 1,800.00 | 0 | 500 | √ |  | DDA | ASDA, GIZ |
| - Conduct livestock and poultry census throughout the district | Adomakokrom,Sankore | √ | √ | √ | √ | 6,000.00 | 0 | 0 | √ |  | DDA | ASDA |
| - Train 25 Community Livestock Workers to act as service agents | Agyarekrom, Alavanyo | √ | √ | √ | √ | 1,750.00 | 0 | 0 | √ |  | DDA | ASDA |
| - Carry out training of 25 livestock farmers each in 4 communities on Biosecurity in livestock production | Kwapong,Sankore, Abuom, Anwiam, Adomakokrom, Camp No 1, Noberkaw | √ | √ | √ | √ | 2,400.00 | 0 | 0 | √ |  | DDA | ASDA |
| - Carry out 2 field training for 50 livestock farmers on improved housing techniques for livestock production | Dietwa,Teteh Kwao | √ | √ | √ | √ | 2,400.00 | 0 | 0 | √ |  | DDA | ASDA |
| - Carry out 2 trainings for livestock farmers on ration formulation and supplementary feeding | Yankye, Kukuom | √ | √ | √ | √ | 1,200.00 | 0 | 0 | √ |  | DDA | ASDA |
| - Organize 1 mass vaccination exercises each on Newcastle, PPR and Rabies diseases | Kwapong,Sankore, Abuom, Anwiam, Adomakokrom, Camp No 1, Noberkaw | √ | √ | √ | √ | 5,240.00 | 1,000.00 | 0 | √ |  | DDA | ASDA |
| - Organize 2 trainings for 30 butchers in two zones on handling of slaughtered animals (carcass) for human consumption | Kukuom, Sankore | √ | √ | √ | √ | 1,000.00 | 500 | 0 | √ |  | DDA | ASDA |
| - Organize 2 trainings for 50 women on Food Diversification, Farm and Home Resource Management or record keeping of farm activities | Asibrem, Agyeikrom | √ | √ | √ | √ | 2,400.00 | 0 | 0 | √ |  | DDA | ASDA |
| - Educate 20 women processors on Good Processing Techniques and hygiene | Kukuom | √ | √ | √ | √ | 1,440.00 | 0 | 0 | √ |  | DDA | ASDA |
| - Support the establishment and running of DCACT Centre | Kukuom | √ | √ | √ | √ | 5,000.00 | 2,000.00 | 0 | √ |  | DDA | ASDA |
| SUB -TOTAL |  |  |  |  |  | 300,263.94 | 12,600.00 | 7,500.00 |  |  |  |  |
| SUB -TOTAL 2 |  |  |  |  |  | 329,733.94 | 16,084.00 | 43,500.00 |  |  |  |  |
| Goal: Ensure efficiency, transparency and accountability in decentralized governance |  |  |  |  |  |  |  |  |  |  |  |  |
| Programmes 1: Management and Administration |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-programme 1.1: General Administration |  |  |  |  |  |  |  |  |  |  |  |  |
| - Strengthening of sub district structures | 6-area council | √ | √ | √ | √ | 24,200.00 | 2,420.00 | 0 | √ | √ | CA | Other Department |
| - Organize regular town hall meetings / press meetings | Kukuom, Sankore, Kwapong | √ | √ | √ | √ | 12,100.00 | 6,050.00 | 0 | √ | √ | PLG Unit |  |
| - Convene 3no. General Assembly meetings | Kukuom | √ | √ | √ | √ | 30,250.00 | 1,210.00 | 0 | √ | √ | Cent Admin | Other Depts |
| - Convene 3no. EXECO meetings | Kukuom | √ | √ | √ | √ | 12,100.00 | 2,420.00 | 0 | √ | √ | Cent Admin |  |
| - Organize 3no. meetings of 5 statutory sub-committee | Kukuom | √ | √ | √ | √ | 8,470.00 | 1,210.00 | 0 | √ | √ | Cent Admin |  |
| - Organize quarterly Audit Committee meetings | Kukuom | √ | √ | √ | √ | 9,680.00 | 2,420.00 | 0 | √ | √ | Cent Admin | Internal Audit Unit |
| - Organize 1no. Independence Day Anniversary celebration | Kukuom | √ | √ | √ | √ | 24,200.00 | 1,210.00 | 0 | √ | √ | Educ Dept | Cent Admin |
| - Organize 1no. Republic Day celebration | Kukuom | √ | √ | √ | √ | 1,210.00 | 1,210.00 | 0 | √ | √ | Cent Admin |  |
| - Organize quarterly Entity Tender Committee meetings | Kukuom | √ | √ | √ | √ | 9,680.00 | 2,420.00 | 0 | √ | √ | Proc Unit | Plg Unit |
| - Organize quarterly management and staff meetings | Kukuom | √ | √ | √ | √ | 12,100.00 | 1,210.00 | 0 | √ | √ | Cent Admin |  |
| - Organize quarterly PRCC meeting | Kukuom | √ | √ | √ | √ | 9,680.00 | 2,420.00 | 0 | √ | √ | Cent Admin | PM |
| - Procure office equipment and stationaries for the Assembly | Kukuom | √ | √ | √ | √ | 24,200.00 | 12,100.00 | 0 | √ | √ | Proc Unit | PLG Unit |
| - Support to Good Governance institutions and agencies | Kukuom | √ | √ | √ | √ | 6,050.00 | 2,420.00 | 0 | √ |  | CA | Other Department |
| - Update data on business establishment, market surveys of selected food items and others | Kukuom, Sankore, kwapong | √ | √ | √ | √ | 6,050.00 | 121 | 12,100.00 | √ |  | Statistics | BACD, DA |
| - Research, Documentation and Development of Heritage Sites Festivals and Sacred Grooves for Tourism | Kukuom, Tanoso – Dantano, Sankore, Asufufuo |  | √ | √ | √ | 6,050.00 | 242 | 0 | √ |  | CNC | Physical planning & MMDES, Traditional Authorities |
| - Departmental cultural orientation on various Customary/ Traditional Rites and courtesies. | Kukuom | √ | √ | √ | √ | 1,210.00 | 605 | 0 | √ |  | CNC | DA |
| - Radio Cultural info and education on Traditional/ Cultural Values and Ethics | Districtwide | √ | √ | √ | √ | 191,180.00 | 37,268.00 | 12,100.00 | √ |  | CNC |  |
| - Selection and beautification of spots with murals, sculptures, paintings | Kwapong, Kukuom, Abuom, Sankore |  | √ | √ | √ | 388,410.00 | 76,956.00 | 24,200.00 | √ |  | CNC | Physical planning, Parks & Gardens |
| SUB-TOTAL |  |  |  |  |  | 776,820.00 | 153,912.00 | 48,400.00 |  |  |  |  |
| Sub-programme 1.2: Finance and Audit |  |  |  |  |  |  |  |  |  |  |  |  |
| - Prepare and implement Revenue Improvement Action Plan | Kukuom | √ | √ | √ | √ | 24,200.00 | 550 | 0 | √ |  | Finance Dept. | CA |
| - Prepare and submit 12No. monthly trail balances | Kukuom | √ | √ | √ | √ |  | 15,000.00 |  |  |  | Finance Dept. |  |
| - Prepare and submit 2023 Annual Financial Statements | Kukuom | √ | √ | √ | √ |  | 24,000.00 |  |  |  | Internal Audit |  |
| - Undertake quarterly internal Audits of the Assembly | Kukuom | √ | √ | √ | √ |  | 3,000.00 |  |  |  | Internal Audit |  |
| - Preparation of annual internal audit workplan for 2024 | Kukuom | √ | √ | √ | √ |  | 650 |  |  |  | Internal Audit |  |
| - Preparation and submission of annual performance audits report | Kukuom | √ | √ | √ | √ |  | 650 |  |  |  | Internal Audit |  |
| - Inspection and verification of procured items into stores | Kukuom | √ | √ | √ | √ |  | 650 |  |  |  | Internal Audit |  |
| - Capacity building (workshops, conferences and seminars) |  |  |  |  |  | 25,000.00 |  |  |  |  | Internal Audit |  |
| SUB -TOTAL |  |  |  |  |  | 49,200.00 | 44,500.00 | 0.00 |  |  |  |  |
| Sub-programme 1.3: Human Resource Management |  |  |  |  |  |  |  |  |  |  |  |  |
| - Organize 1no. refresher workshop on Performance Management System for LGS staff | Kukuom | √ | √ | √ | √ | 24,200.00 | 200 |  | √ | √ | Cent Admin |  |
| - Organize 1no. training on service protocols for LGS staff | Kukuom | √ | √ | √ | √ | 96,800.00 | 2,000.00 |  | √ | √ | HRD | PLG Unit |
| - Staff Appraisal for 2024 | Kukuom | √ | √ | √ | √ | 605 | 200 |  | √ | √ | HRD |  |
| - Salary and Payroll Management | Kukuom | √ | √ | √ | √ | 2,972,857.83 | 100 |  | √ | √ | HRD | Finance Dept. ASDA |
| - Prepare and submit 2025 capacity building plans | Kukuom |  |  |  |  | 25,000.00 | 2,000.00 |  |  |  | HRD |  |
| SUB -TOTAL |  |  |  |  |  | 3,119,462.83 | 4,500.00 | 0.00 |  |  |  |  |
| Sub-programme 1.4: Planning, Budgeting, Coordination and Statistics |  |  |  |  |  |  |  |  |  |  |  |  |
| - Organize quarterly DPCU meetings | Kukuom | √ | √ | √ | √ | 24,200.00 | 1,210.00 | 0 | √ | √ | Plg Unit |  |
| - Organize quarterly Budget C’ttee meetings | Kukuom | √ | √ | √ | √ | 12,100.00 | 1,210.00 | 0 | √ | √ | Budget Unit |  |
| - Preparation of composite Annual Action Plan and budget | Kukuom |  | √ | √ | √ | 12,100.00 | 6,050.00 | 0 | √ |  | CA | Other Department |
| - Preparation and submission of 2024 quarterly and annual Progress reports |  | √ | √ | √ | √ | 5,500.00 | 500 |  |  |  | Plg Unit |  |
| - Embark on monitoring and evaluation of projects/programmes | Districtwide | √ | √ | √ | √ | 60,500.00 | 6,050.00 | 0 | √ | √ | DPCU | TA, HON. Assembly members |
| SUB -TOTAL |  |  |  |  |  | 114,400.00 | 15,020.00 | 0.00 |  |  |  |  |
| Sub-programme 1.5: Legislative Oversights |  |  |  |  |  |  |  |  |  |  |  |  |
| - Hold quarterly DISEC meetings | Kukuom | √ | √ | √ | √ | 12,100.00 |  |  | √ | √ | Cent Admin | Security Agencies |
| SUB -TOTAL |  |  |  |  |  | 12,100.00 | 0 | 0 |  |  |  |  |
| SUB -TOTAL 2 |  |  |  |  |  | 4,071,982.83 | 217,932.00 | 48,400.00 |  |  |  |  |
| Goal: Create an environment supportive of personal development and wealth creation |  |  |  |  |  |  |  |  |  |  |  |  |
| Programmes 2. Social Services Delivery |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-programme 2.1: Education, Youth &Sports Services |  |  |  |  |  |  |  |  |  |  |  |  |
| - Completion of 3- unit classroom block at siiso | Siiso | √ | √ | √ | √ | 77,524.15 |  |  |  | √ | DWD | DED, TA, Assembly Member |
| - Const. of 1 no 3- unit clrm blk wth 4 0 kvip & at siiso bowjiase | siiso bowjiase | √ | √ | √ | √ | 181,970.90 |  |  |  | √ | DWD | DED, TA, Assembly Member |
| - Const. of 1no 3 - unit clrm blk wth 4 0 kvip & at asampanaye | Asempaneye | √ | √ | √ | √ | 182,437.65 |  |  |  | √ | DWD | DED, TA, Assembly Member |
| - Const. of 1 No 3 Unit Classroom Block at Kukuom Methodist | Kukuom Methodist | √ | √ | √ | √ | 191,769.29 |  |  |  | √ | DWD | DED, TA, Assembly Member |
| - Renovation of 1 no 6- unit classroom block at kukuom methodist | Kukuom Methodist | √ | √ | √ | √ | 148,245.50 |  |  |  | √ | DWD | DED, TA, Assembly Member |
| - Const. of 1No 3- Unit Clrm Blk at Abuom D/A Jhs | Abuom D/A JHS | √ | √ | √ | √ | 274,740.13 |  |  |  | √ | DWD | DED, TA, Assembly Member |
| - Const. of 1 No 3 - Unit Clrm Blk at Siiso D/A Jhs | Siiso D/A JHS | √ | √ | √ | √ | 273,869.50 |  |  |  | √ | DWD | DED, TA, Assembly Member |
| - Renovation of 1 No 6- Unit Classroom Block at Kukuom Methodist | Kukuom Methodist | √ | √ | √ | √ | 506,841.34 |  |  |  | √ | DWD | DED, TA, Assembly Member |
| - Construction of 1No. 3-Unit Classroom block with Staff Common room and office and ancillary facility at Noberkaw Methodist JHS | Noberkaw Methodist JHS | √ | √ | √ | √ | 325,294.88 |  |  |  | √ | DWD | DED, TA, Assembly Member |
| - Construction of 1No. 3-Unit Classroom Block with office, staff common room, 3-Seater KVIP and supply of Furniture at Kukuom Girls Model School | Kukuom Girls Model School | √ | √ | √ | √ |  |  | 248,734.07 |  | √ | DWD | DED, TA, Assembly Member |
| - Construction of 1No. 3-Unit Classroom Block with office, staff common room, 3-Seater KVIP and supply of Furniture at Kukuom SDA School | Kukuom SDA School | √ | √ | √ | √ |  |  | 271,245.72 |  | √ | DWD | DED, TA, Assembly Member |
| - Procure Dual Desk | All schools | √ | √ | √ | √ | 242,000.00 | 0 | 0 |  | √ | DED | DWD, TA, Assembly Member |
| - Monitoring and distribution of learning materials | All schools | √ | √ | √ | √ | 10,000 | 0 | 0 | √ |  | GES | DWD, TA, Assembly Member |
| - Monitoring and implementation of “All must read” program | All schools | √ | √ | √ | √ | 10,000.00 | 0 | 0 |  | √ | GES | ASDA |
| - Organize my First Day at school for KG & Prim. 1 | All KG and Primary schools | √ | √ | √ | √ | 20,000.00 | 0 | 0 |  | √ | Cent Admin | Educ Dept |
| - Monitoring and Collection of Data on schools, infrastructure and furniture | All schools |  | √ |  | √ | 10,000.00 | 0 | 0 |  | √ | GES |  |
| - Sensitization of parents and teachers on the learning needs of PWDs | All schools | √ | √ | √ | √ | 6,050.00 | 1,210.00 | 0 |  | √ | GDO | GES, SWCD |
| - Monitoring the implementation of Standard Base and Common Core Curriculum | All Basic Schools |  | √ |  | √ | 30,000.00 | 0 | 0 | √ |  | GES | MoE, PTA |
| - Organize Independence Day celebration | District wide |  |  |  | √ | 15,000.00 | 0 | 0 | √ |  | GES | ASDA |
| - Organize Ghana Teacher Prize | All Basic & second cycle schools | √ | √ | √ | √ | 30,000.00 | 0 | 0 | √ |  | GES | DA, HRMD |
| - Organize Reading Festival | All Basic Schools | √ | √ | √ | √ | 20,000.00 | 0 | 0 | √ |  | GES | DA |
| - Data collection on Staffing and enrolment | All Basic Schools | √ | √ | √ | √ | 10,000.00 |  |  | √ |  | EMIS | DA |
| - Preparation and presentation of ADEOP | District Assembly | √ | √ | √ | √ | 10,000.00 |  |  |  | √ | EMIS | DA |
| - Conduct Annual school census | All basic schools | √ | √ | √ | √ | 10,000.00 |  |  | √ |  | EMIS | DA |
| - Support to the conduct of BECE & WASCE | All centers | √ | √ | √ | √ | 20,000.00 |  |  | √ |  | GES | DA |
| - Organize 1No. Orientation for newly Appointed Head teachers and Newly Posted Teachers | Kukuom | √ | √ | √ | √ | 30,000.00 |  |  | √ |  | GES | DA |
| - Organize 1No. ICT training for all teachers | Kukuom | √ | √ | √ | √ | 20,000.00 |  |  | √ |  | GES | DA |
| - Organize Interschool Athletics & sports | All Circuits | √ | √ | √ | √ | 20,000.00 |  |  | √ |  | GES | DA |
| - Organize Inter school cultural festival | All circuits | √ | √ | √ | √ | 20,000.00 |  |  | √ |  | GES | DA |
| - Promote skill and career guidance training for the youth | Districtwide | √ | √ | √ | √ | 3,300.00 | 0 | 0 |  | √ | DGDO | NYADA |
| SUB -TOTAL |  |  |  |  |  | 2,699,043.34 | 1,210.00 | 519,979.79 |  |  |  |  |
| Sub-programme 2.2: Public Health Services and Management |  |  |  |  |  |  |  |  |  |  |  |  |
| - Construction of 1 no chps compound at wejakrom | Weijakrom | √ | √ | √ | √ | 153,371.70 |  |  |  | √ | DWD | DA, DHD |
| - Organize monthly and quarterly data Audit | All chps zones | √ | √ | √ | √ |  |  | 74,000.00 | √ |  | DDHS, HIOs | UNIT HEADS |
| - Regular monitoring and supervision of all health facilities | All facilities | √ | √ | √ | √ |  |  | 60,000 | √ |  | DDHS, HIOs | UNIT HEADS |
| - Conduct one operational research within the district | 6 area councils | √ | √ | √ | √ |  |  | 45,000.00 | √ |  | DDHS, HIOs | FACILITY IN-CHARGES , DA |
| - Monthly collection and distribution of vaccines and other EPI logistics to health facilities | All facilities | √ | √ | √ | √ |  |  | 45,000.00 | √ |  | EPI Coordinator | DDHS, HIOs |
| - Monitor EPI performance, outain home vist of children and pregnant mothers and creation of more outreach centers | 6 area councils | √ | √ | √ | √ |  |  | 17,760.00 | √ |  | UNIT HEADS | DA |
| - Strengthen daily review of consulting room registers | All facilities | √ | √ | √ | √ |  |  | 800 | √ |  | CHOs | Facility Incharges , DHD |
| - Carryout family planning (F/P) sensitization and community durbar in two communities on long term method. | All facilities | √ | √ | √ | √ |  |  | 6000 | √ |  | PHN,DNO,DHIO, DDHS HPO | ASSEMBLYMEN AND OPINION LEADERS , DA |
| - Train staff on how to capture data into the register, reporting formats, and IRSLOG. |  | √ | √ | √ | √ |  |  | 9000 | √ |  | PHN,DNO,DHIO, DDHS, HPO,DDCO | PHN,DNO,DHIO, DDHS, HPO,DDCO |
| - Increase maternal health services to the CHPS compounds. | All facilities | √ | √ | √ | √ |  |  | 45,500 | √ |  | PHN,DNO,DHIO, DDHS HPO, DDCO | ASSEMBLYMEN,OPINION LEADERS AND MP |
| - Intensify health education on the prevention of teenage pregnancy | 6 area councils | √ | √ | √ | √ |  |  | 10,000 | √ |  | PHN,DNO,DHIO, DDHS HPO, DDCO | ASSEMBLYMEN, School Heads and NGOS |
| - Organize adolescent forum in the two SHS in the district to create awareness on HIV/AIDS, STI. | Kukuom SHS, Sankore SHS | √ | √ | √ | √ |  |  | 4000 | √ |  | PHN,DNO,DHIO, DDHS HPO, DDCO and CHNs | PHN,DNO,DHIO, DDHS HPO, DDCO and CHNs |
| - Increase immunization coverage by all antigen | All CWC centers | √ | √ | √ | √ |  |  | 4000 | √ |  | PHN,DNO,DHIO, DDHS HPO, DDCO | PHN,DNO,DHIO, DDHS HPO, DDCO and CHNs |
| - Increase functional CHPS zones from 23 to 25 by the end of the year 2024 |  | √ | √ | √ | √ |  |  | 6000 | √ |  | PHN,DNO,DHIO, DDHS HPO, DDCO | PHN,DNO,DHIO, DDHS HPO, DDCO and CHNs |
| - Scale up Start Right Feed Right campaign/education to the community level |  | √ | √ | √ | √ |  |  | 8,000.00 | √ |  | DDHS, Community Leaders, DNOs | Sub-District Heads,DAS,DHD |
| - Establish Institutional Wellness Clinic |  | √ | √ | √ | √ |  |  | 10,000.00 | √ |  | DDHS,Nut. Officers, PHNs, HPOs,DCO,HIOs | DHD, DAS ,GES,MOFA,Ghana Police Service,Immigration, Armajaro Company, |
| - Conduct Day Care Surveillance in 4 Preschools in 2 Sub-districts |  | √ | √ | √ | √ |  |  | 5,000.00 | √ |  | DDHS, Nos | GES, DHD |
| - Scale up Nutrition Friendly Schools Initiative (NFSI) activities from 9 to 11 schools |  | √ | √ | √ | √ |  |  | 2,000.00 | √ |  | DDHS, NOs | GES Directorate |
| - Monitoring and supervision |  | √ | √ | √ | √ |  |  | 3500 | √ |  | DDHS, NOs | Sub-District Heads,DDHS, NO,Community stakeholders |
| - Stakeholder Engagement Meeting for SRFR Campaign |  | √ | √ | √ | √ |  |  | 6000 | √ |  | DDHS, NOs | Sub-District Heads,DDHS, NO,Community stakeholders |
| - Visit and conduct school and adolescent health services in at least three schools in the District within every quarter of 2024. |  | √ | √ | √ | √ |  |  | 1,200.00 | √ |  | DHD | HPO, PHN |
| - Conduct a satisfaction survey and assessment on the health needs of clients and staff in at least one health facility in the district in 2024 |  | √ | √ | √ | √ |  |  | 2,000.00 | √ |  | DHD | HPO |
| - Assist each of the sub-districts to organize at least one community durbar in their sub-district for the year 2024 |  | √ | √ | √ | √ |  |  | 2,000.00 | √ |  | DHD | HPO, CHNs, CHPS coordinator |
| - Observe and organize activities for at least 60% of all important health days in 2024 |  | √ | √ | √ | √ |  |  | 2,000.00 | √ |  | DHD | All staffs |
| - Organize at least two adolescent health forums among adolescents in the district in 2024 |  | √ | √ | √ | √ |  |  | 800 | √ |  | DHD | HPO, PHN, CHNs |
| - Conduct health education and create awareness about health events in the district from January to December 2024 |  | √ | √ | √ | √ |  |  | 5,000.00 | √ |  | DHD | All health staff |
| - Visit and provide support to each facility at least once in 2024 |  | √ | √ | √ | √ |  |  | 1,000.00 | √ |  | DHD | HPO, DDHS |
| - Validate and enter monthly health promotion reports from January to December 2024 |  | √ | √ | √ | √ |  |  | 800 | √ |  | DHD | HPO, PHN,DNO |
| - Lead all risk communication activities on any health events from January to December 2024 |  | √ | √ | √ | √ |  |  | 4,000.00 | √ |  | DHD | All health staff |
| - Extension of male hostel with 3 no teacher's quarters at kwapong ntc | Kwapong NTC | √ | √ | √ | √ | 245,323.05 |  |  |  | √ | DWD | DA, DHD |
| SUB -TOTAL |  |  |  |  |  | 398,694.75 | 0.00 | 380,360.00 |  |  |  |  |
| Sub-programme 2.3: Social Welfare and Community Development |  |  |  |  |  |  |  |  |  |  |  |  |
| - Support to family & individuals with non-child maintenance, abuse, custody and paternity cases | 6-area council | √ | √ | √ | √ | 400 |  |  | √ |  | SW & CD | Judicial Service, ASDA, GPS, Other stakeholders |
| - Sensitization on SGBV information for children | 6-area council | √ | √ | √ | √ | 300 |  |  | √ |  | SW & CD | Judicial Service,ASDA, GPS, Other stakeholders |
| - Children reached by social work and social services | 6-area council | √ | √ | √ | √ | 300 |  |  | √ |  | SW & CD | Judicial Service, ASDA, GPS, Other stakeholders |
| - Supervise, monitor and facilitate registration of Day-Care centres | 6-area council | √ | √ | √ | √ | 1000 |  |  | √ |  | SW & CD | Dept. of Children, ASDA |
| - Render alternative care services | Kukuom | √ | √ | √ | √ | 1500 |  |  | √ |  | SW & CD | Transitional Home ASDA,Foster Parents ,Children’s Home, Other stakeholders |
| - Give support and referrals services to children in worse forms of child labour | 6-area council | √ | √ | √ | √ | 1500 |  |  | √ |  | SW & CD | GPS, ASDA, Anti-human trafficking Unit, Community Leaders and chiefs |
| - Register adults and children with disabilities and give them support (health, Education, mobility aids) | 6-area council | √ | √ | √ | √ | 1000 |  |  | √ |  | SW & CD | NHIS, GES, GHS, ASDA, Other stakeholders |
| - Provide vocational skills for persons with Disability | 6-area council | √ | √ | √ | √ | 1500 |  |  | √ |  | SW & CD MoGCSP, GFPD | NCCE, ISD,Trad. leaders, CSO, FBO’s, ASDA, Dev. Partners |
| - Create awareness and sensitized persons with disability on Gender Based Violence and its related issues | 6-area council | √ | √ | √ | √ | 1000 |  |  | √ |  | SW & CD , MoGCSP,NCPD,DOVVSU | NCCE, ISD, ASDA,Trad. Leaders, CSO ,FBO’s ,Dev. Partners |
| - Organize medical screening for women and girls with disabilities | 6-area council | √ | √ | √ | √ | 3000 |  |  | √ |  | SW & CD | GHS, Other stakeholders |
| - Build capacity of persons with disabilities to be able to report perpetuators of Gender Based Violence | Kukuom | √ | √ | √ | √ | 1000 |  |  | √ |  | SW & CD MoGCSP,NCPD, DOVVSU | ISD , NCCE, Traditional Leaders , CSO, FBO’s , ASDA,Development Partners |
| - Provide livelihood support and counseling to persons with disabilities | Kukuom | √ | √ | √ | √ | 1500 |  |  | √ |  | SW & CD | ISD , Traditional Leaders , CSO, FBO’s ,ASDA, Development Partners |
| - Facilitate payment and assist beneficiaries to access other social protection interventions | Kukuom | √ | √ | √ | √ | 1000 |  |  | √ |  | SW & CD | Ghana Police Service, ASDA, Clic / CFP Members |
| - Ensure registration and renewal of beneficiaries NHIS cards and Other vulnerable groups | Kukuom | √ | √ | √ | √ | 1000 |  |  | √ |  | SW & CD | NHIS, ASDA |
| - Facilitate sensitization and grant payment for beneficiary households | Kukuom | √ | √ | √ | √ | 1000 |  |  | √ |  | SW & CD | PFI, GPS, Focal persons |
| - Public lecture and sensitization on Gender Based Violence and other vulnerability related issues | Kukuom | √ | √ | √ | √ | 1500 |  |  | √ |  | SW & CD | ASDA, CFP |
| - Provide probation services to juveniles and families | Kukuom | √ | √ | √ | √ | 1500 |  |  | √ |  | SW & CD | GPS, Community Leaders and chiefs |
| - Education and support on Menstrual Hygiene for JHS Students | Kukuom | √ | √ | √ | √ | 2,420.00 | 1,210.00 | 0 | √ | √ | DGDO | SWCD, GES |
| SUB -TOTAL |  |  |  |  |  | 22,420.00 | 1,210.00 | 0.00 |  |  |  |  |
| Sub-programme 2.4: Birth and Death Registration Services |  |  |  |  |  |  |  |  |  |  |  |  |
| - Registration of births and deaths | 6-area councils | √ | √ | √ | √ | 5,445.00 | 100 |  | √ | √ | BDD | GHS, traditional Authorities, Private Morgue operators |
| - Sensitization and education on the importance of births and deaths registration | 6-area councils | √ | √ | √ | √ | 5,000.00 | 100 |  | √ | √ | BDD | GHS, traditional Authorities, Private Morgue operators |
| - Capacity building (workshops, conferences and seminars) |  |  |  |  |  | 3,000.00 |  |  |  |  | Birth & Death Dept. |  |
| SUB -TOTAL |  |  |  |  |  | 13,445.00 | 200.00 | 0.00 |  |  |  |  |
| Sub-programme 2.5: Environmental Health and Sanitation Services |  |  |  |  |  |  |  |  |  |  |  |  |
| - Regular cleaning and clearing of public places | Kukuom, Sankore, Kwapong | √ | √ | √ | √ |  | 8,150.00 | 0 | √ | √ | EHU | Zoomlion GH. LTD,Assembly members |
| - Implementation of SHEP programmes i.e Sanitation, environment and safety systems in schools | Districtwide | √ | √ | √ | √ | 18,150.00 | 0 | 0 | √ | √ | GES | DEHU, GHS |
| - Screening of food vendors, butcher meat sellers, drinking bar operators and School feeding Operators | 6 area councils |  | √ |  |  |  | 2,500.00 | 0 | √ |  | DEHU | DA, GHS |
| - Intensify school health programes | 6 area councils | √ | √ | √ | √ |  | 1,000.00 |  | √ |  | DEHU | GES |
| - Intensify routine inspection and hygiene Education | 6 area councils | √ | √ | √ | √ | 0 | 1,000.00 | 0 | √ | √ | DEHU | DGDO, DHD |
| - Monitoring of WSMT and water facilities in the district | 6-area council | √ | √ | √ | √ | 5,500.00 | 220 | 5,500.00 | √ | √ | DWSMT | DPCU |
| - Fumigate and Disinfestation of sanitary sites and public toilets | Kukuom, Kwapong, Sankore | √ | √ | √ | √ | 60,000.00 | 0 | 0 | √ | √ | DEHO | Zoomlion GH, LTD |
| - Procurement of assorted sanitary tools and equipment | Kukuom |  | √ |  |  | 24,000.00 | 651 | 0 | √ |  | DEHU | DA |
| - Expansion of waste collection points from 10 to 15 | Kukuom, Sankore | √ | √ | √ | √ | 100,000.00 |  |  | √ |  | DEHU | DA, Zoomlion Gh, Assembly Members. |
| - Enforce sanitation bye laws | 6 area councils | √ | √ | √ | √ |  | 1,000.00 |  | √ |  | DEHU | DA, Zoomlion Gh, Assembly Members. |
| - Evacuation of refuse heaps & mechanically pushing and leveling of refuse heaps | Kukuom, Kwapong Sankore |  |  |  | √ | 60,000.00 | 0 | 0 | √ |  | DEHU | DA, Zoomlion Gh, Assembly Members. |
| - Daily collection and disposal of refuse (SIP) | Kukuom, Kwapong, Sankore | √ | √ | √ | √ |  | 2,000.00 | 0 | √ |  | DEHU | ASDA, Zoomlion Gh. |
| - Introduction of community led total sanitation (CLTs) programme | 6 area councils | √ | √ | √ | √ |  | 2,000.00 |  |  |  | DEHU | Landlords |
| - Dislodging of 4No. Public Toilets |  |  | √ |  |  | 24,651.00 | 0 | 0 | √ |  | DEHU | ASDA, Zoomlion Gh. |
| - Prosecution of sanitary offenders | 6 area councils | √ | √ | √ | √ |  | 200 | 0 | √ |  | DEHU | Assembly Members, Ghana police service |
| - Training of environmental health officers on report writing and health education strategies | Kukuom | √ |  |  |  |  | 3,000.00 |  | √ |  | DEHU | GHS |
| - Arrest of stray animals | 6 area councils | √ | √ | √ | √ |  | 300 | 0 | √ |  | DEHU | Trad. Authorities, Assembly Members |
| - Construction of public pound to house stray animals | Kukuom | √ | √ | √ | √ |  | 8,700 |  | √ |  | DEHU | Trad. Authorities, Assembly Members |
| SUB -TOTAL |  |  |  |  |  | 292,301.00 | 30,721.00 | 5,500.00 |  |  |  |  |
| SUB -TOTAL 2 |  |  |  |  |  | 3,425,904.09 | 33,341.00 | 905,839.79 |  |  |  |  |
| Goal: Create an environment supportive of personal development and wealth creation |  |  |  |  |  |  |  |  |  |  |  |  |
| Programmes 3. Infrastructure Delivery and Management |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-programme 3.1: Physical and Spatial Planning Development |  |  |  |  |  |  |  |  |  |  |  |  |
| - Prepare District Spatial Development framework | District Wide | √ | √ | √ | √ | 65,000.00 | 0 | 0 | √ | √ | DA | PPD, RCC, Trad. Authorities, Depts, LUSPA |
| - Continuation of Street Naming and Property Addressing System | Sankore |  |  |  |  | 5,200.00 |  | 0 |  | √ | PPD | DA, Trad. Authorities, GIZ, LUSPA |
| - Preparation of structural plans for the district | Sankore, Noberkaw, Kwapong and Abuom | √ | √ | √ |  | 40,000.00 | 0 | 0 | √ |  | PPD | RCC, Trad. Authorities, Depts, LUSPA |
| - Prepare Local plans for 5 communities | Kukuom,Kamirekrom, Nfrekrom, Abuom and Sankore | √ | √ | √ |  | 38,800.00 | 0 | 0 | √ |  | PPD | RCC, Trad. Authorities, Depts, LUSPA |
| - Organize 12No. Technical Sub-committee (TSC) and Spatial planning committee (SPC) meeting | Kukuom | √ | √ | √ | √ | 29,000.00 |  | 0 | √ |  | PPE | EPA,GNFS,Lands Commission, T.A |
| - Train staff and Spatial Planning Committee members on land use and spatial planning Act | Kukuom | √ | √ | √ |  | 2,050.00 |  | 0 | √ |  | PPD | RCC, MLGRD, LGS,, Depts, LUSPA |
| - Create public awareness on greening of human settlements | Kukuom |  | √ | √ | √ | 10,000.00 |  | 0 | √ |  | PPD | Trad. Authorities, Depts, Developers |
| - update 1No. layout for Sankore | Sector 1 | √ | √ | √ |  | 6,000.00 |  | 0 | √ |  | PPD | RCC,T.A,deps, LUSPA |
| - procure logistics for parks and Garden Unit | Kukuom | √ | √ | √ |  | 8,000.00 |  | 0 | √ |  | PPD | RCC, TA, Depts, LUSPA |
| - Landscaping of the forecourt of the district administration block | Kukuom | √ | √ | √ |  | 12,000.00 |  |  | √ |  | PPD | RCC, TA, Depts, LUSPA |
| - Procure 1No. printer and repair existing faulty colored printer | Kukuom |  | √ | √ | √ | 2,700 |  |  | √ |  | PPD | DA |
| - Procure auto photos for six communities | Abuom, Sankore, Anwiam, Siana, Kwapong, Noberkaw |  | √ | √ |  | 50,000 |  |  | √ |  | PPD | RCC, TA, Depts, LUSPA |
| - Create public awareness on planning regulations, plot allocation &permits | Abuom, Sankore, Anwiam, Siana, Kwapong, Noberkaw | √ | √ | √ |  | 1,200.00 |  |  | √ |  | PPD | RCC, TA, Depts, LUSPA |
| - Monitor and enforce compliance with building regulations | 6 area councils | √ | √ | √ | √ | 1,500.00 |  |  | √ |  | PPD | Judicial service, police, Trad. Authorities, private developers |
| - Organize refresher training for SAT members on SNPA | Kukuom |  |  | √ | √ | 1,600.00 |  |  | √ |  | PPD | DA, Trad. Auth. GIZ |
| - Collect data on all properties and businesses | Kukuom, Sankore |  | √ | √ | √ | 3,500.00 |  |  | √ |  | PPD | DA, Trad. Auth. GIZ, LUSPA |
| SUB -TOTAL |  |  |  |  |  | 226,550.00 | 0.00 | 0.00 |  |  |  |  |
| Sub-programme 3.2: Public Works, Rural Housing and Water Management |  |  |  |  |  |  |  |  |  |  |  |  |
| - Construction of Staff Quarters | Kukuom | √ | √ | √ | √ | 242,000.00 | 0 | 0 | √ | √ | DWD | TA, Assembly members |
| - Construction of durbar ground at kwapong | Kwapong | √ | √ | √ | √ | 241,985.00 |  |  |  | √ |  |  |
| - Development of the forecourt of the District Assembly’s Office Block | Kukuom | √ | √ | √ | √ | 357,962.04 | 0 | 0 |  | √ | DWD | TA, Assembly members |
| - Completion of 1No Store for Sankore Daily Market (20-Unit) | Sankore | √ | √ | √ | √ | 162,742.00 |  |  |  | √ | DWD | TA, Assembly members |
| - Renovation of 1No. 12-seater Aqua Privy Toilet at Kukuom | Kukuom | √ | √ | √ | √ | 65,145.00 |  |  |  | √ | DWD | TA, Assembly members |
| - Completion of the first floor of 3-storey Administration Block | Kukuom | √ | √ | √ | √ | 1,186,436.83 | 0 | 0 |  | √ | DWD | TA, Assembly members |
| - Completion of 1No. Police station at Abuom | Abuom | √ | √ | √ | √ |  | 0 | 295,836.40 |  | √ | DWD | DA, GPS |
| - Support for community-initiated projects | 6-area councils | √ | √ | √ | √ | 14,520.00 | 6,050.00 | 0 | √ |  | DWD | DA |
| - Drilling, construction and completion of boreholes, LMS and pipe systems | Kamirekrom, pafoNkwanta, Adwumam, Noberkaw, Abuom, Ntonsu, Kokooso No.2, Nseinnua, Manhyia No.4, Asarekrom, Sikafrebogya, Kwadoma | √ | √ | √ | √ | 40,000.00 | 0 | 90,000.00 |  | √ | DWD | TA, Assembly members, IRC |
| - Reshaping/Spot Improvement/Rehabilitation of 10 km feeder roads | 6-area councils | √ | √ | √ | √ | 423,500.00 | 0 | 0 |  | √ | DWD | ASDA, |
| - Facilitate the organization of road safety campaigns | Kukuom | √ | √ | √ | √ | 18,150.00 | 1,210.00 | 0 | √ |  | GRSA, MTTD | DA, GPRTU |
| - Construction of speed bumps | 6-area councils | √ | √ | √ | √ | 9,680.00 | 2,420.00 | 0 |  | √ | GHA | DA |
| - Clearing of weedy road pedestrians’ walkways | 6-area councils | √ | √ | √ | √ | 8,470.00 | 0 | 0 |  | √ |  |  |
| - Extension of electricity | 6-area councils | √ | √ | √ | √ | 36,300.00 | 0 | 0 |  | √ | DWD | ASDA Assembly Members, NEDCO |
| - Maintenance of street lights | 6-area councils | √ | √ | √ | √ | 118,580.00 | 0 | 0 |  | √ | DWD | ASDA, |
| - Rehabilitate Staff bungalows | Kukuom | √ | √ | √ | √ | 102,850.00 | 0 | 0 | √ | √ | Wks Dept | Plg Unit/Proc Unit |
| - Implementation of WASH activities | 6-area councils |  |  |  |  | 10,000.00 |  | 590,991.98 |  |  | IRC | DA |
| - Construction of Multi-purpose Town Park | Kukuom | √ | √ | √ | √ | 0 | 0 | 99,000.00 | √ |  | DA | NYA, T.A |
| SUB -TOTAL |  |  |  |  |  | 4,228,988.87 | 9,680.00 | 1,095,828.38 |  |  |  |  |
| SUB -TOTAL 2 |  |  |  |  |  | 4,455,538.87 | 9,680.00 | 1,095,828.38 |  |  |  |  |
| Goal: safeguard the natural environment and ensure a resilient built environment |  |  |  |  |  |  |  |  |  |  |  |  |
| Programmes 5. Mainstream emergency planning and preparedness into the District’s Development Planning agenda at all levels to respond to potential internal and external threats |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-programme 5.1: Disaster Prevention and Management |  |  |  |  |  |  |  |  |  |  |  |  |
| - Conduct integrated active case search bi-annually | 6-area councils | √ | √ | √ | √ | 0 | 0 | 7960 | √ |  | DHD | GHS |
| - Provide monthly and Quarterly feedback on integrated Disease Surveillance and Response (IDSR) to all facilities | 6-area council | √ | √ | √ | √ |  |  | 320 | √ |  | DHD | DA, GHS |
| - Timely collation and submission of IDSR reports to region | All facilities | √ | √ | √ | √ |  |  | 500 | √ |  | DHD | GHS |
| - Conduct Quarterly supervision and monitoring visits on IDSR to facilities | All facilities | √ | √ | √ | √ |  |  | 6520 | √ |  | DHD | GHS |
| - Conduct Public Health Emergency Management Committee meetings bi-annually | Kukuom | √ | √ | √ | √ |  |  | 700 | √ |  | DHD | GHS |
| - Train staff on appropriate sample taking techniques | Kukuom | √ | √ | √ | √ |  |  | 5280 | √ |  | DHD | DA, GHS |
| - Conduct active case search on BU, Yaws TB and Leprosy | All facilities | √ | √ | √ | √ |  |  | 1000 | √ |  | DHD | DA, GHS |
| - Sensitize clinicians and other health workers on TB case detection | Kukuom | √ | √ | √ | √ |  |  | 960 | √ |  | DHD | DA, GHS |
| - Strengthen contacts tracing and screening of contacts | All facilities | √ | √ | √ | √ |  |  | 5800 | √ |  | DHD | DA, GHS |
| - Organize education and Sensitizations on the causes and effects of natural disasters | Kukuom, Noberkaw, Kwapong, Sankore and Abuom | √ | √ | √ | √ |  | 2000 | 6,050.00 | √ |  | NADMO | DA, Assembly Members, EPA, Fire Service, TA |
| - Training of zonal coordinators, fire volunteer groups and other volunteer groups on firefighting techniques | Kukuom | √ |  | √ |  | 1,000.00 |  | 3,000.00 | √ |  | NADMO | DA, GNFS |
| - Support to disaster victims | 6-area councils | √ | √ | √ | √ |  | 0 | 24,200.00 | √ |  | NADMO | DA |
| - Organize Public education and sensitization on the prevention of wild fires, scooping, distilling, poaching, charcoal burning, etc. | Abuom,Kokooso,asarekrom kwapong, sankore | √ |  |  | √ |  | 6000 |  | √ |  | NADMO | DEHU Trad. Authorities, GNFS, FC |
| - Support to COVID-19 vaccination exercise | 6-area councils | √ | √ | √ | √ | 6,050.00 | 1,210.00 | 0 | √ | √ | GES | Cent Admin |
| - Embark on community education and sensitization programmes on COVID-19 vaccination | 6-area councils | √ | √ | √ | √ | 6,050.00 | 2,420.00 | 0 | √ | √ | Cent Admin | Comm Sub-Ct |
| SUB -TOTAL |  |  |  |  |  | 13,100.00 | 11,630.00 | 62,290.00 |  |  |  |  |
| Sub-programme 5.2: Natural Resource Conservation and Management |  |  |  |  |  |  |  |  |  |  |  |  |
| - Support to the regular visit and protection of the protected forest reserves in the district | Bonsam Bepo reserve, Abonwere reserve | √ | √ | √ | √ | 6,050.00 | 0 | 0 | √ | √ | FC | DA |
| - Organize regular education and sensitization programs, and monitor the activities of small-scale mining in the district | 6-area councils | √ | √ | √ | √ | 2,420.00 | 605 | 24,200.00 | √ | √ | DA | EPA, GPS, GIS, TA, Hon. Assembly Members |
| - Intensify the implementation of bye laws on the preservation of water bodies | 6-area councils | √ | √ | √ | √ | 11,000.00 | 0 | 5,500.00 | √ |  | DA, EPA | GPS, GIS, TA, Hon. Assembly Members |
| - Regular monitoring of the waterbodies against the activities of small-scale mining | 6-area councils | √ | √ | √ | √ | 12,100.00 | 0 | 6,050.00 | √ | √ | Pln Unit | EPA |
| - Intensify regulations and bye laws against illegal logging and hunting | 6-area councils | √ | √ | √ | √ | 6,050.00 | 605 | 0 | √ | √ | FC | DA, GPS |
| - Support and implement tree planting activities | 6-area councils |  | √ | √ |  | 6,050.00 | 1,210.00 | 0 | √ | √ | FC | ASDA, NADMO |
| - Implementation of the Ghana Productive Safety Net Project (GPSNP) | 6-area councils | √ | √ | √ | √ | 11,000.00 | 484 | 55,000.00 |  | √ | DA | MLGRD, World Bank, Consultants |
| - Support the Supply of improved and early maturing tree species seedlings | 6-area councils |  | √ | √ |  | 7,260.00 | 484 | 50,000.00 | √ | √ | FC | DDA, ASDA |
| - Organize radio talk shows on natural disasters and climate change | 6-area councils | √ | √ | √ | √ | 0 | 1,210.00 | 0 | √ | √ | FC | DA, DPCU, EPA, NCCE, TA |
| SUB -TOTAL |  |  |  |  |  | 61,930.00 | 4,598.00 | 140,750.00 |  |  |  |  |
| SUB -TOTAL 2 |  |  |  |  |  | 75,030.00 | 16,228.00 | 203,040.00 |  |  |  |  |
| GRAND TOTAL 2 |  |  |  |  |  | 12,358,189.73 | 293,265.00 | 2,296,608.17 |  |  |  | 14,948,062.90 |